## Tracker
S/N | Customer Name | Project Code | Project assignment Date | Scope | IKOM | EKOM | Country | WO# | SVC# | WO Type | SVC Type | WO Creation Date | Target RFS | Customer Request Date | ASE to SDE | SDE to DPE | DPE to OLLC | Provider | Bandwidth | Site Address | Local Site Contact Person details | Handoff interface | LSP/ Ref | OLLC PO Date | OLLC PO # | OLLC order Ack Date | OLLC Site Survey date | OLLC FOC date | Bill start date | OLLC BW | C+ BW / Port Speed | Activity Name | Weekly Status | Project Status
1 | DHL Global Forwarding | MGCA458S | 2023-12-08 | 1 x ISDN to SIP Trunk Migration. To migrate 45 blocks of ISDN DDI. With bundled access Meg@POP EthernetLink Access with Exchange Diversity (Active Active) With Load Sharing, 30 concurrent calls. | 2023-12-12 | 2023-12-14 | Singapore | Refer WO Tab |  |  |  | 2023-12-29 | 2024-01-22 | 2024-02-24 | NA | NA | NA | Domestic | 3M | DDC DHL Global Forwarding (Singapore) Pte Ltd No.1 Changi South Street 2, DHL Distribution Centre, Singapore 486760 | Mark Christian Gonzales Mark.Gonzales@dhl.com Alice Lee alice.lee@dhl.com +65 9788 8251 | Fiber | NA | NA | NA | NA | NA | NA |  |  |  |  | Feb 02: Migration requested on 24-Feb. Jan 22: Link activated, emailed DHL to start with pre-migration testing. Migration scheduled on 3-Feb. resources booked. Jan 16: Fiber for SIP Trunk provisoned and tested on 15-Jan. Target for ONT installation and link activation on 22-Jan. Jan 02: Site survey schedule on 4-Jan between 2pm - 4pm. Dec 29: WO raised. To arrange for site survey by 4-Jan. Dec 28: WO raising still in progress. Portback form pending from British telecommunication. Dec 15: IKOM done, EKOM done. WO raising in progress. Dec-08: Project assigned. IKOM scheduled on 12-Dec. | Green

## WO
| Customer Name | DHL GLOBAL FORWARDING (SINGAPORE) PTE. LTD.
| Project Code | MGCA458S
S.No | Product Description | Bw | Service Type | Service Order No | Order Type | Work Order No | Service No | Ex | A-End Installation Address | CRD | WO Status
1 | TS - DEL |  | TS - DEL |  | Cease | ZJX8325001 | 65427668 |  |  | 2024-01-08 | Closed
2 | Fibre To The Office |  | TS - FTTH |  | Provide | ZKV9813001 | 181660661 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-22 | Closed
3 | eLite for SIP Voice | 10000kbps | CN - Meg@pop Suite Of IP Services |  | Provide | ZKV9813002 | SIP00302461SNG | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-22 | Closed
4 | I-Phonenet Voice Portal - incoming |  | TS- I Phonenet |  | Provide | ZKV9813003 | 63599945 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-22 | Closed
5 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813004 | 64214900 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
6 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813005 | 64214901 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
7 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813006 | 64214902 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
8 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813007 | 64214903 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
9 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813008 | 64214904 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
10 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813009 | 64214905 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
11 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813010 | 64214906 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
12 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813011 | 64214907 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
13 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813012 | 64214908 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
14 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813013 | 64214909 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
15 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813014 | 64214910 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
16 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813015 | 64214911 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
17 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813016 | 64214912 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
18 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813017 | 64214913 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
19 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813018 | 64214914 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
20 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813019 | 64214915 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
21 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813020 | 64214916 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
22 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813021 | 64214917 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
23 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813022 | 64214918 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
24 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813023 | 64214919 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
25 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813024 | 64214920 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
26 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813025 | 64214921 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
27 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813026 | 64214922 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
28 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813027 | 64214923 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
29 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813028 | 64214924 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
30 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813029 | 64214925 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
31 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813030 | 64214926 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
32 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813031 | 64214927 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
33 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813032 | 64214928 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
34 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813033 | 64214929 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
35 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813034 | 64214930 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
36 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813035 | 64214931 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
37 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813036 | 64214932 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
38 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813037 | 64214933 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
39 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813038 | 64214934 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
40 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813039 | 64214935 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
41 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813040 | 64214936 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-22 | Closed
42 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813041 | 64214937 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
43 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813042 | 64214938 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
44 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813043 | 64214939 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
45 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813044 | 64214940 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
46 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813045 | 64214941 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
47 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813046 | 64214942 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
48 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813047 | 64214943 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
49 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813048 | 64214944 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
50 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813049 | 64214945 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
51 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813050 | 64214946 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
52 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813051 | 64214947 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-22 | Closed
53 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813052 | 64214948 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed
54 | SIP (Meg@POP) Exchange Line |  | Meg@POP SIP Trunking DDI |  | Provide | ZKV9813053 | 64214949 | CG | 1 AEI DISTRIBUTION CENTRE MAIN CHANGI SOUTH STREET 2 486760 | 2024-01-15 | Closed

## I-E KOM
2023-12-12 | Internal Kick Off Meeting | Location/ Time: Teams – 04:30 PM to 05:00 PM SGT
Attendees: | Singtel: Charles Toh, Sajiv Nair Mukandan, Alicia Liew Suan Ching, Muhammad Arief Ghazali, Revati Shirsaokar. | Absent with Apologies:
S/N | Topics | Type / Owner | Status | Date Due
1 | Scope: 1 x ISDN to SIP Trunk Migration
| Address: DDC - No. 1 Changi South Street 2, DHL Distribution Centre, Singapore 486760. | Info | NA | NA
Main Contact: Alice Lee ¦ +65 9788 8251 ¦ alice.lee@dhl.com
2 | Proposed CRD: 20-Dec (TBC) | Info | NA | NA
3 | Singtel:
Global Account Manager (AM): Charles Toh ¦ charles.toh@singtel.com ¦ +65 8031 6512
Solution Manager (CS) : Sajiv Nair Mukandan ¦ sajivnair.mukandan@singtel.com ¦ +60126600453
| Sector Lead: Kairav Mody kairavmody@singtel.com +65 91193673 | Info | NA | NA
Team Lead: Kushwant Mishra ¦ kushwant.mishra@singtel.com ¦ +91 8287227360
PM: Muhammad Arief Ghazali ¦ xv.muhammadarief.ghazali@singtel.com ¦ +60133880543
PC: Revati Shirsaokar xv.revati.shirsaokar@singtel.com +91 7977268336
4 | Points Discussed:
Scope
| SIP Trunking Service with Meg@POP eLite access with 30 concurrent calls. (ISDN to SIP Migration) | Info | NA | NA
SIP DDI Numbers (Block of 44 + 1 DEL 65427668)
6548 9400 - 6548 9699 (300 numbers) : Direct Absorption, no need number reservation.
6589 3300 - 6589 3399 (100 numbers) : Direct Absorption, no need number reservation.
6589 3400- 6589 3439 (40 numbers) : reservation of N2 mapping done.
1 DEL 65427668 + 9 other SIP numbers to complete set of (10 numbers) : reservation of N2 mapping done.
Migration
Customer request migration date on 20-Dec (TBC). Highly unlikely will be able to meet request date.
Customer to complete pre-migration testing before migration.
Voice team to book 2-weeks prior to firm migration date.
Others
WO raising in progress.
No diversity requirement.
5 | Action Items:
| EKOM arranged on 14-Dec with customer. | AM | Open
| Chase for WO raising. | PM/PC | Open | TBC
Contact and Escalation Matrix
Designation | Name | Role | Contact Number | Email
Project Manager | Muhammad Arief Ghazali | Customer Fronting | +60 133880543 | xv.muhammadarief.ghazali@singtel.com
Project Coordinator | Revati | Coordination and Support | +91 7977268336 | xv.revati.shirsaokar@singtel.com
PE Team Lead | Kushwant | 1st point of escalation for project related matters | +91 8287227360 | kushwant.mishra@singtel.com
Team Lead | Kairav Mody | 2nd point of escalation for project related matters | +65 91193673 | kairavmody@singtel.com
S/N | Description | Type | Mitigation/ Resolution Plan | Status | Date | Owner
| Delay in raising work orders and matching PO. | Risk | Delivery of the circuit may get delayed due to delay in work orders and matching PO/ AM, PM & PC to expedite the order raising requesting. | Open | 2023-12-15 | AM/ASE
1
Communication Plan
Sr.No | Description | Frequency | Mode
1 | Project Progress Update | As per the received updates | Email / Call
2023-12-14 | Project Kick Off Meeting | Location/ Time: Teams – 03:30 PM to 04:30 PM SGT
Attendees: | Alice (DHL), Mark (DHL), Felimon (DHL), Vishal (BT), Charles (Singtel), Alicia (Singtel), Arief (Singtel) | Absent with Apologies:
S/N | Topics | Type / Owner | Status | Date Due
1 | Scope: 1 x ISDN to SIP Trunk Migration
| Address: DDC - No. 1 Changi South Street 2, DHL Distribution Centre, Singapore 486760. | Info | NA | NA
Main Contact: Alice Lee ¦ +65 9788 8251 ¦ alice.lee@dhl.com
2 | Proposed CRD: 8th Jan 24 | Info | NA | NA
3 | Singtel:
Global Account Manager (AM): Charles Toh ¦ charles.toh@singtel.com ¦ +65 8031 6512
Global Account Manager (AM): Alicia Liew Suan Ching ¦ aliciasc@singtel.com ¦ +65 97847199
Solution Manager (CS) : Sajiv Nair Mukandan ¦ sajivnair.mukandan@singtel.com ¦ +60126600453
| Sector Lead: Kairav Mody kairavmody@singtel.com +65 91193673 | Info | NA | NA
Team Lead: Kushwant Mishra ¦ kushwant.mishra@singtel.com ¦ +91 8287227360
PM: Muhammad Arief Ghazali ¦ xv.muhammadarief.ghazali@singtel.com ¦ +60133880543
PC: Revati Shirsaokar xv.revati.shirsaokar@singtel.com +91 7977268336
4 | Points Discussed:
SIP Trunking Service with Meg@POP eLite access with 30 concurrent calls. (ISDN to SIP Migration)
SIP DDI Numbers (Block of 44 + 1 DEL 65427668)
| 6548 9400 - 6548 9699 (300 numbers) : Direct Absorption, no need number reservation. | Info | NA | NA
6589 3300 - 6589 3399 (100 numbers) : Direct Absorption, no need number reservation.
6589 3400- 6589 3439 (40 numbers) : reservation of N2 mapping done.
440 numbers to be ported over from Starhub.
Revision of porting form as details in form required from rightful owner (BT).
Any technical clarifications on the integration guide and process, BT can send query via email and Singtel will help to direct the queries to Voice/Engineering team.
Migration to be implemented in Jan-24, target by 8-Jan.
5 | Action Items:
| Revision of Porting Form | BT | Open
| BT to send technical queries and clarifications on the integration guide/process. | BT | Closed | TBC
| Singtel to chase for internal WO raising and proceed with SIP trunk provisioning | Singtel | Open
Contact and Escalation Matrix
Designation | Name | Role | Contact Number | Email
Project Manager | Muhammad Arief Ghazali | Customer Fronting | 60133880543 | xv.muhammadarief.ghazali@singtel.com
Project Coordinator | Revati | Coordination and Support | +91 7977268336 | xv.revati.shirsaokar@singtel.com
PE Team Lead | Kushwant | 1st point of escalation for project related matters | +91 8287227360 | kushwant.mishra@singtel.com
Team Lead | Kairav Mody | 2nd point of escalation for project related matters | +65 91193673 | kairavmody@singtel.com
S/N | Description | Type | Mitigation/ Resolution Plan | Status | Date | Owner
1 | Delay in raising work orders. | Risk | Delivery of the circuit may get delayed due to delay in work orders AM, PM & PC to expedite the order raising requesting. | Open |  | Singtel
Communication Plan
Sr.No | Description | Frequency | Mode
1 | Project Progress Update | As per the received updates | Email / Call

## WBS
Work Breakdown Structure (WBS)
| Milestones | Activity Start Date | Target Completion Date | Current Status | Remark
1 | Project Assignment | 2023-05-09 | - | Completed
2 | WO Raising | 2023-05-30 | 2023-05-30 | Completed
3 | Site Survey | 2023-06-19 | 2023-06-19 | Completed
4 | Fiber Planning & Implementation |  |  | Pending
5 | Customer Site Readiness (RFS) |  |  | Pending
6 | SIP Trunking Provisioning |  |  | Pending
7 | Migration |  |  | Pending
8 | Link Handover | - | 2023-06-30 | Pending
Work Breakdown Structure (WBS)
| Milestones | Activity Start Date | Target Completion Date | Current Status | Remark
1 | Internal Order Processing | 2023-05-30 | 2023-06-09 | Completed
2 | Site Survey | 2023-06-12 | 2023-06-19 | Completed
3 | Fibre Planning & Implementation | 2023-06-20 | 2023-06-27 | Completed
4 | SIP Trunking Provisioning | 2023-06-28 | 2023-06-29 | Completed
5 | Link Handover |  | 2023-06-30 | Completed
6 | Siltronics - Link Testing |  | 2023-07-05 | Pending | To be advised by Siltronics
7 | Migration |  | 2023-07-20 | Pending
USE THIS ONE
Work Breakdown Structure (WBS)
| Milestones | Activity Start Date | Target Completion Date | Current Status | Remark
1 | Project Assignment | 2023-12-08 | 2023-12-08 | Completed
2 | Internal Order Processing | 2023-11-27 | 29-Dec-23 | Completed
3 | Project Kick Off | 2023-12-14 | 2023-12-14 | Completed
4 | Porting Form endorsement from BT | 2023-12-14 | 2024-01-05 | Completed
5 | Site Survey | 4-Jan-24 | 4-Jan-24 | Completed | 2-4 PM
6 | Fiber Planning & Implementation | 4-Jan-24 | 2024-01-12 | Completed
7 | SIP Trunk Provisioning and Testing | 15-Jan-24 | 2024-01-15 | Completed
8 | ONT Installation & Circuit Activation | 2024-01-22 | 2024-01-22 | Completed | 9AM – 11AM
8 | Pre-Migration Testing (DHL/BT) | 2024-01-23 | 2024-02-24 | On going
9 | Migration | 2024-02-24 | 2024-02-24 | To Be Initiated | Subject to Pre-migration testing completion.
Starting 10:30 AM

## Stakeholder
Company | Position | Name | Tel | Email | Remark
Singtel | AM | Charles Toh | +65 8031 6512 | charles.toh@singtel.com
| CS | Sajiv Nair Mukandan | 60126600453 | sajivnair.mukandan@singtel.com
| AM | Alicia Liew Suan Ching | +65 9784 7199 | aliciasc@singtel.com
DHL | Main Contact | Alice Lee | +65 9788 8251 | alice.lee@dhl.com
| Site Contact | Mark Christian Gonzales |  | Mark.Gonzales@dhl.com

## SIP Trunk Process
SIP Trunking Provision/Pre-Migration Process
1.Provisioning SIP Trunking
a.(Total lead time T+15WD) (T: order raised)
a.GSP (CRD - 3WD)
b.IPCTX (CRD – 5WD)
b.On CRD SIP trunking service, Pilot and Numbers (Test Number) Active for customer testing.
2.Sales raise Cease order for ISDN numbers, CRD: migration date
3.Sales book Migration date with Engineering Tracy/Alvin 14WD prior to migration date
4.Up SIP Trunking Service provision, customer can start Integration and testing based checklist : Customer
a.Customer integration of their PBX/SBC to SIP Trunk (Customer Responsibility)
i.Reference to SRCA form on recommended PBX/SBC configuration
ii.When customer encounter issues with integration
1.Customer will need to open ticket with TAC and provide the list of information (refer to slide 3)
2.Because IPCTX will take some time to check on the calls and error encountered on Singtel end
3.Customer can request for conference call with FVO to troubleshoot if Operation confirmed the Option ping (Application layer) is OK(at least 1 day notice) on a case by case basis subjected to FVO’s availability.
4.FVO will assist in the troubleshooting session and duration should keep within 30mins to 1hr during office hour
b.Pre-migration Testing/checklist has to be completed by Customer and to revert to Sales at least 3 WD prior to migration date with completed checklist, sales to submit the completed checklist to Tracy, Alvin.
c.If Checklist incomplete Migration to be rescheduled by Sales, Sales to get new migration date from customer and update Tracy and Alvin
Information Required for Voice Troubleshooting
Customer can make a Sample Call and provide the following information
a)Called number
b)Calling number (complete dialling pattern)
c)Date/time encountered, number of occurrences
d)Impact of the fault, affect all users or selected users
e)Actual nature of problem encountered
f)SIP Session Logs or Wireshark trace that was captured from customer's gateway/SBC/or other devices, which shows the fault.
g)Router and SIP Device information such as brand and model number.
h)Customer's SIP loopback IP address. Is customer's SIP gateway device able to ping Singtel SIP headend or not?
SIP trunking Migration Process
1.Number Migration
a.ISDN >> SIP Migration (2 hours down)
i.Exchange Team will bring down number from ISDN switch
ii.IPCTX will provision/mapping of ISDN N1 Number to SIP N2 number numbers on BroadSoft
1.Absorption: Provisioning of ISDN number (block of 100 numbers) to BroadSoft
2.Number Retention (NRS) Mapping of ISDN number (N1) to SIP Number (N2)
iii.Upon completion IPCTX will update completion of Migration to customer
2.Post Number Migration
a.Customer testing of Number on the migration date.
i.If encounter issue inform SPOC (Sales/AM/PM).
b.Customer to inform the migration teams to standdown once testing completed.
3.Order taker raise covering Order to provision number to SIP in Pegasus
Roles & Responsibilities
Customer needs to complete Checklist for SIP Readiness to ensure SIP integration to customer's PBX/CPE is complete.
Customer needs to provide required documents/information:
•NRS Mapping
•SIP Absorption List
•Migration Batches and date time of execution
Migration Planner:
•Tracy Tang <tracy.tang@singtel.com>
•Alvin Sze Toh <alvinst@singtel.com>
Migration Operation POC:
•Alvin Sze Toh alvinst@singtel.com
•Networks - FNE / Voice Opns.VAS-IPCTX NWVOIPCTX@singtel.com
•Network - VO - OCNGN g-ocngn@singtel.com
•Network - VO - LNGN - NGN – JO ml-ngnjo@singtel.com
•SingtelIN g-singtelin@singtel.com
Customer Issues
Voice:
•Networks - FNE / Voice Opns.VAS-IPCTX <NWVOIPCTX@singtel.com>
•IC: Calissa Lim Siow Leng calissa@singtel.com / Chew Peng Kheng pkchew@singtel.com
Meg@POP Access:
•GSP . Megapop <IPDENMGMC@singtel.com>
•IC: Sazlina Sahir <sazlina@singtel.com>
Escalation:
•ML-EDMS - TAC - ODC - Megapop1.5 ml-edmstac@singtel.com
•TAC IP <g-gnocc@singtel.com>

## My Note
| Basic Project Information | DHL Global Forwarding
1 | Led by GAM | EAG1
2 | ISAM | Charles Toh
3 | Solutions Manager | Sajiv Nair Mukandan
4 | Project Manager | To be assigned
5 | SDE | To be assigned
6 | Service to Provide | ISDN to SIP Migration
7 | Scope of Work |  | To port back 440 numbers from Starhub to Singtel SIP (new megapop elite 30cc trunk with caller ID).
|  | To migrate 55 blocks of ISDN DDI. | To migrate 1 DEL 65427668 number to Singtel SIP.
With bundled access Meg@POP EthernetLink Access with Exchange Diversity (Active Active)
|  | With Load Sharing, 30 concurrent calls. | 6548 9400 - 6548 9699(300 numbers) : Direct Absorption, no need number reservation
6589 3300 - 6589 3399 (100 numbers) : Direct Absorption, no need number reservation
Migration in 1 phase
|  | Target CRD Nov/Dec 2023 | 6589 3400- 6589 3439 (40 numbers) : reservation of N2 mapping done.
|  | Target RFS: 20 Dec 2023 | 1 DEL 65427668 + 9 other SIP numbers to complete set of (10 numbers) : reservation of N2 mapping done.
Note: N2 Numbers: 64214900 to 64214949 (50) Number reserved for 3 months.
8 | OLLC providers | NA
9 | Router provided by | -
10 | Any RMS | NA
11 | No. of site/link
12 | Proposed CRD of the sites | 20 Dec 2023
13 | Have your follow the Standard Lead Time as per GA guidelines | YES
14 | Intended 1st internal Kickoff Meeting date | To be managed by PM
15 | Order submitted to SDE | Not yet
16 | Customer signed SCRA | Not yet
17 | Provided Network Diagram | Yes but not confirmed by customer yet
3 Years term
441 numbers
first 441 belongs to Starhub
port back from Starhub - Portback form
6548 9400 - 6548 9699 (300 numbers) : Direct Absorption, no need number reservation
6589 3300 - 6589 3399 (100 numbers) : Direct Absorption, no need number reservation
6589 3400- 6589 3439 (40 numbers) : reservation of N2 mapping done.
1 DEL 65427668 + 9 other SIP numbers to complete set of (10 numbers) : reservation of N2 mapping done.