## Tracker
S/N | Customer | Prime PM | PE | PC | Project Code | Scope | Country | Site ID | main / Link a / Link b | A-End : Installation Address | Exch | B-End : Installation Address | Exch | Customer Contact/Email | BW | Product Desc | Order Type | Standard/Express | Service Reference | Workorders | QH Ref | Standard/ ED/PD | WAN IP Singtel | WAN IP Customer | LAN IP Segment | WO raised date | Customer Request Date | FDD Date | RFS Date | Migration Date | Order Matching Ref | Order Matching Date | Partner/LSP name | POP name | FOC Received Date | FOC date | Equipment PO Date | PO/SO Ref | Equipment Vendor Name | Equipment Type / Model | Equipment ETA Date | Survey Date | IB date | UG date | Mux Installation | SO Date for CPE | Router ETA Received Date | ETA for CPE | CPE Model | Equipment TD Name | CPE Installation date | Link Activation date | LSP circuit reference | LSP bill start date | VPN | AS# | Work Order status | Bill start date | Cease Workorders | Cease Service Reference | Cease Date | Cease Order Status | Issue Category | Issue Owner | Issue Date | Customer / Sales Escalated Case (Y/N) | Updates
1 | Fujitsu Asia Pte Ltd | Ki Kit Fan | Arief Ghazali | Hamizan | MGHA431S | 1 x C+ IPVPN Parallel Relocation with CPE/RMS | Hong Kong |  |  | Current: 10/F, Kerry Tsuen Wan Godown, 3 Shing Yiu Street, Kwai Chung, Hong Kong New: 10/F, Kerry Tsuen Wan Godown, 3 Shing Yiu Street, Kwai Chung, Hong Kong (Singtel rack 2724 at Equinix HK2) |  | Current: FLAT 118, 1/F, PHILIPS ELECTRONICS BLDG, 5 SCIENCE PARK EAST, HONG KONG SCIENCE PARK, SHA TIN. New: Tseung Kwan O Industrial Estate, Rack (Ground floor MMR, Rack GF13.08), 2 Chun Yat Street, New Territories, Hong Kong |  | Ng Ah Yong 69915671 ahyong.ng@fujitsu.com | 16000kbps 16000kbps | CN - ConnectPlus IP VPN CN - ConnectPlus IP VPN Resale of Overseas Data Svcs Resale of Overseas Data Svcs CPE Router Mgmt Svc | Cease Provide Cease Provide Change Change | Std | 00155354HKG 00302049HKG HKG0000023351LLC HKG0000040844LLC FDO2212A0ER RMS0000034142 | ZKJ0650001 ZKJ0650002 ZKJ0650003 ZKJ0650004 ZLA5665001 ZLA5665003 | STD-2308-02278-0.6 |  |  |  |  | 2023-12-13 | 2024-01-27 |  | 2024-01-26 | Target 27/1/2024 | STPCGHKY23335 | 2023-12-14 | PCCW | Equinix HK2 |  |  | 2024-01-11 | SO# 7680029058 |  | Cisco Router | n/a | 2024-01-10 |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | [5 empty] | Open | 2024-01-27 | ZKJ0650001 ZKJ0650003 | 00155354HKG HKG0000023351LLC | 2024-02-01 | Closed |  |  |  |  | Feb 01: Old circuit terminated on 1-Feb. Jan 27: Relocation and cutover completed on 27-Jan. WO COMQ initiated Jan 05: Awaiting survey date from LSP. LSP acknowledge RFS on 27-Jan. Dec 28: Awaiting survey date from LSP. LSP acknowledge RFS on 27-Jan. Dec 21: EKOM done. LSP assigned PM. Awaiting firm survey date from LSP. Dec 15: Matching order placed. Customer request RFS on 28-Jan. EKOM arranged on 18-Dec. Dec 14: IKOM done. Wo raised. Matching order placed. PO/SO awaited for router. To arrange for EKOM. Dec 07: Project assigned. IKOM to be scheduled on 11-Dec.
Note on AJ1: INTL Firm order date
Note on AV1: INTL
Note on AZ1: Customer Premise Equipment

## WO
Customer Name |  | Fujitsu
Project Code
S/N | Work Order No | Service No | Order Type | Product Description | Bw | Service Type | Service Order No | Pegasus RFS Date | Ex | A-End Installation Address | Ex | B-End Installation Address | WO Status
1 | ZKJ0650001 | 00155354HKG | Cease | ConnectPlus IP - VPN Broadband Port | 16000kbps | CN - ConnectPlus IP VPN |  | 2024-02-01 |  |  |  |  | Closed
2 | ZKJ0650002 | 00302049HKG | Provide | ConnectPlus IP - VPN Broadband Port | 16000kbps | CN - ConnectPlus IP VPN |  | 2024-01-27 | TP | RACK (GROUND FLOOR MMR. TSEUNG KWAN O INDUSTRIAL ESTATE. |  |  | Closed
3 | ZKJ0650003 | HKG0000023351LLC | Cease | Singtel Hong Kong LLC |  | Resale of Overseas Data Svcs |  | 2024-02-01 |  |  |  |  | Submitted
4 | ZKJ0650004 | HKG0000040844LLC | Provide | Singtel Hong Kong LLC |  | Resale of Overseas Data Svcs |  | 2024-01-27 | TP | RACK (GROUND FLOOR MMR. TSEUNG KWAN O INDUSTRIAL ESTATE. |  |  | Closed
5 | ZLA5665001 | FDO2212A0ER | Change | Rental Of CPE |  | CPE |  | 2024-01-27 | TP | RACK (GROUND FLOOR MMR. TSEUNG KWAN O INDUSTRIAL ESTATE. |  |  | Closed
6 | ZLA5665003 | RMS0000034142 | Change | Router Management Service for C+ IP |  | Router Mgmt Svc |  | 2024-01-27 | TP | RACK (GROUND FLOOR MMR. TSEUNG KWAN O INDUSTRIAL ESTATE. |  |  | Closed
| ZKJ0650005 | RMS0000034142 | Cease | Router Management Service for C+ IP |  | Router Mgmt Svc |  | 2024-02-09 |  |  |  |  | Cancelled
| ZKJ0650006 | RMS0000050173 | Provide | Router Management Service for C+ IP |  | Router Mgmt Svc |  | 2024-01-31 | TP | RACK (GROUND FLOOR MMR. TSEUNG KWAN O INDUSTRIAL ESTATE. |  |  | Cancelled
| ZKJ0650007 | FDO2212A0ER | Cease | Rental Of CPE |  | CPE |  | 2024-02-09 |  |  |  |  | Cancelled
| ZKJ0650008 |  | Provide | Rental Of CPE |  | CPE |  | 2024-01-31 | TP | RACK (GROUND FLOOR MMR. TSEUNG KWAN O INDUSTRIAL ESTATE. |  |  | Cancelled

## WBS
Work Breakdown Structure (WBS)
| Milestones | Activity Start Date | Target Completion Date | Current Status | Remark
1 | Project Assignment | 2023-12-04 | 2023-12-04 | Completed
2 | Internal Order Processing | 2023-12-04 | 13-Dec-23 | Completed
3 | External Kick Off Meeting | 2023-12-18 | 2023-12-18 | Completed
4 | Order Placement to Local Service Provider | 2023-12-19 | 2023-12-19 | Completed
5 | Site Survey | 10-Jan-24 | 10-Jan-24 | Completed
6 | Demarcation Details provided to Fujitsu | 2024-01-15 | 2024-01-15 | Completed
7 | Cross Connect Readiness | 2024-01-25 | 2024-01-25 | Completed
8 | Fibre Circuit Installation & Testing | 2024-01-26 | 2024-01-26 | Completed
9 | Migration | 2024-01-27 | 2024-01-27 | Completed

## Stakeholders
Company | Position | Name | Tel | Email | Remark
Singtel | AM | David Wee |  | david.wee@singtel.com
| SGO | Swlok Man | +852 91511500 | swlok.man@singtel.com
| SGO | Dave Szeto |  | dave.szeto@singtel.com
| CS | Fey Loong Mak |  | feyloong.mak@singtel.com
Fujitsu (Customer) | Main Contact | Ng Ah Yong | 69915671 | ahyong.ng@fujitsu.com
| Site Contact | Alistair Lam | +852 3910 8171 | alistair.lam@fujitsu.com
| Site Contact | Michael Tam | +852 6809 8900
PCCW (LSP) | PM | Manna Biplab | (+852) 9745 0975 | bmanna@pccwglobal.com
| Sales | Helen Tan |  | hshtan@pccwglobal.com

## I-E KOM
2023-12-11 | Internal Kick Off Meeting | Location/ Time: Teams – 4:00 PM to 4:30 PM SGT
Attendees: | Singtel: David Wee, Fey Loong Mak, Muhammad Arief Ghazali, Revati Shirsaokar. | Absent with Apologies:
S/N | Topics | Type / Owner | Status | Date Due
1 | Scope: 1 x C+ IPVPN Parallel Relocation with CPE/RMS.
| Current Address: | Info | NA | NA
FLAT 118, 1/F, PHILIPS ELECTRONICS BLDG, 5 SCIENCE PARK EAST, HONG KONG SCIENCE PARK, SHA TIN.
Relocation Address:
Tseung Kwan O Industrial Estate, Rack (Ground floor MMR, Rack GF13.08), 2 Chun Yat Street, New Territories, Hong Kong.
Main Contact: Ng Ah Yong ¦ +65 69915671 ¦ ahyong.ng@fujitsu.com
Main Contact: Alistair Lam ¦ +852 3910 8171 ¦ alistair.lam@fujitsu.com
2 | Proposed CRD: 31-Jan-24 | Info | NA | NA
3 | Singtel:
Global Account Manager(AM): David Wee ¦ david.wee@singtel.com ¦ +65 96471399
Solution Manager (CS) : Fey Loong Mak ¦ feyloong.mak@singtel.com ¦
Sector Lead: Kairav Mody ¦ kairavmody@singtel.com ¦ +65 91193673
| Team Lead: Kushwant Mishra ¦ kushwant.mishra@singtel.com ¦ +91 8287227360 | Info | NA | NA
PM: Muhammad Arief Ghazali ¦ xv.muhammadarief.ghazali@singtel.com ¦ +60 133880543
PC: Revati Shirsaokar ¦ xv.revati.shirsaokar@singtel.com ¦ +91 7977268336
4 | Points Discussed:
Scope:
Parallel relocation of Hong Kong local loop circuit (Existing OLLC ID: HKG0000023351LLC)
| To provide new PE port (Existing Port ID: 00155354HKG) | Info | NA | NA
Existing CPE to be reused (Existing CPE ID: FDO2212A0ER) (Existing RMS ID: RMS0000034142)
Migration:
Target 31-Jan-24, after office hours (TBC).
Existing WAN IP to be retained.
LSP to test link with Dummy IP prior to migration.
Others:
Matching order have not issued yet.
WO raising in progress.
To engage CPE team to align on assigned TM/TD.
5 | Action Items:
| To arrange EKOM with customer. Check availability of customer. | PM | Open
| Chase SDE for WO raising. | PC/PM/AM | Open
| Chase DPE for order matching. | PC/PM | Open | TBC
| Engage CPE team for TM/TD assignment. | PM | Open
Contact and Escalation Matrix
Designation | Name | Role | Contact Number | Email
Project Manager | Muhammad Arief Ghazali | Customer Fronting | +60 133880543 | xv.muhammadarief.ghazali@singtel.com
Project Coordinator | Revati | Coordination and Support | +91 7977268336 | xv.revati.shirsaokar@singtel.com
PE Team Lead | Kushwant | 1st point of escalation for project related matters | +91 8287227360 | kushwant.mishra@singtel.com
Team Lead | Kairav Mody | 2nd point of escalation for project related matters | +65 91193673 | kairavmody@singtel.com
S/N | Description | Type | Mitigation/ Resolution Plan | Status | Date | Owner
| Delay in raising work orders and matching PO. | Risk | Delivery of the circuit may get delayed due to delay in work orders and matching PO/ AM, PM & PC to expedite the order raising requesting. | Open | 2023-12-22 | AM/ASE
1
2 | Lack of resources for TD to support activity | Risk | Engage with TM early for heads up on the schedule relocation. | Open | 2023-12-29 | PM
Communication Plan
Sr.No | Description | Frequency | Mode
1 | Project Progress Update | As per the received updates | Email / Call
2023-12-18 | Project Kick Off Meeting | Location/ Time: Teams – 11:00 AM to 11:30 AM SGT
Attendees: | Fujitsu: Matthew Yim | Absent with Apologies:
Singtel: David Wee, Fey Loong Mak, Revati Shirsaokar & Arief Ghazali.
S/N | Topics | Type / Owner | Status | Date Due
1 | Scope: 1 x C+ IPVPN Parallel Relocation with CPE/RMS.
| Current Address: | Info | NA | NA
FLAT 118, 1/F, PHILIPS ELECTRONICS BLDG, 5 SCIENCE PARK EAST, HONG KONG SCIENCE PARK, SHA TIN.
Relocation Address:
Tseung Kwan O Industrial Estate, Rack (Ground floor MMR, Rack GF13.08), 2 Chun Yat Street, New Territories, Hong Kong.
Main Contact: Ng Ah Yong ¦ +65 69915671 ¦ ahyong.ng@fujitsu.com
Matthew Yim ¦ matthew.yim@fujitsu.com
Local Contact: Alistair Lam ¦ +852 3910 8171 ¦ alistair.lam@fujitsu.com
2 | Proposed CRD: 27-Jan 24 | Info | NA | NA
3 | Singtel:
Global Account Manager(AM): David Wee ¦ david.wee@singtel.com ¦ +65 96471399
Solution Manager (CS) : Fey Loong Mak ¦ feyloong.mak@singtel.com ¦
Sector Lead: Kairav Mody ¦ kairavmody@singtel.com ¦ +65 91193673
| Team Lead: Kushwant Mishra ¦ kushwant.mishra@singtel.com ¦ +91 8287227360 | Info | NA | NA
PM: Muhammad Arief Ghazali ¦ xv.muhammadarief.ghazali@singtel.com ¦ +60 133880543
PC: Revati Shirsaokar ¦ xv.revati.shirsaokar@singtel.com ¦ +91 7977268336
4 | Points Discussed:
Scope:
Parallel relocation of Hong Kong local loop circuit (Existing OLLC ID: HKG0000023351LLC).
| To provide new PE port (Existing Port ID: 00155354HKG). | Info | NA | NA
Existing CPE to be reused (Existing CPE ID: FDO2212A0ER) (Existing RMS ID: RMS0000034142).
Migration:
Target 27-Jan-24, Time TBC. To aligned with LSP timeline.
Existing WAN IP to be retained.
LSP to test link with Dummy IP prior to migration.
Ping test to be done from Singapore site to HK site as well.
Others:
LSP is PCCW
Old link termination will be 1-week after migration.
Singtel to share update on progress weekly via email.
Refer slides discussed during call as attached.
5 | Action Items:
| To send weekly progressive update to Fujitsu Team. | Singtel | Open | TBC
| To arrange site survey soon once order to LSP processed and accepted. | Singtel | Open
Contact and Escalation Matrix
Designation | Name | Role | Contact Number | Email
Project Manager | Muhammad Arief Ghazali | Customer Fronting | 60133880543 | xv.muhammadarief.ghazali@singtel.com
Project Coordinator | Revati | Coordination and Support | +91 7977268336 | xv.revati.shirsaokar@singtel.com
PE Team Lead | Kushwant | 1st point of escalation for project related matters | +91 8287227360 | kushwant.mishra@singtel.com
Team Lead | Kairav Mody | 2nd point of escalation for project related matters | +65 91193673 | kairavmody@singtel.com
S/N | Description | Type | Mitigation/ Resolution Plan | Status | Date | Owner
1 | Delay in raising work orders. | Risk | Delivery of the circuit may get delayed due to delay in work orders AM, PM & PC to expedite the order raising requesting. | Closed | 2023-12-18 | Singtel
Communication Plan
Sr.No | Description | Frequency | Mode
1 | Project Progress Update | As per the received updates | Email / Call

## Note
PM Assingment
Basic Project Information:
1 | Led by SGO/GAM/Enterprise/Biz Sales/Carrier Sales/Optus | GB2
2 | Account Manager | David Wee
3 | Solutions Manager | Mak Fey Loong
4 | Project Manager | TBA
5 | SDE | TBA
6 | Service Provide | 1. ConnectPlus IP-VPN Port
ID: 00155354HKG
Inclusive:
ConnectPlus IP-VPN Premium Real Time Upgrade (HKG)
ConnectPlus IP-VPN Buffet Class of Service
2. OLLC ID: HKG0000023351LLC
3. RMS Enhanced ID: RMS0000034142
4. Managed CPE ID: FDO2212A0ER
5. CPE RELOCATION (Non-Standard Hour)
7 | Scope of Work | WO Instruction
1. Parallel relocate of HK local end circuit
|  | 2. Relocation of existing Managed CPE | Old IP will retain
8 | Installation Address | Present circuit address : | To test with Dummy Ip
FLAT 118, 1/F, PHILIPS ELECTRONICS BLDG, 5 SCIENCE PARK EAST, HONG KONG SCIENCE PARK, SHA TIN
Relocation circuit address :
Tseung Kwan O Industrial Estate, Rack (Ground floor MMR, Rack GF13.08), 2 Chun Yat Street, New Territories, Hong Kong
9 | FDD Date | 16 Feb 2024, after-office hours (TBC)
10 | Any customisation? | No
11 | If customisation is yes, provide customisation portal number #. | No
12 | OLLC providers | Maintain existing | Partner | PCCW
13 | Router provided by | Customer
14 | Any RMS | YES
15 | No. of site/link | 1
16 | Proposed CRD of the sites | 16 Feb 2024, after-office hours (TBC) | 31st Jan 2024.
17 | Have you followed the Standard Lead Time as per GA guidelines | YES
18 | Intended 1st internal Kick-off Meeting date | PM to advice
19 | Order submitted to SDE | In progress.
20 | Customer signed SCRA | Please refer attached
21 | Provided Network Diagram | @Fey Loong Mak Please help provide the Network Diagram
Quote ID (QH) = STD-2308-02278-0.6
|  |  |  | Staff No. | Name | Mobile | ID NO.
|  |  |  | 1604529 | NG WAI HUNG TONY | 92190542 | C629
|  |  |  | 1504836 | CHUNG WAI MAN | 63891550 | K897
|  |  |  | 1518679 | MAK LOK KI | 55434728 | Y520
|  |  |  | 441196 | CHAN YU HANG | 61575744 | K443
|  |  |  | 2010842 | CHOI MUK CHUNG | 63820298 | G801
|  |  |  | 2007242 | HO TSZ NGONG | 60283669 | Z735
|  |  |  | 1558584 | YIU YU | 54988584 | R288
|  |  |  | SWC0206 | LAI CHI MING | 51883219 | C447
|  |  |  | SWC0205 | YIP HOI CHE | 68029140 | C624
|  |  |  | 1176478 | CHAN YIN SUM | 66212961 | P029