## Gantt Chart - Beta (hidden)
2022-08-08
| Project Start Date: | 2022-08-08 | [5 empty] | 2022-08-08 |  |  |  | 2022-09-05 |  |  |  |  | 2022-10-03 |  |  |  |  | 2022-11-07
| Project #: |  | Date Updated: |  |  |  | Week Starting: | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21
# | Activity | Start Date | End Date | Owner | Days | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
1 | Task1 | 2022-08-08 | 2022-08-08 |  | 1 | bar: 2022-08-08
2 | Task2 | 2022-08-10 | 2022-08-29 |  | 14 | bar: 2022-08-29
3 | Task3 | 2022-08-30 | 2022-09-01 |  | 14 | bar: 2022-08-29
4 | Task4 | 2022-09-02 | 2022-09-20 |  | 3 | bar: 2022-08-29
5 | Task5 | 2022-08-30 | 2022-09-20 |  | 13 | bar: 2022-09-19
6 | Task6 | 2022-09-21 | 2022-09-22 |  | 16 | bar: 2022-09-19
2 | bar: 2022-09-19
To be initiated
Work in Progress
Completed
2022-10-05
Formulas:
Days = IF([End Date]="","",NETWORKDAYS([Start Date],[End Date]))
Days = IF([End Date, row above]="","",NETWORKDAYS([Start Date, row above],[End Date, row above]))
Start Date = WORKDAY([End Date, row above],1)
Note on B49: Hashim Aslam: formula for today's date
Note on B51: Hashim Aslam: formula for Gantt Chart
Note on B53: Hashim Aslam: formula for % completed
Note on B55: Hashim Aslam: formula for task Completed

## AIR Register (hidden)
IF(COUNTIFS($H$7:$H$21,$AM10,$I$7:$I$21,$AN$9)=0,"",COUNTIFS($H$7:$H$21,$AM10,$I$7:$I$21,$AN$9))
AIR REGISTER
Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-07-30 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
# | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
1 | Description1 |  | Issue |  |  | Very High | Very High | Critical | [6 empty] | Action Item |  |  | Very High | Low | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk | Issue
2 | Description2 |  | Issue |  |  | Medium | Very High | Critical | [6 empty] | Issue |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High | Very High
3 | Description3 |  | Risk |  |  | Very High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Very High | Critical |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High | High
4 | Description4 |  | Action Item |  |  | Low | Medium | Moderate | [6 empty] | Issue |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium | Medium
5 | Description5 |  | Issue | [23 empty] | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
6 | Description6 |  | Risk | [23 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
7 | Description7
8 | Description8 | [35 empty] | Action Item | Issue | Risk | Issue
9 | Description9 | [35 empty] | Very High | Very High | Very High | Very High
10 | Description10 | [35 empty] | High | High | High | High
11 | Description11 | [35 empty] | Medium | Medium | Medium | Medium
12 | Description12 | [35 empty] | Low | Low | Low | Low
13 | Description13 | [35 empty] | Very Low | Very Low | Very Low
14 | Description14 | [35 empty] | NIL | NIL | NIL
15 | Description15
Inherent Impact Matrix |  | Date Last Updated: | 2023-07-30 |  |  |  | Action Items | Issues | Risk
Impact: |  | Very Low | Low | Medium | High | Very High | 1 | 3 | 2
Probability | Very High |  |  |  |  | 2
High
| Medium |  |  |  |  | 1
| Low |  |  | 1
Very Low
Residual Impact Matrix |  | Date Last Updated: | 2023-07-30 |  |  |  | Action Items |  | Issues |  | Risks
Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open
Probability | Very High |  | 1 |  |  | 1
High
| Medium |  | 1
Low
Very Low

## Dashboard Tracker - Template (hidden)
2024-02-09
Summary Tab catalyst
Site ID | Scope | QH# | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing Completed and Handed Over | Testing and Handed Over | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD | Target RFS | CRD | Work orders to be closed | Timeline | % completed
|  |  | 2023-08-18 | NA | 2023-08-29 | 2023-09-26 | 2023-09-28 | 2023-09-29 | [19 empty] | TIMELINES |  |  |  | AIR REGISTER
| #REF! | #REF! | COMPLETED | NA | WIP | WIP | WIP | WIP | [8 empty] | AGGRESSIVE | 0% | [10 empty] | EXTERNAL DEPENDENCIES | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: |  |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[20 empty] | Site ID | Project Assigned | Target RFS | [7 empty] | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | #REF! | #REF! | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | 2023-08-15 | [10 empty] | 1 |  |  | Action Item |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[32 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[32 empty] | 5 |  |  | Risk |  |  | High | Very Low | [7 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | #REF! | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[32 empty] | 6 |  |  | Issue |  |  | High | Very Low | [7 empty] | Issue |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[20 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [6 empty] | 7 |  |  | Issue |  |  | Low | Medium | [7 empty] | Action Item |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED
|  | RFS Analysis | [16 empty] | WBS | Order Processing | COMPLETED | [10 empty] | 8 |  |  | Action Item |  |  | High | High | Critical | [6 empty] | Issue |  |  | Low | Medium | [5 empty] | OPEN | [11 empty] | Action Item | Issue | Risk
|  | Days required for Admin Works | 5 | [16 empty] | Access Clearance for Site Survey | NA | [10 empty] | 9 |  |  | Issue |  |  | High | Medium | Severe | [6 empty] | Issue |  |  | Medium | Medium | [5 empty] | OPEN | [11 empty] | Very High | Very High | Very High
[20 empty] | Site Survey | 2023-08-29 | [10 empty] | 10 |  |  | Risk |  |  | Low | High | [7 empty] | Action Item |  |  | Low | Very High | [5 empty] | OPEN | [11 empty] | High | High | High
|  | CRITICAL PATH ANALYSIS | [17 empty] | MUX Installation & Link Readiness | 2023-09-26 | [10 empty] | 11 |  |  | Action Item |  |  | Medium | Medium | [7 empty] | Action Item |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED | [11 empty] | Medium | Medium | Medium
|  | Activity | Predecessor | Description | Duration | CPA | [13 empty] | HW Installation | 2023-09-28 | [10 empty] | 12 |  |  | Issue |  |  | High | Very Low | [7 empty] | Issue |  |  | Medium | Low | [5 empty] | OPEN | [11 empty] | Low | Low | Low
|  | A | - | Order Processing | 3 | 3 | [13 empty] | Testing and Handover | 2023-09-29 | [10 empty] | 13 |  |  | Risk |  |  | High | High | Critical | [6 empty] | Issue |  |  | Medium | Low | [5 empty] | OPEN | [11 empty] | Very Low | Very Low | Very Low
|  | B | - | Access Clearance for Site Survey | 6 | 6 | [25 empty] | 14 |  |  | Action Item |  |  | Low | Medium | [7 empty] | Action Item |  |  | Medium | Medium | [5 empty] | OPEN | [11 empty] | NIL | NIL | NIL
|  | C | - | Site Survey | 10 | 10 | [25 empty] | 15 |  |  | Issue |  |  | Low | Medium | [7 empty] | Issue |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED
|  | D | A | MUX Installation & Link Readiness | 30 | 27
|  | E | B,C | HW Installation | 32 | 22
|  | F | C | Testing Completed and Handed Over | 33 | 23 | [13 empty] | Work Orders to be closed
|  | G | F |  | 10 | -23 | [13 empty] | Duration to complete critical tasks | 0 | Status |  | REFERENCE | Owner | [6 empty] | Inherent Impact Matrix |  | Date Last Updated: |  |  |  |  | Action Items | Issues | Risk |  |  | Risk Rating | Inherent |  | Residual
|  | H |  |  | 8 | 8 | [12 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA |  |  |  |  | TD/TM | [6 empty] | Impact: |  | #REF! | #REF! | Medium | High | Very High | 4 | 5 | 4 |  |  | Risk | 50% | 4 | 50%
|  | I | E |  | 12 | -20 | [13 empty] | Infrabuild/RFS date by Partner |  |  |  |  | SDO/PARTNER | [6 empty] | Probability | Very High |  |  |  | 1 | [6 empty] | Issues | 30% | 5 | 30%
|  | J | I |  | 14 | 2 | [13 empty] | External Dependencies |  |  |  |  | CLIENT | [7 empty] | High |  |  | 1 | 2 | 1 | [5 empty] | Action Items | 20% | 4 | 20%
|  | K |  | Work Orders to be closed | 4 | [14 empty] | Cease Date Confirmation |  |  |  |  | CLIENT/PARTNER | [7 empty] | Medium |  |  | 1 | [9 empty] | 4.3 |  | 0
[33 empty] | #REF! | [10 empty] | Nett Rating |  | 4.3
|  | Description | Duration | ES | EF | LS | LF | [12 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [6 empty] | #REF!
|  | IKOM | 3 | 0 | 3 | 3 | 6 | [12 empty] | Kick off Email to Client | 2023-08-16 |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 29 | 29 | [12 empty] | Instructions for Internal Orders to ASE | 2023-08-16 |  |  | PC | [7 empty] | Residual Impact Matrix |  | Date Last Updated: |  |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 10 | 0 | 10 | 19 | 29 | [12 empty] | Instructions for Matching Order to DPE | 2023-08-16 |  |  | PC | [7 empty] | Impact: |  | #REF! | #REF! | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open
|  | EKOM | 27 | 3 | 30 | 6 | 33 | [12 empty] | Instructions for CPE Order to ASE | 2023-08-16 |  |  | PC | [7 empty] | Probability | Very High |  |  | 1
|  | Site Survey Schedule | 22 | 10 | 32 | 29 | 51 | [12 empty] | Handover email to Customer |  |  |  | PE | [8 empty] | High |  |  | 1
|  | PO/SO to be issued | 23 | 10 | 33 | 33 | 56 | [25 empty] | Medium |  |  | 2
|  | CPE ETA confirmation at Destination | -23 | 33 | 10 | 56 | 33 | [25 empty] | #REF!
|  | Cease Date Confirmation | 8 | 0 | 8 | 25 | 33 | [25 empty] | #REF!
|  | Site Survey Completion | -20 | 32 | 12 | 51 | 31 | [12 empty] | WBS | Status |  | Owner | Remarks
|  | CE Routing | 2 | 12 | 14 | 31 | 33 | [12 empty] | Matching Orders Processing
|  | Work orders to be closed | [17 empty] | DPE instructions to Partner- - MPLS |  |  | DPE
[20 empty] | Confirmation from Partner - MPLS |  |  | Partner
[20 empty] | DPE instructions to Partner - CGI |  |  | DPE
[20 empty] | Confirmation from Partner - CGI |  |  | Partner
|  |  | 3 |  |  |  | 3 | [10 empty] | 33 |  | Pro-active WBS confirmation from Partner - CGI |  |  | Partner
|  | A | 0 | 3 |  | D | 3 | 30 | [9 empty] | FINISH |  | Internal Work Orders Processing
|  | 3 | 3 | 6 |  | 27 | 6 | 33 | [11 empty] | ASE Instrcutions to SDE |  |  | ASE
[20 empty] | SDE to Order Raising Team |  |  | SDE
|  |  | 29 | [16 empty] | ASE Instructions to CPE Order Raising Team |  |  | ASE
|  | B | 0 | 0 |  |  | 19 |  |  |  | 19 |  |  |  | 19 |  |  |  |  | SSOT raised |  |  | CS
|  | 0 | 29 | 29 |  | E | 10 | 32 |  | I | 32 | 12 |  | J | 12 | 14 |  |  |  | PO/SO issued to CPE Vendor |  |  | CPE Admin
[6 empty] | 22 | 29 | 51 |  | -20 | 51 | 31 |  | 2 | 31 | 33 |  |  |  | Loan CPE Order Processing
[20 empty] | ASE Instructions to CPE Order Raising Team |  |  | ASE
|  |  | 19 |  |  |  | 23 |  |  |  | 23 | [8 empty] | SSOT raised |  |  | CS
|  | C | 0 | 10 |  | F | 10 | 33 |  | G | 33 | 10 | [7 empty] | PO/SO issued to CPE Vendor |  |  | CPE Admin
|  | 10 | 19 | 29 |  | 23 | 33 | 56 |  | -23 | 56 | 33 | [7 empty] | Cease Date Confirmation
[20 empty] | Cease Date Confirmation from Client |  |  | Client
|  |  | 25 | [16 empty] | Cease date informed to DPE |  |  | PC
|  | H | 0 | 8 | [15 empty] | Cease date acknowledgment from Partner |  |  | Partner
|  | 8 | 25 | 33 | [15 empty] | Technical Alignment
[20 empty] | Network Diagram |  |  | CS
|  | Deadline Catalysts | [17 empty] | Tech.File provided |  |  | CS
|  | IKOM | TRUE | 84 | FALSE | 70 | [13 empty] | CR Form provided |  |  | CS
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [13 empty] | Partner Port/NEF provided |  |  | GSP
|  | Internal Work Orders | FALSE | 70 | FALSE | 70 | [13 empty] | Demarcation details, if applicable |  |  | SDO/Customer
|  | EKOM | FALSE | 70 | FALSE | 70 | [13 empty] | IP address retained or New Provide |  |  | Customer
|  | Site Survey Schedule | FALSE | 70 | FALSE | 70 | [13 empty] | VLAN information, if applicable |  |  | Customer
|  | PO/SO to be issued | FALSE | 70 | FALSE | 70 | [13 empty] | WAN/ LAN IP info from customer/Partner |  |  | Customer/Partner
|  | CPE ETA confirmation at Destination | FALSE | 70 | FALSE | 70 | [13 empty] | Provisioning
|  | Cease Date Confirmation | FALSE | 70 | FALSE | 70 | 0 | 0 | [11 empty] | Pre-provisioning - OLLC Activation/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | FALSE | 70 | FALSE | 70 | [13 empty] | Handover documents from Partner - MPLS |  |  | Partner
|  | CE Routing | FALSE | 70 | FALSE | 70 | [13 empty] | Handover documents from Partner - CGI |  |  | Partner
|  | Work orders to be closed | FALSE | 70 | [15 empty] | PE Port Status, for MPLS Services only. |  |  | GSP
[20 empty] | Schedule |  |  | PC
|  | External Depedencies Catalysts | [17 empty] | Technical IKOM, if applicable |  |  | PC
|  | INFRABUILD DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | 0 | 0 | [9 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | [11 empty] | Customer POC |  |  | Customer
|  | EXTERNAL DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | [11 empty] | TAC booking, if applicable |  |  | PC
[20 empty] | GSP Booking, if applicable |  |  | PC
[20 empty] | RVPN Template, if applicable |  |  | GSP
|  | PROBABILITY ANALYSIS | [17 empty] | CPE WAN IP for Z Scalar configuration |  |  | Customer
|  | Duration to complete critical tasks | 0 | [16 empty] | SGO/LSP SUPPORT |  |  | Partner
|  | Standard Deviation | 2.6771 | [16 empty] | Conference Bridge |  |  | PC
[20 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [12 empty] | UAT by Customer |  |  | Customer
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5 | [12 empty] | Handover email |  |  | PE
|  | Matching Orders | 3 | 6 | 10 | 6.1667 | 0 | [12 empty] | CRD amendment |  |  | PC
|  | Internal Work Orders | 3 | 10 | 10 | 8.8333 | 1.1667 | [12 empty] | Work order closures |  |  | PC
|  | EKOM | 4 | 30 | 8 | 22 | 0.66667 | [12 empty] | Percentage Completed | 0% | Pending Completion | 100%
|  | Site Survey Schedule | 5 | 32 | 10 | 23.8333 | 0.83333 | [12 empty] | Project Progress | 0%
|  | PO/SO to be issued | 5 | 33 | 10 | 24.5 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner | 25 | 45
|  | Sales | 30 | 75
|  | Client | 45 | 90
|  | TD/TM | 50 | 120
60
75
90
Communication Catalysts
|  | Kick off Email to Client | FALSE | 70
|  | Instrcutions for Internal Orders to ASE | FALSE | 70
|  | Instructions for Matching Order to ASE | FALSE | 70 | FALSE | 70
|  | Instructions for CPE Order to ASE | FALSE | 70 | FALSE | 70
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Matching Orders Processing |  | 24 |  |  | 2.0833
|  | DPE instructions to Partner- - MPLS | FALSE | 70 | FALSE | 70 | 0 | 0 | 0 | 0
|  | Confirmation from Partner - MPLS | FALSE | 70 | FALSE | 70 | 0 | 0
|  | DPE instructions to Partner - CGI | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Confirmation from Partner - CGI | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Pro-active WBS confirmation from Partner - CGI | FALSE | 70 | FALSE | 70 | 0 | 0
Internal Work Orders Processing
|  | ASE Instrcutions to SDE | FALSE | 70 |  |  | 0
|  | SDE to Order Raising Team | FALSE | 70 |  |  | 0 | 2.0833
|  | ASE Instructions to CPE Order Raising Team | FALSE | 70 | FALSE | 70 | 0 | 0
|  | SSOT raised | FALSE | 70 | FALSE | 70 | 0 | 0
|  | PO/SO issued to CPE Vendor | FALSE | 70 | FALSE | 70 | 0 | 0
Loan CPE Order Processing
|  | ASE Instructions to CPE Order Raising Team | FALSE | 70 | FALSE | 70 | 0 | 0
|  | SSOT raised | FALSE | 70 | FALSE | 70 | 0 | 0
|  | PO/SO issued to CPE Vendor | FALSE | 70 | FALSE | 70 | 0 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Cease date informed to DPE | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Cease date acknowledgment from Partner | FALSE | 70 | FALSE | 70 | 0 | 0
Technical Alignment
|  | Network Diagram | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Tech.File provided | FALSE | 70 | FALSE | 70 | 0 | 0
|  | CR Form provided | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Partner Port/NEF provided | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Demarcation details, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | IP address retained or New Provide | FALSE | 70 | FALSE | 70 | 0 | 0
|  | VLAN information, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | WAN/ LAN IP info from customer | FALSE | 70 | FALSE | 70 | 0 | 0
Provisioning
|  | Pre-provisioning - OLLC Activation/Cutover |  | 13 |  |  | 1.5385
|  | Handover documents from Partner - MPLS | FALSE | 70 | FALSE | 70 | 0 | 0 | 0 | 0
|  | Handover documents from Partner - CGI | FALSE | 70 | FALSE | 70 | 0 | 0
|  | PE Port Status, for MPLS Services only. | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Schedule | FALSE | 70 |  |  | 0 | 3.8462
|  | Technical IKOM, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | TD/TM booking, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Customer POC | FALSE | 70 |  |  | 0
|  | TAC booking, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | GSP Booking, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | RVPN Template, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | CPE WAN IP for Z Scalar configuration | FALSE | 70 | FALSE | 70 | 0 | 0
|  | SGO/LSP SUPPORT | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Conference Bridge | FALSE | 70 |  |  | 0
|  | Post Provisioning/OLLC Activation |  |  |  | 4 | 2.5 |  | 0
|  | UAT by Customer | FALSE | 70 |  |  | 0
|  | Handover email | FALSE | 70 |  |  | 0
|  | CRD amendment | FALSE | 70 |  |  | 0
|  | Work order closures | FALSE | 70 |  |  | 0
[6 empty] | Internal Dependencies | 0
[6 empty] | Risk Analysis | 0
[6 empty] | Provisioning Check List | 0
[6 empty] | Post Provisioning | 0
0
Formulas:
Order Processing = IF(E62<=83,IF(G62<=83,(IF(TODAY()<=WORKDAY([Order Processing, row above],-1),"INITIATED","WIP")),INDEX(AA12,MATCH(Z12,Z12:Z21,0))),"COMPLETED")
Access Clearance for Site Survey = IF(E63<=83,IF(G63<=83,(IF(TODAY()<=WORKDAY([Access Clearance for Site Survey, row above],-2),"INITIATED","WIP")),INDEX(AA13,MATCH(Z13,Z13:Z21,0))),"COMPLETED")
Site Survey = IF(E64<=83,IF(G64<=83,(IF(TODAY()<=WORKDAY([Site Survey, row above],-8),"TO BE SCHEDULED","WIP")),INDEX(AA14,MATCH(Z14,Z14:Z21,0))),"COMPLETED")
MUX Installation & Link Readiness = IF(E65<=83,IF(G65<=83,(IF(TODAY()<=WORKDAY([MUX Installation & Link Readiness, row above],-15),"TO BE SCHEDULED","WIP")),INDEX(AA15,MATCH(Z15,Z15:Z21,0))),"COMPLETED")
HW Installation = IF(E66<=83,IF(G66<=83,(IF(TODAY()<=WORKDAY([HW Installation, row above],-20),"TO BE SCHEDULED","WIP")),INDEX(AA16,MATCH(Z16,Z16:Z21,0))),"COMPLETED")
Testing Completed and Handed Over = IF(E67<=83,IF(G67<=83,(IF(TODAY()<=WORKDAY([Testing Completed and Handed Over, row above],-21),"TO BE SCHEDULED","WIP")),INDEX(AA17,MATCH(Z17,Z17:Z21,0))),"COMPLETED")
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
0%

## Dashboard Summary Tab (hidden)
Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing Completed and Handed Over | Target RFS | Remarks
| WIP | NA | NA | WIP | WIP | TO BE SCHEDULED

## Gantt Chart (hidden)
| Project Start Date: | 0 |  |  |  |  | #NUM! |  |  |  | #NUM! |  |  |  |  | #NUM! |  |  |  |  | #NUM!
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM!
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
2023-06-12
| Project Start Date: | 2023-06-23 |  |  |  |  | 2023-06-12 | W4: 2023-07-10; W9: 2023-08-07; W14: 2023-09-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
18 | Scoot - T3
18.1 | Clean Order Processing | 2023-06-23 | 2023-07-03 | bar: 2023-07-03
18.2 | SDWAN Device Installation and configuration | 2023-07-04 | #REF! | bar: 2023-07-03
18.3 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18.4 | Day2 Support & Handover | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Project Start Date: | 2023-06-07 |  |  |  |  | 2023-06-05: 2023-06-12; 2023-07-03: 2023-07-10; 2023-08-07: 2023-08-07; 2023-09-11: 2023-09-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
B | SIA Primary Data Centre (TSQ)
B1.1 | Clean Order Processing for Link Delivery | 2023-06-07 | 2023-06-14 | Singtel | bar: 2023-06-12
B1.2 | Site Survey for Rack Space & Power Readiness | 2023-06-15 | 2023-06-22 | Singtel | bar: 2023-06-12
B1.3 | SDWAN Device Installation and configuration | 2023-06-23 | 2023-06-26 | Singtel | bar: 2023-06-19
B1.4 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-06-27 | 2023-06-28 | SIA | bar: 2023-06-26
B1.5 | Day2 Support & Handover | 2023-06-27 | 2023-06-28 | SIA | bar: 2023-06-26
B1.6 | Termination of existing Services - Parallel Run Period | 2023-06-27 | 2023-06-28 | SIA | bar: 2023-06-26
| Project Start Date: | 2023-06-07 |  |  |  |  | 2023-06-05: 2023-06-12; 2023-07-03: 2023-07-10; 2023-08-07: 2023-08-07; 2023-09-11: 2023-09-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
A | SIA Secondary Data Centre (Kim Chuan DCE)
A1.1 | Clean Order Processing | 2023-05-30 | 2023-06-07 | Singtel | bar: 2023-06-05
A1.2 | Site Survey Rack Space & Power Readiness | 2023-06-08 | 2023-06-15 | Singtel | bar: 2023-06-05
A1.3 | SDWAN Device Installation and configuration | 2023-06-16 | 2023-06-19 | Singtel | bar: 2023-06-12
A1.4 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-06-20 | 2023-06-21 | SIA | bar: 2023-06-19
A1.5 | Day2 Support & Handover | 2023-06-22 | 2023-06-22 | SIA | bar: 2023-06-19
A1.6 | Termination of existing Services - Parallel Run Period | 2023-12-31 | 2023-06-23 | SIA | bar: 2023-06-19
| Project Start Date: | 2023-06-23 |  |  |  |  | 2023-06-05: 2023-06-12; 2023-07-03: 2023-07-10; 2023-08-07: 2023-08-07; 2023-09-11: 2023-09-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
18 | Scoot - T1
18.1 | Clean Order Processing | 2023-06-23 | 2023-07-03 | Singtel | bar: 2023-07-03
18.2 | SDWAN Device Installation and configuration | 2023-07-04 | 2023-07-05 | Singtel | bar: 2023-07-03
18.3 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-07-06 | 2023-07-07 | SIA | bar: 2023-07-03
18.4 | Day2 Support & Handover | 2023-07-10 | 2023-07-10 | Singtel | bar: 2023-07-03
| Project Start Date: | 2023-07-06 |  |  |  |  | 2023-06-05: 2023-07-10; 2023-07-03: 2023-08-07; 2023-08-07: 2023-09-04; 2023-09-11: 2023-10-09
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
11 | CHAI CHEE
11.1 | Clean Order Processing for Link Delivery | 2023-07-06 | 2023-07-11 | Singtel | bar: 2023-08-07
11.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-07-12 | 2023-07-21 | Singtel | bar: 2023-08-07
11.3 | Link Provisioning | 2023-07-24 | 2023-08-21 | Singtel | bar: 2023-08-14
11.4 | SDWAN Device Installation and configuration | 2023-08-22 | 2023-08-23 | Singtel | bar: 2023-09-18
11.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-08-24 | 2023-08-25 | SIA | bar: 2023-09-18
11.6 | Day2 Support & Handover | 2023-08-28 | 2023-08-28 | Singtel | bar: 2023-09-18
11.7 | Termination of existing Services - Parallel Run Period | 2023-09-27 | 2023-09-27 | Singtel | bar: 2023-09-25
| Project Start Date: | 2023-07-13 |  |  |  |  | 2023-07-03: 2023-07-10; 2023-07-31: 2023-08-07; 2023-09-04: 2023-09-04; 2023-10-09: 2023-10-09
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
1 | ION
1.1 | Clean Order Processing for Link Delivery | 2023-07-13 | 2023-07-18 | Singtel | bar: 2023-08-14
1.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-07-19 | 2023-07-28 | Singtel | bar: 2023-08-14
1.3 | Link Provisioning | 2023-07-31 | 2023-08-28 | Singtel | bar: 2023-08-21
1.4 | SDWAN Device Installation and configuration | 2023-08-29 | 2023-08-30 | Singtel | bar: 2023-09-25
1.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-08-31 | 2023-09-01 | SIA | bar: 2023-09-25
1.6 | Day2 Support & Handover | 2023-09-04 | 2023-09-04 | Singtel | bar: 2023-09-25
1.7 | Termination of existing Services - Parallel Run Period | 2023-10-04 | 2023-10-04 | Singtel | bar: 2023-10-02
| Project Start Date: | 2023-07-20 |  |  |  |  | 2023-07-03: 2023-07-10; 2023-07-31: 2023-08-07; 2023-09-04: 2023-09-04; 2023-10-09: 2023-10-09
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
12 | ALH GUARD
12.1 | Clean Order Processing for Link Delivery | 2023-07-20 | 2023-07-25 | Singtel | bar: 2023-08-21
12.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-07-26 | 2023-08-04 | Singtel | bar: 2023-08-28
12.3 | Link Provisioning | 2023-08-07 | 2023-09-04 | Singtel | bar: 2023-08-28
12.4 | SDWAN Device Installation and configuration | 2023-09-05 | 2023-09-06 | Singtel | bar: 2023-10-02
12.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-09-07 | 2023-09-08 | SIA | bar: 2023-10-02
12.6 | Day2 Support & Handover | 2023-09-11 | 2023-09-11 | Singtel | bar: 2023-10-02
12.7 | Termination of existing Services - Parallel Run Period | 2023-10-11 | 2023-10-11 | Singtel | bar: 2023-10-09
| Project Start Date: | 2023-07-27 |  |  |  |  | 2023-07-03: 2023-07-10; 2023-07-31: 2023-08-07; 2023-09-04: 2023-09-04; 2023-10-09: 2023-10-09
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
13 | DATAPOST (Standalone) - Biz Partners
13.1 | Clean Order Processing for Link Delivery | 2023-07-27 | 2023-08-01 | Singtel | bar: 2023-08-28
13.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-08-02 | 2023-08-11 | Singtel | bar: 2023-09-04
13.3 | Link Provisioning | 2023-08-14 | 2023-09-11 | Singtel | bar: 2023-09-04
13.4 | Diverse Link Readiness | 2023-09-11 | 2023-09-11 | SIA | bar: 2023-10-09
13.5 | SDWAN Device Installation and configuration | 2023-09-12 | 2023-09-13 | Singtel | bar: 2023-10-09
13.6 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-09-14 | 2023-09-15 | SIA | bar: 2023-10-09
13.7 | Day2 Support & Handover | 2023-09-18 | 2023-09-18 | Singtel | bar: 2023-10-09
13.8 | Termination of existing Services - Parallel Run Period | 2023-10-18 | 2023-10-18 | Singtel | bar: 2023-10-16
| Project Start Date: | 2023-08-03 |  |  |  |  | 2023-07-03: 2023-07-17; 2023-07-31: 2023-08-14; 2023-09-04: 2023-09-11; 2023-10-09: 2023-10-16
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
14 | MENTORMEDIA (Standalone) - Biz Partners
14.1 | Clean Order Processing for Link Delivery | 2023-08-03 | 2023-08-08 | Singtel | bar: 2023-09-11
14.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-08-09 | 2023-08-18 | Singtel | bar: 2023-09-18
14.3 | Link Provisioning | 2023-08-21 | 2023-09-18 | Singtel | bar: 2023-09-18
14.4 | Diverse Link Readiness | 2023-09-18 | 2023-09-18 | SIA | bar: 2023-10-23
14.5 | SDWAN Device Installation and configuration | 2023-09-19 | 2023-09-20 | Singtel | bar: 2023-10-23
14.6 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-09-21 | 2023-09-22 | SIA | bar: 2023-10-23
14.7 | Day2 Support & Handover | 2023-09-25 | 2023-09-25 | Singtel | bar: 2023-10-23
14.8 | Termination of existing Services - Parallel Run Period | 2023-10-25 | 2023-10-25 | Singtel | bar: 2023-10-30
| Project Start Date: | 2023-08-11 |  |  |  |  | 2023-07-10: 2023-08-14; 2023-08-07: 2023-09-11; 2023-09-11: 2023-10-09; 2023-10-16: 2023-11-13
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
6 | SMC - SIAEC
6.1 | Clean Order Processing for Link Delivery | 2023-08-11 | 2023-08-16 | Singtel | bar: 2023-10-16
6.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-08-17 | 2023-08-28 | Singtel | bar: 2023-10-30
6.3 | Link Provisioning | 2023-08-29 | 2023-09-26 | Singtel | bar: 2023-10-30
6.4 | SDWAN Device Installation and configuration | 2023-09-27 | 2023-09-28 | Singtel | bar: 2023-11-27
6.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-09-29 | 2023-10-02 | SIA | bar: 2023-11-27
6.6 | Day2 Support & Handover | 2023-10-03 | 2023-10-03 | Singtel
6.7 | Termination of existing Services - Parallel Run Period | 2023-11-02 | 2023-11-02 | Singtel
| Project Start Date: | 2023-08-18 |  |  |  |  | 2023-08-07: 2023-08-14; 2023-09-04: 2023-09-11; 2023-10-09: 2023-10-09; 2023-11-13: 2023-11-13
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
5 | PTB4 - SIAEC
5.1 | Clean Order Processing for Link Delivery | 2023-08-18 | 2023-08-23 | Singtel | bar: 2023-10-23
5.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-08-24 | 2023-09-04 | Singtel | bar: 2023-11-06
5.3 | Link Provisioning | 2023-09-05 | 2023-10-03 | Singtel | bar: 2023-11-06
5.4 | SDWAN Device Installation and configuration | 2023-10-04 | 2023-10-05 | Singtel
5.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-10-06 | 2023-10-09 | SIA
5.6 | Day2 Support & Handover | 2023-10-10 | 2023-10-10 | Singtel
5.7 | Termination of existing Services - Parallel Run Period | 2023-11-09 | 2023-11-09 | Singtel
| Project Start Date: | 2023-08-25 |  |  |  |  | 2023-08-07: 2023-08-14; 2023-09-04: 2023-09-11; 2023-10-09: 2023-10-09; 2023-11-13: 2023-11-13
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
15 | KRISSHOP @ CHANGI
15.1 | Clean Order Processing for Link Delivery | 2023-08-25 | 2023-08-30 | Singtel | bar: 2023-10-30
15.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-08-31 | 2023-09-11 | Singtel | bar: 2023-11-13
15.3 | Link Provisioning | 2023-09-12 | 2023-10-10 | Singtel | bar: 2023-11-13
15.4 | SDWAN Device Installation and configuration | 2023-10-11 | 2023-10-12 | Singtel
15.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-10-13 | 2023-10-16 | SIA
15.6 | Day2 Support & Handover | 2023-10-17 | 2023-10-17 | Singtel
15.7 | Termination of existing Services - Parallel Run Period | 2023-11-16 | 2023-11-16 | Singtel
| Project Start Date: | 2023-09-01 |  |  |  |  | 2023-08-07: 2023-08-14; 2023-09-04: 2023-09-11; 2023-10-09: 2023-10-09; 2023-11-13: 2023-11-13
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
4 | SICC1
4.1 | Clean Order Processing for Link Delivery | 2023-09-01 | 2023-09-06 | Singtel | bar: 2023-11-06
4.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-09-07 | 2023-09-18 | Singtel | bar: 2023-11-06
4.3 | Link Provisioning | 2023-09-19 | 2023-10-17 | Singtel | bar: 2023-11-20
4.4 | SDWAN Device Installation and configuration | 2023-10-18 | 2023-10-19 | Singtel
4.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-10-20 | 2023-10-23 | SIA
4.6 | Day2 Support & Handover | 2023-10-24 | 2023-10-24 | Singtel
4.7 | Termination of existing Services - Parallel Run Period | 2023-11-23 | 2023-11-23 | Singtel
| Project Start Date: | 2023-09-08 |  |  |  |  | 2023-08-07: 2023-09-11; 2023-09-04: 2023-10-09; 2023-10-09: 2023-11-06; 2023-11-13: 2023-12-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
9 | EC ENGINE - SIAEC
9.1 | Clean Order Processing for Link Delivery | 2023-09-08 | 2023-09-13 | Singtel | bar: 2023-12-11
9.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-09-14 | 2023-09-25 | Singtel | bar: 2023-12-25
9.3 | Link Provisioning | 2023-09-26 | 2023-10-24 | Singtel | bar: 2023-12-25
9.4 | SDWAN Device Installation and configuration | 2023-10-25 | 2023-10-26 | Singtel
9.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-10-27 | 2023-10-30 | SIA
9.6 | Day2 Support & Handover | 2023-10-31 | 2023-10-31 | Singtel
9.7 | Termination of existing Services - Parallel Run Period | 2023-11-30 | 2023-11-30 | Singtel
| Project Start Date: | 2023-09-15 |  |  |  |  | 2023-09-04: 2023-09-11; 2023-10-02: 2023-10-09; 2023-11-06: 2023-11-06; 2023-12-11: 2023-12-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
16 | KRISSHOP @ SIGNATURE
16.1 | Clean Order Processing for Link Delivery | 2023-09-15 | 2023-09-20 | Singtel | bar: 2023-12-18
16.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-09-21 | 2023-10-02 | Singtel
16.3 | Link Provisioning | 2023-10-03 | 2023-10-31 | Singtel
16.4 | SDWAN Device Installation and configuration | 2023-11-01 | 2023-11-02 | Singtel
16.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-11-03 | 2023-11-06 | SIA
16.6 | Day2 Support & Handover | 2023-11-07 | 2023-11-07 | Singtel
16.7 | Termination of existing Services - Parallel Run Period | 2023-12-07 | 2023-12-07 | Singtel
| Project Start Date: | 2023-09-07 |  |  |  |  | 2023-09-04: 2023-09-11; 2023-10-02: 2023-10-09; 2023-11-06: 2023-11-06; 2023-12-11: 2023-12-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
4 | SICC1
4.1 | Clean Order Processing for Link Delivery | 2023-09-01 | 2023-09-06 | Singtel | bar: 2023-12-04
4.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-09-07 | 2023-09-18 | Singtel | bar: 2023-12-18
4.3 | Link Provisioning | 2023-09-19 | 2023-10-17 | Singtel | bar: 2023-12-18
4.4 | SDWAN Device Installation and configuration | 2023-10-18 | 2023-10-19 | Singtel
4.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-10-20 | 2023-10-23 | SIA
4.6 | Day2 Support & Handover | 2023-10-24 | 2023-10-24 | Singtel
4.7 | Termination of existing Services - Parallel Run Period | 2023-11-23 | 2023-11-23 | Singtel
| Project Start Date: | 2023-09-08 |  |  |  |  | 2023-09-04: 2023-09-11; 2023-10-02: 2023-10-09; 2023-11-06: 2023-11-06; 2023-12-11: 2023-12-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
9 | EC ENGINE - SIAEC
9.1 | Clean Order Processing for Link Delivery | 2023-09-08 | 2023-09-13 | Singtel | bar: 2023-12-11
9.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-09-14 | 2023-09-25 | Singtel | bar: 2023-12-25
9.3 | Link Provisioning | 2023-09-26 | 2023-10-24 | Singtel | bar: 2023-12-25
9.4 | SDWAN Device Installation and configuration | 2023-10-25 | 2023-10-26 | Singtel
9.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-10-27 | 2023-10-30 | SIA
9.6 | Day2 Support & Handover | 2023-10-31 | 2023-10-31 | Singtel
9.7 | Termination of existing Services - Parallel Run Period | 2023-11-30 | 2023-11-30 | Singtel
| Project Start Date: | 2023-09-21 |  |  |  |  | 2023-09-04: 2023-09-11; 2023-10-02: 2023-10-09; 2023-11-06: 2023-11-06; 2023-12-11: 2023-12-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
16 | KRISSHOP @ SIGNATURE
16.1 | Clean Order Processing for Link Delivery | 2023-09-15 | 2023-09-20 | Singtel | bar: 2023-12-18
16.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-09-21 | 2023-10-02 | Singtel
16.3 | Link Provisioning | 2023-10-03 | 2023-10-31 | Singtel
16.4 | SDWAN Device Installation and configuration | 2023-11-01 | 2023-11-02 | Singtel
16.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-11-03 | 2023-11-06 | SIA
16.6 | Day2 Support & Handover | 2023-11-07 | 2023-11-07 | Singtel
16.7 | Termination of existing Services - Parallel Run Period | 2023-12-07 | 2023-12-07 | Singtel
| Project Start Date: | 2023-09-22 |  |  |  |  | 2023-09-04: 2023-09-11; 2023-10-02: 2023-10-09; 2023-11-06: 2023-11-06; 2023-12-11: 2023-12-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
3 | LOYANG - SIAEC
3.1 | Clean Order Processing for Link Delivery | 2023-09-22 | 2023-09-27 | Singtel | bar: 2023-12-25
3.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-09-28 | 2023-10-09 | Singtel
3.3 | Link Provisioning | 2023-10-10 | 2023-11-07 | Singtel
3.4 | SDWAN Device Installation and configuration | 2023-11-08 | 2023-11-09 | Singtel
3.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-11-10 | 2023-11-13 | SIA
3.6 | Day2 Support & Handover | 2023-11-14 | 2023-11-14 | Singtel
3.7 | Termination of existing Services - Parallel Run Period | 2023-12-14 | 2023-12-14 | Singtel
| Project Start Date: | 2023-09-29 |  |  |  |  | 2023-09-04: 2023-09-11; 2023-10-02: 2023-10-09; 2023-11-06: 2023-11-06; 2023-12-11: 2023-12-11
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
8 | ALPS - SIAEC
8.1 | Clean Order Processing for Link Delivery | 2023-09-29 | 2023-10-04 | Singtel
8.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-10-05 | 2023-10-16 | Singtel
8.3 | Link Provisioning | 2023-10-17 | 2023-11-14 | Singtel
8.4 | SDWAN Device Installation and configuration | 2023-11-15 | 2023-11-16 | Singtel
8.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-11-17 | 2023-11-20 | SIA
8.6 | Day2 Support & Handover | 2023-11-21 | 2023-11-21 | Singtel
8.7 | Termination of existing Services - Parallel Run Period | 2023-12-21 | 2023-12-21 | Singtel
| Project Start Date: | 2023-10-06 |  |  |  |  | 2023-09-04: 2023-10-09; 2023-10-02: 2023-11-06; 2023-11-06: 2023-12-04; 2023-12-11: 2024-01-08
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
2 | ESD CHANGI - SIAEC
2.1 | Clean Order Processing for Link Delivery | 2023-10-06 | 2023-10-11 | Singtel
2.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-10-12 | 2023-10-23 | Singtel
2.3 | Link Provisioning | 2023-10-24 | 2023-11-21 | Singtel
2.4 | SDWAN Device Installation and configuration | 2023-11-22 | 2023-11-23 | Singtel
2.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-11-24 | 2023-11-27 | SIA
2.6 | Day2 Support & Handover | 2023-11-28 | 2023-11-28 | Singtel
2.7 | Termination of existing Services - Parallel Run Period | 2023-12-28 | 2023-12-28 | Singtel
| Project Start Date: | 2023-10-13 |  |  |  |  | 2023-10-02: 2023-10-09; 2023-10-30: 2023-11-06; 2023-12-04: 2023-12-04; 2024-01-08: 2024-01-08
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
10 | KRISLITE @ SIAEC
10.1 | Clean Order Processing for Link Delivery | 2023-10-13 | 2023-10-18 | Singtel
10.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-10-19 | 2023-10-30 | Singtel
10.3 | Link Provisioning | 2023-10-31 | 2023-11-28 | Singtel
10.4 | SDWAN Device Installation and configuration | 2023-11-29 | 2023-11-30 | Singtel
10.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-12-01 | 2023-12-04 | SIA
10.6 | Day2 Support & Handover | 2023-12-05 | 2023-12-05 | Singtel
10.7 | Termination of existing Services - Parallel Run Period | 2024-01-04 | 2024-01-04 | Singtel
| Project Start Date: | 2023-10-20 |  |  |  |  | 2023-10-02: 2023-10-09; 2023-10-30: 2023-11-06; 2023-12-04: 2023-12-04; 2024-01-08: 2024-01-08
| Project #: | SIA - SDWAN TECH REFRESH | Date Updated: |  |  | Week Starting: | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22
# | Activity | Start Date | End Date | Owner | Status | % Done |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
17 | KRISSHOP @ SICC2
17.1 | Clean Order Processing for Link Delivery | 2023-10-20 | 2023-10-25 | Singtel
17.2 | Site Survey for Link Delivery, Rack Space & Power Readiness | 2023-10-26 | 2023-11-06 | Singtel
17.3 | Link Provisioning | 2023-11-07 | 2023-12-05 | Singtel
17.4 | SDWAN Device Installation and configuration | 2023-12-06 | 2023-12-07 | Singtel
17.5 | LAN Cabling / Patching / Inter- Rack, Inhouse Cabling | 2023-12-08 | 2023-12-11 | SIA
17.6 | Day2 Support & Handover | 2023-12-12 | 2023-12-12 | Singtel
17.7 | Termination of existing Services - Parallel Run Period | 2024-01-11 | 2024-01-11 | Singtel
To be initiated
Work in Progress
Completed
Formulas:
Start Date = WORKDAY([End Date, row above],1)
End Date = WORKDAY([Start Date],#REF!,I15:I21)
End Date = WORKDAY([Start Date],#REF!)

## Monthly Report (hidden)
S/N. | Site Reference | Target Date for completion | Actual Completion Date | % of Work Completed | Stage | Call-Out | Status (Current Report) | Status (Previous Report)
1 | SCOOT - T3 | 2023-07-12 | 2023-07-12 | 100% | Completed | To raise Cease orders for HW and Existing links. | G | G
2 | TSQ | 2023-10-06 |  | 81.3% | Work In Progress | To raise Cease orders for HW and Existing links. | G | G
3 | DCE DC | 2023-10-09 |  | 79.13% | Work In Progress | To raise Cease orders for HW and Existing links. | G | G
4 | CHAI CHEE | 2023-10-10 |  | 71.63% | Work In Progress | To raise Cease orders for HW and Existing links. | G | G
5 | ION | 2023-10-11 |  | 40.43% | Work In Progress | To raise Cease orders for HW and Existing links. | G | G
6 | ALH GUARD | 2023-10-12 |  | 28.91% | Work In Progress | To raise Cease orders for HW and Existing links. | G | G
7 | SMC- SIAEC | 2023-10-19 |  | 15.87% | Work In Progress | To raise Cease orders for HW and Existing links. | G | G
8 | DATAPOST | 2023-10-26 |  | 18.04% | To be Initiated | To raise Provide order for Ethernet Link, Cease orders for HW and Existing Links. | A | A
9 | Mentor Media | 2023-11-02 |  | 11.52% | To be Initiated | To raise Provide order for Ethernet Link, Cease orders for HW and Existing Links. | A | A
10 | Scoot T1 | 2023-11-09 |  | 55.98% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G
11 | PTB4 - SIAEC | 2023-11-16 |  | 15.87% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G
12 | Krisshop @ Changi | 2023-11-23 |  | 13.7% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G
13 | SICC1 | 2023-11-30 |  | 13.7% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G
14 | EC Engine | 2023-12-07 |  | 13.7% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G
15 | KRISSHOP @ SIGNATURE | 2023-12-14 |  | 15.87% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G
16 | LOYANG - SIAEC | 2023-12-21 |  | 15.87% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G
17 | ALPS - SIAEC | 2023-12-21 |  | 13.7% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G
18 | ESD CHANGI - SIAEC | 2024-01-04 |  | 13.7% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G
19 | KRISLITE @ SIAEC | 2024-01-11 |  | 13.7% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G
20 | KRISSHOP @ SICC2 | 2024-01-18 |  | 13.7% | To be Initiated | To raise Cease orders for HW and Existing links. | G | G

## Agile Tracker
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [66 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
Summary Tab catalyst
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed
[31 empty] | TIMELINES | [8 empty] | AIR REGISTER
[13 empty] | NEEDS ATTENTION |  |  |  |  | 0% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Impact |  |  |  | Date Last Updated: | 2024-02-09 |  |  |  | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X |  |  |  | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | [14 empty] | 1 | [13 empty] | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 | [14 empty] | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 | [14 empty] | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 | [14 empty] | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  |  | 0
[40 empty] | 5 | [14 empty] | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [14 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7 | [24 empty] | NIL | NIL | NIL
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | [18 empty] | 8 | [28 empty] | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | [18 empty] | 9 | [27 empty] | WBS | Order Processing
[21 empty] | Internal Work Orders | [18 empty] | 10 | [28 empty] | Access Clearance for Site Survey
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | [18 empty] | 11 | [28 empty] | Site Survey
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | [18 empty] | 12 | [28 empty] | MUX Installation & Link Readiness
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | [18 empty] | 13 | [28 empty] | HW Installation
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | [18 empty] | 14 | [28 empty] | Testing and Handover
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | [18 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [46 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2024-02-09 |  |  |  | Action Items |  | Issues |  | Risks | [16 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA |  |  |  |  | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [15 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  |  | SDO/PARTNER | [13 empty] | Probability | Very High | [6 empty] | 0 |  | 0 |  | 0 | [15 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  |  | CLIENT | [14 empty] | High | [26 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  |  | CLIENT/PARTNER | [14 empty] | Medium | [26 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [26 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [26 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client |  |  |  | PE
|  | Matching Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Internal Orders to ASE/SDE |  |  |  | PC
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE |  |  |  | PC | [42 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to MPE |  |  |  | PC | [42 empty] | Order Processing | FALSE | 70 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [42 empty] | Access Clearance for Site Survey | FALSE | 70 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [60 empty] | Site Survey | FALSE | 70 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [60 empty] | MUX Installation & Link Readiness | FALSE | 70 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [60 empty] | HW Installation | FALSE | 70 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [42 empty] | Testing and Handover | FALSE | 70 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO
[21 empty] | Link Orders Processed |  |  | SDE/SDO
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO
HW Readiness
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 0 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 5 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 5 | 0 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | FALSE | 70 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | FALSE | 70 | [14 empty] | Technical Alignment
|  | Internal Work Orders | FALSE | 70 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | FALSE | 70 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | FALSE | 70 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | FALSE | 70 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | FALSE | 70 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | FALSE | 70 | FALSE | 70 | 0 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | FALSE | 70 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | FALSE | 70 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | 0 | 0 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.8868 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 0% | Pending Completion | 100%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 0%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 8.3333
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | FALSE | 70
|  | Instrcutions for Internal Orders to ASE | FALSE | 70
|  | Instructions for Matching Order to ASE | FALSE | 70 | FALSE | 70
|  | Instructions for CPE Order to ASE | FALSE | 70 | FALSE | 70
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Link Orders Processed | FALSE | 70 |  |  | 0 | 0
|  | Diversity Confirmation in orders | FALSE | 70 | FALSE | 70 | 0 | 0
HW Readiness
|  | HW released by Ingram | FALSE | 70 |  |  | 0 | 0
|  | HW availability at Xsys | FALSE | 70 |  |  | 0 | 0
|  | BOM Confirmation | FALSE | 70 |  |  | 0 | 0
|  | HW Ready for Deployment | FALSE | 70 |  |  | 0 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | FALSE | 70 |  |  | 0 | 0
HW Readiness
|  | Survey Schedule Confirmed | FALSE | 70 |  |  | 0 | 0
|  | Access Required | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Access Documents submitted | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Access Approved | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Site Survey Completed | FALSE | 70 |  |  | 0 | 0
CE Routing
|  | SLD Released | FALSE | 70 |  |  | 0 | 0
|  | Patching Required | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Patching Completed, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Routing Released | FALSE | 70 |  |  | 0 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | FALSE | 70 | FALSE | 70 | 0 | 0
|  | CRD amended to Cease Date | FALSE | 70 | FALSE | 70 | 0 | 0
Technical Alignment
|  | Network Diagram | FALSE | 70 |  |  | 0 | 0
|  | IP address retained or New Provide | FALSE | 70 | FALSE | 70 | 0 | 0
|  | VLAN information, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | WAN/ LAN IP info from customer/Partner | FALSE | 70 | FALSE | 70 | 0 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | FALSE | 70 | FALSE | 70 | 0 | 0 | 0 | 0
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | TD/TM & FE details, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Site POC | FALSE | 70 |  |  | 0 | 0
|  | TAC booking, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | GSP Booking, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 0
|  | Completion Status |  |  |  | Risk Analysis | 0
|  | WIP |  |  |  | Provisioning Check List | 0
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
0%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## PUBLIC IP'S
Site Name | WO# | WO TYPE | Svc# | A - End Address | PE WAN IP | CE WAN IP | Speed
ION | ZFJ0973002 | Provide | CE00296864SNG | 2 ION ORCHARD #04-05C ORCHARD TURN 238801 | 165.21.246.5/30 | 165.21.246.6/30 | 100M
ION | ZFJ0973001 | Provide | CE00296862SNG | 2 ION ORCHARD #04-05C ORCHARD TURN 238801 | 165.21.246.9/30 | 165.21.246.10/30 | 100M
Chai Chee | ZFJ2460003 | Provide | CE00296949SNG | 750B,WESTERN DIGITAL #04-05. CHAI CHEE ROAD. 469002 | 165.21.239.137/30 | 165.21.239.138/30 | 10M
Chai Chee | ZFJ2460004 | Provide | CE00296953SNG | 750B,WESTERN DIGITAL #04-05. CHAI CHEE ROAD. 469002 | 165.21.239.129/30 | 165.21.239.130/30 | 10M
ALH Guard | ZFJ2460005 | Provide | CE00296962SNG | 4 AIRLINE HOUSE GUARDHOUSE AIRLINE ROAD 819825 | 165.21.246.77/30 | 165.21.246.78/30 | 10M
ALH Guard | ZFJ2460006 | Provide | CE00296963SNG | 4 AIRLINE HOUSE GUARDHOUSE AIRLINE ROAD 819825 | 165.21.246.17/30 | 165.21.246.18/30 | 10M
Data Post |  | Provide |  | Work Orders to be raised
Mentor Media |  | Provide |  | Work Orders to be raised
SMC - SIAEC | ZFJ0973009 | Provide | CE00296947SNG | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499614 | 165.21.122.89/30 | 165.21.122.90/30 | 50M
SMC - SIAEC | ZFJ0973010 | Provide | CE00296951SNG | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499614 | 165.21.122.29/30 | 165.21.122.30/30 | 50M
PTB4 - SIAEC | ZFJ7294019 | Provide | CE00296981SNG | 10 AIRPORT BOULEVARD #01-44. CHANGI AIRPORT TERMINAL 4 819665 | 165.21.249.173/30 | 165.21.249.174/30 | 10M
PTB4 - SIAEC | ZFJ7294020 | Provide | CE00297030SNG | 10 AIRPORT BOULEVARD #01-44. CHANGI AIRPORT TERMINAL 4 819665 | 165.21.249.173/30 | 165.21.249.174/30 | 10M
KRISSHOP @ CHANGI | ZFJ7294015 | Provide | CE00296976SNG | #03-02 CHANGI SOUTH LANE 486045 | 165.21.123.37/30 | 165.21.123.38/30 | 10M
KRISSHOP @ CHANGI | ZFJ7294016 | Provide | CE00296977SNG | #03-02 CHANGI SOUTH LANE 486045 | 42.61.64.241/30 | 42.61.64.242/30 | 10M
SICC1 | ZFJ0973007 | Provide | CE00296939SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 | 165.21.122.97/30 | 165.21.122.98/30 | 50M
SICC1 | ZFJ0973008 | Provide | CE00296940SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 | 165.21.122.101/30 | 165.21.122.102/30 | 50M
EC Engine | ZFJ7294013 | Provide | CE00296968SNG | 300, LOYANG AVENUE 509071 | 165.21.122.105/30 | 165.21.122.106/30 | 10M
EC Engine | ZFJ7294014 | Provide | CE00296973SNG | 300, LOYANG AVENUE 509071 | 165.21.122.117/30 | 165.21.122.118/30 | 10M
KRISSHOP @ SIGNATURE | ZFJ2460007 | Provide | CE00297027SNG | THE SIGNATURE #08-06/07 CHANGI BUSINESS PARK CENTRAL 2 486066 | 165.21.104.157/30 | 165.21.104.158/30 | 100M
KRISSHOP @ SIGNATURE | ZFJ2460008 | Provide | CE00297028SNG | THE SIGNATURE #08-06/07 CHANGI BUSINESS PARK CENTRAL 2 486066 | 165.21.122.77/30 | 165.21.122.78/30 | 100M
LOYANG - SIAEC | ZFJ0973005 | Provide | CE00296927SNG | 60,SIA SUPPLIES CENTRE, LOYANG WAY, 508751 | 165.21.123.29/30 | 165.21.123.30/30 | 100M
LOYANG - SIAEC | ZFJ0973006 | Provide | CE00296928SNG | 60,SIA SUPPLIES CENTRE, LOYANG WAY, 508751 | 165.21.122.121/30 | 165.21.122.122/30 | 100M
ALPS - SIAEC | ZFJ7294011 | Provide | CE00296946SNG | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508988 | 165.21.122.129/30 | 165.21.122.130/30 | 50M
ALPS - SIAEC | ZFJ7294012 | Provide | CE00296964SNG | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508988 | 165.21.122.137/30 | 165.21.122.138/30 | 50M
ESD CHANGI - SIAEC | ZFJ0973003 | Provide | CE00296909SNG | 36,SATS MAINTENANCE CENTRE, CHANGI NORTH CRESCENT, 499620 | 42.61.64.93/30 | 42.61.64.94/30 | 100M
ESD CHANGI - SIAEC | ZFJ0973004 | Provide | CE00296914SNG | 36,SATS MAINTENANCE CENTRE, CHANGI NORTH CRESCENT, 499620 | 42.61.64.117/30 | 42.61.64.118/30 | 100M
KRISLITE @ SIAEC | ZFJ2460001 | Provide | CE00296901SNG | 9, #03-00 LOYANG WAY 508722 | 165.21.123.41/30 | 165.21.123.42/30 | 10M
KRISLITE @ SIAEC | ZFJ2460002 | Provide | CE00296902SNG | 9, #03-00 LOYANG WAY 508722 | 165.21.123.45/30 | 165.21.123.46/30 | 10M
KRISSHOP @ SICC2 | ZFJ7294017 | Provide | CE00296978SNG | 30,SATS INFLIGHT CATERING, CHANGI NORTH CRESCENT, 499612 | 165.21.122.141/30 | 165.21.122.142/30 | 50M
KRISSHOP @ SICC2 | ZFJ7294018 | Provide | CE00301230SNG | 30,SATS INFLIGHT CATERING, CHANGI NORTH CRESCENT, 499612 | 118.201.94.61/30 | 118.201.94.62/30 | 50M

## Pre-Provisioning Check List
PRE-PROVISIONING CHECK LIST
Site ID | ACTIVITY | DATE | Schedule | Rack and Power availability confirmation | Site POC | IM Plan & FW rules | Meeting Invite | BOM details | config files | Site Access | FE DETAILS | FE visiting Site | CAB Approval Details | Remarks
TSQ DC |  | 2023-10-10 | 6PM-10PM | Available |  | NA | SENT | Provided | Provided | Cleared | Provided | Kasiraja | CHG00000055512
ION ORHCARD |  | 2023-10-12 | 6PM-10PM | Available |  | Shared with Client | SENT | Provided | Provided | Cleared | Provided | Kairaja | CHG00000055520
Chai Chee |  | 2023-10-18 | 6PM-10PM | Available |  | NA | SENT | NA | Provided | NA | NA | NA
SMC-SIAEC | HW INSTALLATION & CUTOVER (CANCELLED) | 2023-11-30 | 4PM-8PM | Available | Zhi Hao/Hafiz | Shared with Client | SENT | Provided | Provided | Cleared | Provided | Saravanan | CHG00000058862 CHG00000058878 | Cancelled due to security approvals which SIA need to sort out. Cancelled on 30-Nov
| HW INSTALLATION | 2023-12-07 | 4PM-8PM | Available | Zhi Hao/Hafiz | Shared with Client | SENT | Provided | Provided | Cleared | Provided |  | CHG00000058862 CHG00000058878
| CUTOVER | [8 empty] | Cleared | Provided
EC Engine | HW INSTALLATION | 2023-12-14 | 3PM-10PM | Available | Kayliang Koh | Shared with Client | SENT | Provided | Provided | Cleared | Provided | Saravanan | CHG00000060020
CUTOVER
Krisshop @ Signature | HW INSTALLATION & CUTOVER (CANCELLED) | 2023-12-26 | 3PM - 10PM | Available | Siti | Shared with Client | SENT | Provided | Provided | Cleared | Provided | Raja | CHG00000060369 | Cancelled due to DC routing issue. BGP config between DC required. SIA to settle internally. Cancelled on 21-Dec
| HW INSTALLATION | 2024-01-04 | 3PM - 6PM
| CUTOVER | 2024-01-10 | 6PM - 10PM |  | ARIS/SATS | Shared with Client | SENT | NA | NA | NA | NA | NA | CHG00000060367
ALH GUARD | HW INSTALLATION | 2023-11-22 | 6PM-10PM | Available | ARIS/SATS | Shared with Client | SENT | BALA/XSYS | Provided | Cleared | Provided | Kasiraja | CHG00000058270
| CUTOVER (CANCELLED) | 2024-01-12 | 6PM-10PM |  | ARIS/SATS |  | SENT | NA | NA | NA | NA | NA | CHG00000061532 | Cancelled due to one change request missed by SIA team. Awaiting new date from SIA. Cancelled on 12-Jan (7PM)
| CUTOVER | 2024-01-31 | 6PM-10PM |  | ARIS | Shared with Client | SENT | NA | NA | NA | NA | NA | CHG00000061532
ESD CHANGI | HW INSTALLATION & CUTOVER (CUTOVER CANCELLED) | 2024-01-18 | 4PM-10PM | Hot Cutover | Weekhiang Tay | Shared with Client | SENT | Provided | Provided | Cleared | Provided | Kasiraja | CHG00000061652 | CHG00000062050 - SIN SDWAN FW Rules ESD communication with DC (pending approval from INFOSEC) Cutover cancelled on 18-Jan
| CUTOVER | 2024-01-30 | 6PM onwards | Hot Cutover | Weekhiang Tay | Shared with Client | SENT | Provided | Provided | n/a | n/a | n/a | CHG00000061652 | Rollbacked due to LAN connectivity issue, SIA could not reach one of the server and could not figured out where the packet dropped. New schedule awaited.
| CUTOVER | 2024-01-31 | 6PM onwards | Hot Cutover | Weekhiang Tay | Shared with Client | SENT | Provided | Provided | n/a | n/a | n/a | CHG00000061652
Krisshop @ Changi | HW INSTALLATION & CUTOVER | 2024-01-25 | 4PM-10PM |  | Siti Nur Hawa | Shared with Client | SENT | Provided | Provided | Cleared | Provided | Kasiraja | CHG00000062701
ALPS - SIAEC | HW INSTALLATION & CUTOVER | 2024-02-01 | 4PM-10PM | Hot Cutover | Arion Fermo | Shared with Client | SENT | Provided | Provided | Cleared | Provided | Kasiraja | CHG00000063182
LOYANG SSC | HW INSTALLATION & CUTOVER (CANCELLED) | 2024-01-24 | 4PM-10PM |  | 2024-02-01 | Shared with Client |  | Provided |  |  | Provided | Kasiraja | CHG00000062073 | cancelled due to issues in DC. SIA to solve internally and propsoed new date. Cancelled on 23-Jan
| HW INSTALLATION & CUTOVER | 2024-02-02 | 4PM-10PM | Hot Cutover | Siying Png | Shared with Client | SENT | Provided | Provided | Cleared | Provided | Kasiraja | CHG00000062073
Scoot - T3 | HW INSTALLATION & CUTOVER | 2024-02-06 | 6PM-8PM | n/a | n/a | Shared with Client | SENT | Provided | n/a | n/a | n/a | n/a | CHG00000063625
Scoot - T1 | HW INSTALLATION & CUTOVER | 2024-02-07 | 4PM-10PM |  | Joey Puah Gie Ee | Shared with Client | SENT | Provided | Provided | Cleared | Provided | Kasiraja | CHG00000063632
Krisshop @ SICC2 | HW INSTALLATION & CUTOVER | 2024-02-14 | 4PM-10PM |  | Siti | Shared with Client | SENT | Provided |  | Cleared | Provided | Kairaja
KRISLITE@SIAEC | HW INSTALLATION & CUTOVER (CANCELLED) | 2024-01-16 | 4PM-10PM |  | Hafiz | Shared with Client |  | Provided |  |  | Provided |  | CHG00000061651 | Cancelled due to routing issue. SIA to solve internally. Awaiting new date for the activity. Cancelled on 15-Jan
| HW INSTALLATION & CUTOVER | 2024-02-15 | 4PM-10PM |  | Hafiz | Shared with Client |  | Provided |  |  | Provided |  | CHG00000061651
ION | HW INSTALLATION & CUTOVER | 2024-02-16 | 6PM-10PM | n/a | Sharon | Shared with Client | SENT | n/a | n/a | n/a | n/a | n/a
Datapost | HW INSTALLATION & CUTOVER | 2024-02-19 | 4PM-10PM |  |  | Shared with Client
Mentormedia | HW INSTALLATION & CUTOVER | 2024-02-20 | 4PM-10PM |  |  | Shared with Client
PTB4 - SIAEC | HW INSTALLATION & CUTOVER | 2024-02-21 | 4PM-10PM |  |  | Shared with Client
SICC1 | HW INSTALLATION & CUTOVER | 2024-02-26 | 4PM-10PM |  |  | Shared with Client | [6 empty] | CHG00000062702

## HL-Project Plan
Site# | Delivery Timelines | Duration in Working Days | Tentative Start Date | Tentative Delivery Date | Owner | Updates | RAG Status
| MSA Approved & Issued | 1 | 2022-11-30 | 2022-11-30 | SIA | Completed
| Order Processing | 10 | 2022-12-01 | 2022-12-15 | Singtel | WIP
| External Kickoff | 1 | 2022-12-07 | 2022-12-07 |  | Completed
| HLD Preparation, Submission & Signoff | 30 | 2023-02-03 | 2023-03-17 | Singtel | WIP
| LLD Preparation, Submission & Signoff | 20 | 2023-03-20 | 2023-04-17 | Singtel | WIP
| Hardware - Procurement & Material Delivery | 175 | 2022-12-01 | 2023-08-03 | Singtel | WIP
| Orchestrator Readiness | 14 | 2023-10-02 | 2023-10-20
1 | Scoot Relocation
1.1 | PO awarded for relocation | 1 | 2023-03-09 | 2023-03-09 | SIA
1.2 | Technical Alignment with Client for Relocation | 1 | 2023-03-09 | 2023-03-09 | SIA/SCOOT/SINGTEL
1.3 | Relocation of HW for Scoot Sites | 10 | 2023-03-10 | 2023-03-24 | SINGTEL
I | DC Sites
1 | SIA Primary Data Centre (TSQ) | 60 | 2023-08-11 | 2023-11-03 | Singtel | HW to be replaced after identifying DOA. HW currently at Partner Office for Burn Test. Installation to be scheduled next week, to establish connectivity to V Manage.
2 | SIA Secondary Data Centre (Kim Chuan DCE) | 65 | 2023-08-04 | 2023-11-03 | Singtel | HW Installation completed and connectivity with V Manage established. |  | Provisioning Check List
II | Spoke Sites | [6 empty] | IM Plan | Meeting Invite | BOM details | config flies
1 | CHAI CHEE | 32 | 2023-09-20 | 2023-11-03 | Singtel | HW Installation scheduled on 28-Sep. |  | 2023-10-28 | 2023-10-28 | 2023-10-21 | 2023-10-28
11 | ION | 32 | 2023-11-27 | 2024-01-10 | Singtel | HW Installation tentative date is 5-Oct. |  | 2024-01-04 | 2024-01-04 | 2023-12-28 | 2024-01-04
12 | ALH GUARD | 32 | 2023-11-29 | 2024-01-12 | Singtel | Site Survey Completed. Infra Ready for Deployment |  | 2024-01-06 | 2024-01-06 | 2023-12-30 | 2024-01-06
6 | SMC - SIAEC | 32 | 2023-10-17 | 2023-11-30 | Singtel |  |  | 2023-11-24 | 2023-11-24 | 2023-11-17 | 2023-11-24
3 | LOYANG - SSC | 32 | 2023-12-14 | 2024-01-27 | Singtel |  |  | 2024-01-21 | 2024-01-21 | 2024-01-14 | 2024-01-21
13 | DATAPOST (Standalone) - Biz Partners | 32 | 2023-12-21 | 2024-02-03 | Singtel |  |  | 2024-01-28 | 2024-01-28 | 2024-01-21 | 2024-01-28
14 | MENTORMEDIA (Standalone) - Biz Partners | 32 | 2023-12-28 | 2024-02-10 | Singtel |  |  | 2024-02-04 | 2024-02-04 | 2024-01-28 | 2024-02-04
18 | Scoot - T1 | 32 | 2024-01-04 | 2024-02-17 | Singtel |  |  | 2024-02-11 | 2024-02-11 | 2024-02-04 | 2024-02-11
5 | PTB4 - SIAEC | 32 | 2024-01-11 | 2024-02-24 | Singtel |  |  | 2024-02-18 | 2024-02-18 | 2024-02-11 | 2024-02-18
15 | KRISSHOP @ CHANGI | 32 | 2024-01-18 | 2024-03-02 | Singtel |  |  | 2024-02-25 | 2024-02-25 | 2024-02-18 | 2024-02-25
4 | SICC1 | 32 | 2024-01-25 | 2024-03-09 | Singtel |  |  | 2024-03-03 | 2024-03-03 | 2024-02-25 | 2024-03-03
9 | EC ENGINE - SIAEC | 32 | 2024-02-01 | 2024-03-16 | Singtel |  |  | 2024-03-10 | 2024-03-10 | 2024-03-03 | 2024-03-10
16 | KRISSHOP @ SIGNATURE | 32 | 2023-11-21 | 2024-01-04 | Singtel | HW Installation and migration completed |  | 2023-12-29 | 2023-12-29 | 2023-12-22 | 2023-12-29
8 | ALPS - SIAEC | 32 | 2023-11-28 | 2024-01-11 | Singtel |  |  | 2024-01-05 | 2024-01-05 | 2023-12-29 | 2024-01-05
2 | ESD CHANGI - SIAEC | 32 | 2023-12-05 | 2024-01-18 | Singtel |  |  | 2024-01-12 | 2024-01-12 | 2024-01-05 | 2024-01-12
10 | KRISLITE @ SIAEC | 32 | 2023-12-12 | 2024-01-25 | Singtel |  |  | 2024-01-19 | 2024-01-19 | 2024-01-12 | 2024-01-19
17 | KRISSHOP @ SICC2 | 32 | 2023-12-19 | 2024-02-01 | Singtel |  |  | 2024-01-26 | 2024-01-26 | 2024-01-19 | 2024-01-26
Site# | Delivery Timelines | Tentative Delivery Date | Target dates for IM Plans | Target Dates for Cab Approval | Challenges | RAG Status
Spoke Sites
1 | CHAI CHEE | Completed
6 | SMC - SIAEC | Completed
9 | EC ENGINE - SIAEC | Completed
16 | KRISSHOP @ SIGNATURE | Completed
2 | ESD CHANGI - SIAEC | 2024-01-18 | Submitted | 2024-01-16 | FW rules to be implemented by NTT. Monitoring to be activated by Singtel.
3 | LOYANG - SSC | 2024-02-02 | Submitted | 2024-01-16 | To Schedule on Monday, Wednesday or Friday.
15 | KRISSHOP @ CHANGI | 2024-01-25 | 2024-01-19 | 2024-01-23
18 | ALH GUARD | 2024-01-30 | Submitted | 2024-01-30 | SIA need to apply for cab approvals. CHG00000061532 is the existing approval reference.
4 | SICC1 | 2024-02-26 | 2024-01-19 | 2024-01-23 | IM Plan submitted
8 | ALPS - SIAEC | 2024-02-06 | 2024-01-26 | 2024-01-30
17 | KRISSHOP @ SICC2 | 2024-02-08 | 2024-01-26 | 2024-01-30
11 | ION | 2024-02-15 | 2024-01-26 | 2024-01-30
12 | Scoot - T1 | 2024-02-07 | 2024-02-09 | 2024-02-13 | Meeting to be arranged with NTT
10 | KRISLITE @ SIAEC | 2024-02-23 | 2024-02-09 | 2024-02-13 | CHG00000061651 is the existing cab approval reference.
13 | DATAPOST (Standalone) - Biz Partners | 2024-02-27 | 2024-02-16 | 2024-02-20 | Ethernet links to be delivered
14 | MENTORMEDIA (Standalone) - Biz Partners | 2024-02-29 | 2024-02-16 | 2024-02-20 | Ethernet links to be delivered
5 | PTB4 - SIAEC | 2024-03-05 | 2024-02-23 | 2024-02-27 | UG build to be completed
|  | Planned Date | Expected Date | Dependency
2 | ESD CHANGI - SIAEC | 2024-01-30 | 2024-01-30 |  | Tuesday | Activity to be scheduled after 8PM as per end usser requirement.
18 | ALH GUARD | 2024-02-06 | 2024-01-31 |  | Wednesday | Cabling completed. SIA to support for Cutover.
8 | ALPS - SIAEC | 2024-02-15 | 2024-02-01 | Singtel | Thursday | Singtel to revert after FE availability.
3 | LOYANG - SSC | 2024-02-01 | 2024-02-02 | SIA | Friday | FE availability confirmed. SIA to share rack and power availability toplan for cutover.
| Scoot - T3 |  | 2024-02-06 | SIA | Tuesday | SIA to cehck on In House cabling , downtime schedule and technical discussions with Scoot on Tuesday, 2PM. Pending WAN IP
12 | Scoot - T1 | 2024-02-29 | 2024-02-07 | SIA | Wednesday | SIA to cehck on In House cabling , downtime schedule and technical discussions with Scoot on Tuesday, 2PM.
17 | KRISSHOP @ SICC2 | 2024-02-20 | 2024-02-14 | Singtel | Wednesday | Dependency with Singtel to rectify the orders.Need Rack details from POC. To confirmed by 7-Feb
10 | KRISLITE @ SIAEC | 2024-01-16 | 2024-02-15 | SIA | Thursday | SIA to revert after checking with End User.
11 | ION | 2024-02-27 | 2024-02-16 | SIA | Friday | SIA to revert after checking with End User. Suggested on Friday. No FE required
13 | DATAPOST (Standalone) - Biz Partners | 2024-03-05 | 2024-02-19 | Singtel | Monday | Site survey completed on 7-Feb. Yet to get the survey results. Link delivery to be planned after CNY if Infra available. Eexisting Elite links be used for cutover, if link delivery is delayed.
14 | MENTORMEDIA (Standalone) - Biz Partners | 2024-03-07 | 2024-02-20 | Singtel | Tuesday | site survey completed. Infra available. Link delivery to be planned after CNY. Eexisting Elite links be used for cutover, if link delivery is delayed.
5 | PTB4 - SIAEC | 2024-03-12 | 2024-02-21 | Singtel | Wednesday | Link to be ready by 18-Feb. Cutoover to be planned after that.
4 | SICC1 | 2024-02-08 | 2024-02-26 | SIA | Monday | 26-Feb planned for cutover. End user availbaility to be checked by SIA. Singtel to work on C1900 routers Decomm. Start at 4PM till 8PM
i. | Xsys have no resource on 20-Feb
Xsys have no resource on 15-Feb & 16-Feb
|  | Planned Date | Expected Date | Dependency
2 | ESD CHANGI - SIAEC | 2024-01-30 | 2024-01-30 |  | Tuesday | Activity to be scheduled after 8PM as per end usser requirement.
18 | ALH GUARD | 2024-02-06 | 2024-01-31 |  | Wednesday | Cabling completed. SIA to support for Cutover.
8 | ALPS - SIAEC | 2024-02-15 | 2024-02-01 | Singtel | Thursday | Singtel to revert after FE availability.
3 | LOYANG - SSC | 2024-02-01 | 2024-02-02 | SIA | Friday | FE availability confirmed. SIA to share rack and power availability toplan for cutover.
| Scoot - T3 |  | 2024-02-06 | SIA | Tuesday | SIA to cehck on In House cabling , downtime schedule and technical discussions with Scoot on Tuesday, 2PM. Pending WAN IP
12 | Scoot - T1 | 2024-02-29 | 2024-02-07 | SIA | Wednesday | SIA to cehck on In House cabling , downtime schedule and technical discussions with Scoot on Tuesday, 2PM.
17 | KRISSHOP @ SICC2 | 2024-02-14 | 2024-02-14 |  | Wednesday | No dependency
11 | ION | 2024-02-16 | 2024-02-16 |  | Friday | No dependency
10 | KRISLITE @ SIAEC | 2024-02-15 | 2024-02-19 |  | Thursday | No dependency
13 | DATAPOST (Standalone) - Biz Partners | 2024-02-19 | 2024-02-21 | Singtel | Monday | Site survey completed on 7-Feb. Yet to get the survey results. Link delivery to be planned after CNY if Infra available. Eexisting Elite links be used for cutover, if link delivery is delayed.
14 | MENTORMEDIA (Standalone) - Biz Partners | 2024-02-20 | 2024-02-22 | Singtel | Tuesday | site survey completed. Infra available. Link delivery to be planned after CNY. Eexisting Elite links be used for cutover, if link delivery is delayed.
5 | PTB4 - SIAEC | 2024-02-21 | 2024-02-23 | Singtel | Wednesday | Primary link likely to be delayed, as ED delivery will need approvals.
4 | SICC1 | 2024-02-26 | 2024-02-26 | SIA | Monday | 26-Feb planned for cutover.
Formulas:
Tentative Delivery Date = [Tentative Start Date]
Tentative Delivery Date = WORKDAY([Tentative Start Date],[Duration in Working Days])
Tentative Start Date = WORKDAY([Tentative Delivery Date, row above],1)
Tentative Start Date = WORKDAY([Tentative Delivery Date],-[Duration in Working Days])
IM Plan = [Tentative Delivery Date]-6
Meeting Invite = [IM Plan]
BOM details = [IM Plan]-7
config flies = [Meeting Invite]

## Summary Tab
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | Dependency | Completion Status | Updates
SCOOT - T3 | Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric, with client owned links | COMPLETED | NA | COMPLETED | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA | NA | NEEDS ATTENTION | 2023-07-12 | AMENDMENT REQUIRED | NEEDS ATTENTION | AGGRESSIVE | 95.65% | Sales | Partially Completed | 03-Dec: Migration of DC traffic to Cedge devices after headsup from SIA 28-Nov: Migration of DC traffic to Cedge devices after headsup from SIA 30Oct- Cease orders for Vedge devices to be raised. 10Oct- Cease orders for Vedge devices to be raised. 30Sep- Cease orders for Vedge devices to be raised. 11Sep- Cease orders for Vedge devices to be raised. 6Jul- Migration completed and handed over to Client
TSQ | SDWAN Connectivity setup at TSQ DC with C8500 Device | COMPLETED | NA | COMPLETED | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA | NA | NEEDS ATTENTION | 2023-05-25 |  |  |  | 81.3% | Client | Fully Completed | 28-Nov: Site completed on 3-Nov. 30-Oct: Awaiting client headsup to integrate with SIA SDWAN fabric. 10Oct- RMA device installed and connected to VManage. Awaiting client headsup to integrate with SIA SDWAN fabric. 30Sep- FW rules to be implemented and services to be put to Production. Cease orders to be raised for Vedge devices. 11Sep- FW rules to be implemented and services to be put to Production. Cease orders to be raised for Vedge devices. 3Aug- Migration completed and handed over to Client
DCE DC | SDWAN Connectivity setup at TSQ DC with C8500 Device | COMPLETED | NA | COMPLETED | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA | NA | NEEDS ATTENTION | 2023-08-15 |  |  |  | 100% | Client | Fully Completed | 28-Nov: Site completed on 3-Nov. 30Oct- Awaiting client headsup to integrate with SIA SDWAN fabric. 10Oct- HW installed and awating client headsup to integrate with SIA SDWAN fabric. 30Sep- FW rules to be implemented and services to be put to Production. Cease orders to be raised for Vedge devices. 11Sep- FE visit finalization, Access approvals to be sought for installation on 14-Sep.
CHAI CHEE | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2023-11-10 | NEEDS ATTENTION | 2023-10-17 | AMENDMENT REQUIRED |  | TO ARCHIVE | 100% | Client | Fully Completed | 28-Nov: Site completed on 3-Nov. 30Oct- Partial Migration completed. Awaiting Client feedback and DC site readiness to migrate to SDWAN fabric. 10Oct- HW Installation completed and integrated with VManage. Cease work orders for Vedge and Singnet E to be raised. Cease dates to be confirmed with Client. Partial migration planned for /25 subnets as per client request, as part of Pilot sites. Migration to SDWAN fabric to be scheduled after heads up from Client. 30Sep- HW Installation completed and integrated with VManage. Cease work orders for Vedge and Singnet E to be raised. Cease dates to be confirmed with Client. 11Sep- Mux Installation Schduled. HW replacement schedule don 21-Sep. Access and TD to be secured. Cease work orders for Vedge and Singnet E to be raised. Cease dates to be confirmed with Client.
ION | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2023-12-22 | AMENDMENT REQUIRED |  |  | 75% | Client | Partially Completed | 03-Dec: Migration to be scheduled after headsup from SIA. 28-Nov: Migration to be scheduled after headsup from SIA. 30Oct- HW installation compeleted on 12-Oct. To be integrated with SDWAN fabric after heads up from Client. 10Oct- HW installation scheduled on 12-Oct. To be integrated with SDWAN fabric after heads up from Client. 30Sep- Mux Installation completed and link delivered. HW Installation scheduled on 5-Oct. 11Sep- Site survey completed. Mux Installation to be scheduled.
ALH GUARD | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-12 | AMENDMENT REQUIRED |  |  | 90.65% | Client | Partially Completed | 03-Dec: Cutover to be planned after cable issue and power space are resolved. SIA will notify once ready. 28-Nov: Cutover to be planned after cable issue and power space are resolved. SIA will notify once ready. 22Nov- HW installed but not configured due to site conditions. Cutover to be planned after cable issue and power space are resolved. 14Nov- Actiivty planned on 15-Nov., postponed to 22-Nov by Client. HW installation on 22-nov and Cutover on 23-Nov. 7Nov- Site visit required to understand Mux and CPE installation. Site visit planned on 9-Nov. 30Oct- Link ready. HW installation and Migration to be scheduled after DC site readiness. Rack space for HW instalation to be understood from Client. 10Oct- Bandwidth incorrectly recorded in orders, as notified by FOB. Corrections made and aligned with LTC and GSP team. Link delivery scheduled on 16-Oct. 30Sep- Mux Installation and Link delivery scheduled on 10-Oct. HW Installation scheduled on 12-Oct. 11Sep- Site survey to be intiated.
SMC- SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to integrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NA | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2023-11-30 | AMENDMENT REQUIRED |  |  | 97.83% | PM | Fully Completed | 12-deC: Migration Completed. Zscalar testing to be completed after headsup from SIA. 08-Dec: Migration completed. Failvoer testing to be completed after headsup from Client. 03-Dec: Initially HW Installation and Cutover scheduled 30-Nov, but had to be postponed to 7-Dec as one of the Firewall rules are still pending for approval. 28-Nov: Activity planned on 30-Nov starting at 4PM. 22Nov- C1900 collected. Mux installed. Actiivty to be planned as Hot cutover to free rack space for Cedge devices. 31Oct- No rack space for CEdge devices. Cease work orders for vedge devices need to be raised to remove the existing HW and replace with CEdge device. Cease orders for C1900 devices to be raised as requested by Client. MUX installed and link delivered for deployment. 30Oct- Link delivery planned on 31-Oct, as client support to clear the rack space for MUX. Cease orders for Vedge devices to be raised to make space for Cedge devices. 10Oct- Site survey completed on 9-Oct. Infra identified. Link delivery to be planned. 30Sep-Site Survey to be initiated as Client needs this site earlier.
DATAPOST | Provisioning of Singnet Ethernet Links with client provided deiverse link and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | RISK | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA |  | NEEDS ATTENTION | 2024-02-05 |  |  |  | 41.09% | Sales | WIP | 03-Dec: SIA to confirm diverse link readiness 28-Nov: SIA to confirm diverse link readiness 31Oct- Provide Work orders for Diverse Ethernet Links to be raised. Cease orders for Vedge and Singnet E Links to be raised. 10Oct- Work orders for Diverse Ethernet Links to be raised. Cease orders for Vedge and Singnet E Links to be raised. 30Sep- Work orders for Diverse Ethernet Links to be raised. Cease orders for Vedge and Singnet E Links to be raised.
Mentor Media | Provisioning of Singnet Ethernet Links with client provided deiverse link and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | RISK | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA |  | NEEDS ATTENTION | 2024-02-12 |  |  |  | 43.26% | Sales | WIP | 03-Dec: SIA to confirm diverse link readiness. 28-Nov: SIA to confirm diverse link readiness. 31Oct- Provide Work orders for Diverse Ethernet Links to be raised. Cease orders for Vedge and Singnet E Links to be raised. 10Oct- Work orders for Diverse Ethernet Links to be raised. Cease orders for Vedge and Singnet E Links to be raised. 30Sep- Work orders for Diverse Ethernet Links to be raised. Cease orders for Vedge and Singnet E Links to be raised.
Scoot T1 | Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric, with client owned links | COMPLETED | NA | COMPLETED | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA |  | NEEDS ATTENTION | 2024-02-19 | AMENDMENT REQUIRED |  |  | 80% | Sales | WIP | 03-Dec: SIA to confirm primary and backup link readiness. 28-Nov: SIA to confirm primary and backup link readiness. 28-Nov: SIA to confirm primary and backup link readiness. 31Oct- Cease orders for Vedge devices to be raised. Client to update on diverse links readiness to plan for HW installation. 10Oct- Cease orders for Vedge devices to be raised. 30Sep- Cease orders for Vedge devices to be raised. 11Sep- Cease orders for Vedge devices to be raised. 6Jul- Migration completed and handed over to Client
PTB4 - SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | RISK | RISK |  | NEEDS ATTENTION | 2024-02-26 | AMENDMENT REQUIRED |  |  | 72.5% | PM | WIP | 19-Dec: ZFJ7294019 circuit activated. ZFJ7294020 will be completed after UG works. 03-Dec: Planner suggest alternative route instead of UG to reduce overall time needed. More updates will be provided after site survey on 1-Dec. 28-Nov: UG infra in currently in progress. 7Nov- ZFJ7294019 has existing fibre. ZFJ7294020 needs UG top up. Team identifed that pipe available to pull the fibre and does not involve any cost. Team to work on building UG infra first followed by IB infra. 31Oct- Additonal cost to be discussed with Client for PD delivery. Awaiting feedback from SDO and IE on the cost to get approval from Client. 16Oct- IE planner confirmed additional costs involved irrespective of Infra built within or outside campus.FOB to revert with details to determine cost and netxt course of action. 12Oct- Site survey completed. PD could not be establsihed due to site condition.Infra team checking is cost involve fro building UG. Link readiness to be estimated after cost approvals, if any. 30Sep-Cease orders for Vedge and Singnet E Links to be raised.
Krisshop @ Changi | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | RISK | RISK |  | NEEDS ATTENTION | 2024-03-04 | AMENDMENT REQUIRED |  |  | 80% | PM | WIP | 28-Nov: MUX installation scheduled on 1-Dec. 21Nov- Mux installation postponed as BMO requires more documents. 13Nov- Patching completed. MUX installation and link delivery to be planned. 9Nov- Intercab patching requird at CAB. MUX installation and link delivery to be planned after that. 31Oct- Site survey compeleted on 16-Oct. Infra available. Pending CE routing to be released. 30Sep-Cease orders for Vedge and Singnet E Links to be raised.
SICC1 | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-03-11 | AMENDMENT REQUIRED |  |  | 71.3% | Client | WIP | 03-Dec: First link (ZFJ0973007 ) delivered. Second Link (ZFJ0973008) intercab patching on 5-Dec. Link to be delivered after patching. 28-Nov: Patching scheduled on 29-Nov to 5-Dec 22Nov- MUX installation scheduled on 24-Nov. 15Nov- Site survey completed. MUX and Link installation to be scheduled. 10Nov- Site survey completed on 10-Nov. C1900 devices need to be removed to create power space. 31Oct- Site survey planned could not be completed, due to client unavailability. Need to reschedule. 30Sep-Cease orders for Vedge and Singnet E Links to be raised.
EC Engine | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-03-18 | AMENDMENT REQUIRED |  |  | 97.5% | Client | Fully Completed | 11-Dec: MUX installation scheduled tomorrow due to urgency. Client support required to remove the existing C1900 devices. HW installation scheduled on 15-Dec. 03-Dec: S/N. of C1900 devices to be shared to initiated collection. Site to be planned for Hot cutover to free power soruce for Cedge devices. IB works completed. MUX installation to be scheduled after power source available. 28-Nov: IB works to be completed and IB works scheduled on 30-Nov.C1900 devices need to be remvoed to free power source. VNS001790 access approval shared. 22Nov- IB works to be completed. C1900 devices need to be remvoed to free power source. Site to be planned for Hot cutiover to free power soruce for Cedge devices. Access sought from Client on 30-Nov for IB works. 7Nov- Site survey completed. Infra available. Need power source availability confirmation from client. 31Oct- Site survey to be scheduled on 3rd Nov. Cease orders for Vedge and Singnet E Links to be raised. 30Sep-Cease orders for Vedge and Singnet E Links to be raised.
KRISSHOP @ SIGNATURE | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-04 | AMENDMENT REQUIRED |  |  | 97.5% | PM | Fully Completed | 10Jan- Migrations scheduled and completed. 03-Dec: Link delivered on 30-Nov. HW installation to be scheduled. 28-Nov: Documentation completed for MUX installation and scheduled on 30-Nov.2pm. 22Nov- Site Survey completed on 1-Nov. Infra available. Documentation completed for MUX installation and scheduled on 28-Nov. 31Oct- Site survey to be scheduled. Cease orders for Vedge and Singnet E Links to be raised. 30Sep-Cease orders for Vedge and Singnet E Links to be raised.
LOYANG - SSC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-29 | AMENDMENT REQUIRED |  |  | 85% | PM | WIP | 03-Dec: Link delivery completed on 29-Nov. HW installation & Cutover to be scheduled. 28-Nov: 1st link delivered on 14-Nov. Splicing completed. 2nd link delivery and MUX installation scheduled on 29-Nov. VNS022650 22nov- 1st link delivered on 14-Nov. 2nd link delivery and MUX installation scheduled on 24-Nov. 15nov- 1st link delivered. 2nd link delivery scheduled on 16-Nov. 1Nov- MUX installation planned on 9-Nov, 10AM - 12noon. 31Oct- IB works to be completed to deliver link. Vendor to complete IB works. Cease orders for Vedge and Singnet E Links to be raised. Rack space available for MUX and Cedge devices. 30Oct- Site survey completed. Site survey results to be released. Cease orders for Vedge and Singnet E Links to be raised. Rack space available for MUX and Cedge devices. 30Sep-Cease orders for Vedge and Singnet E Links to be raised.
ALPS - SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-29 | AMENDMENT REQUIRED |  |  | 80% | Sales | WIP | 05-Dec: Infra works scheduled on 14th and 15th Dec. Awaiting access approvals. 03-Dec: Scissors lift cost approved by AM. SDO to porceed for IB work completion. 28-Nov: Chasing AM on the additional cost for scissors lift. 10Nov- Scissors lift cost will be 483$. To be approved by AM to complete the IB works. 9Nov- Scissor lift require to complete IB works. FOB working on the cost 31Oct- IB works to be completed to deliver link. Vendor to complete IB works. Cease orders for Vedge and Singnet E Links to be raised. 30Oct- Site survey scheduled on 30-Oct. Cease orders for Vedge and Singnet E Links to be raised. 30Sep-Cease orders for Vedge and Singnet E Links to be raised.
ESD CHANGI - SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-18 | AMENDMENT REQUIRED |  |  | 78.15% | PM | WIP | 03-Dec: Infra available and MUX installation completed on 23-Nov. HW installation & Cutover to be planned. 23Nov- MUX installation schedueld on 23-Nov. 31Oct- Site survey completed on 30-Oct. Infra available for MUX installation. Cease orders for Vedge and Singnet E Links to be raised. 30Oct- Site survey scheduled on 30-Oct. Cease orders for Vedge and Singnet E Links to be raised. 30Sep-Cease orders for Vedge and Singnet E Links to be raised.
KRISLITE @ SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-25 | AMENDMENT REQUIRED |  |  | 87.5% | PM | WIP | 12-Dec: MUX installation and link delivery completed on 8-Dec. HW installation and migration to be scheduled after headsup from SIA. 03-Dec: Pre-configuration completed for both circuits. mux installation and circuit activation 8 Dec 2023 @ 10am – 12pm. 28-Nov: MUX installation schedueld on 30-Nov. 22Nov- MUX isntallation likely to be scheduled on 30-Nov. Routing to be released. 17Nov- Patching completed. MUX and link delviery to be scheduled. 16Nov- SDO has advised for Intercab patching. 9Nov- Resurvey initiated as order requirement is PD. Access requried to MDF. Resurvey scheduled on 15-Nov. 31Oct- Site survey scheduled on 31-Oct. Cease orders for Vedge and Singnet E Links to be raised. 30Sep-Cease orders for Vedge and Singnet E Links to be raised.
KRISSHOP @ SICC2 | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-02-01 | AMENDMENT REQUIRED |  |  | 87.5% | Order Raising | WIP | 12-Dec: MUX installation scheduled on 14-Dec, 10am - 12pm. 03-Dec: Splicing works scehduled on 6-dec. MUX installation scheduled on 6-Dec. 28-Nov: Splicing works is pending and MUX installation likely on 5-Dec. 22nOV- Splicing works to be completed and MUX installation likely on 27-Nov. 9Nov- Site survey completed. Fibre build onoging. Order raised as PD, should be rectifeied to ED, as per scope. Cease orders for Vedge and Singnet E Links to be raised. 31Oct- Site survey scheduled on 1-Nov. Cease orders for Vedge and Singnet E Links to be raised. 30Sep-Cease orders for Vedge and Singnet E Links to be raised.
2024-02-09 | SIA - SDWAN Tech Refresh Project Updates - Dashboard
Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing Completed and Handed Over | Target RFS | Updates
SCOOT - T3 | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-02-06 | Site Completed
TSQ | COMPLETED | NA | NA | NA | COMPLETED | COMPLETED | 2023-11-03 | Site Completed
DCE DC | COMPLETED | NA | NA | NA | COMPLETED | COMPLETED | 2023-11-03 | Site Completed
CHAI CHEE | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2023-11-03 | Site Completed
ION | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | WIP | 2024-02-15 | HW installation completed on 5-Oct. Migration to be scheduled after headsup from SIA.
ALH GUARD | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-02-12 | Site Completed
SMC- SIAEC | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2023-12-07 | Site Completed
LOYANG - SSC | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-02-02 | Site Completed
DATAPOST | COMPLETED | COMPLETED | WIP | WIP | TO BE SCHEDULED | TO BE SCHEDULED | 2024-02-20 | HW installation to be planned after Ethernet links are delivered
Mentor Media | COMPLETED | COMPLETED | WIP | WIP | TO BE SCHEDULED | TO BE SCHEDULED | 2024-02-23 | HW installation to be planned after Ethernet links are delivered
Scoot T1 | COMPLETED | NA | NA | NA | COMPLETED | COMPLETED | 2024-02-07 | Site Completed
PTB4 - SIAEC | COMPLETED | NA | COMPLETED | WIP | WIP | TO BE SCHEDULED | 2024-02-27 | Primary Link delivered. Secondary Link to be delivered after UG completion. UG build is challengign as per Infra team. Alterante soluiton to be discussed with Client.
Krisshop @ Changi | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-01-30 | Site Completed
SICC1 | COMPLETED | COMPLETED | COMPLETED | COMPLETED | TO BE SCHEDULED | TO BE SCHEDULED | 2024-02-26 | MUX installation and link delivery completed on 13-Dec. HW installation to be planned after headsup from SIA.
EC Engine | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2023-12-14 | Site Completed
KRISSHOP @ SIGNATURE | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-01-10 | Site Completed
ALPS - SIAEC | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-02-06 | Site Completed
ESD CHANGI - SIAEC | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-01-18 | Site Completed
KRISLITE @ SIAEC | COMPLETED | COMPLETED | COMPLETED | COMPLETED | WIP | WIP | 2024-02-23 | HW installation and cutover planned on 16-Jan-24. IM plan to be submitted by 9-Jan.
KRISSHOP @ SICC2 | COMPLETED | COMPLETED | COMPLETED | COMPLETED | WIP | WIP | 2024-02-08 | MUX installation and link delivery completed on 14-Dec. HW installation to be planned after headsup from SIA.
| TO BE SCHEDULED | INITIATED | WIP | COMPLETED
Order Processing |  | 0 | 0 | 20
Site Survey | 0 | 0 | 2 | 15
MUX Installation & Link Readiness | 0 | 0 | 3 | 14
HW Installation | 3 | 0 | 3 | 14
Testing Completed and Handed Over | 4 | 0 | 3 | 13

## CRD controls
2024-02-09
Site ID | Work Order # | Svc# | Order Type | Current CRD | Work Order Status | Remarks
TSQ | ZEW2664034 | SDWP0003400069SNG | Provide | 2023-11-03 | Closed
DCE | ZEW2664033 | SDWP0003400068SNG | Provide | 2023-11-03 | Closed
ION ORCHARD | ZEW2664001 | SDWP0003400036SNG | Provide | 2024-02-15 | Open
ION ORCHARD | ZEV9644003 | ETHCE00296864SNG | Provide | 2023-09-25 | Closed
ION ORCHARD | ZFJ0973002 | CE00296864SNG | Provide | 2023-09-25 | Closed
ION ORCHARD | ZEW2664002 | SDWP0003400037SNG | Provide | 2024-02-15 | Open
ION ORCHARD | ZEV9644004 | ETHCE00296862SNG | Provide | 2023-09-25 | Closed
ION ORCHARD | ZFJ0973001 | CE00296862SNG | Provide | 2023-09-25 | Closed
ION ORCHARD | ZEV9644005 | ELITE00169960SNG | Cease | 2024-04-30 | Open
ION ORCHARD | ZLL8699001 | 00169960SNG | Cease | 2024-04-30 | Open
ION ORCHARD | ZEV9748002 | 181426229 | Cease | 2024-04-30 | Open
ION ORCHARD | ZKQ1431007 | M0583682 | Cease | 2024-04-30 | Open
ION ORCHARD | ZKQ1431008 | M0669817 | Cease | 2024-04-30 | Open
CHAI CHEE | ZEW2664019 | SDWP0003400054SNG | Provide | 2023-11-03 | Closed
CHAI CHEE | ZFJ2259005 | ETHCE00296949SNG | Provide | 2023-09-11 | Closed
CHAI CHEE | ZFJ2460003 | CE00296949SNG | Provide | 2023-09-11 | Closed
CHAI CHEE | ZEW2664020 | SDWP0003400055SNG | Provide | 2023-11-03 | Closed
CHAI CHEE | ZFJ2259006 | ETHCE00296953SNG | Provide | 2023-09-11 | Closed
CHAI CHEE | ZFJ2460004 | CE00296953SNG | Provide | 2023-09-11 | Closed
CHAI CHEE | ZFJ2259004 | ELITE00171059SNG | Cease | 2023-11-10 | Closed
CHAI CHEE | ZFJ2321003 | 00171059SNG | Cease | 2023-11-10 | Closed
CHAI CHEE | ZFJ2321004 | 181426421 | Cease | 2023-11-10 | Closed
CHAI CHEE | ZKP3398001 | M0567363 | Cease | 2024-04-30 | Open
CHAI CHEE | ZKP3398002 | M0578588 | Cease | 2024-04-30 | Open
ALH Guard | ZEW2664021 | SDWP0003400056SNG | Provide | 2024-02-12 | Open
ALH Guard | ZFJ2259009 | ETHCE00296962SNG | Provide | 2023-10-16 | Closed
ALH Guard | ZFJ2460005 | CE00296962SNG | Provide | 2023-10-16 | Closed
ALH Guard | ZEW2664022 | SDWP0003400057SNG | Provide | 2024-02-12 | Open
ALH Guard | ZFJ2259010 | ETHCE00296963SNG | Provide | 2023-10-16 | Closed
ALH Guard | ZFJ2460006 | CE00296963SNG | Provide | 2023-10-16 | Closed
ALH Guard | ZFJ2259008 | ELITE00171056SNG | Cease | 2024-04-30 | Open
ALH Guard | ZFJ2321005 | 00171056SNG | Cease | 2024-04-30 | Open
ALH Guard | ZFJ2321006 | 181426414 | Cease | 2024-04-30 | Open
ALH Guard |  |  | Cease
SMC - SIAEC | ZEW2664011 | SDWP0003400046SNG | Provide | 2023-12-07 | Closed
SMC - SIAEC | ZEV9644018 | ETHCE00296947SNG | Provide | 2023-10-31 | Closed
SMC - SIAEC | ZFJ0973009 | CE00296947SNG | Provide | 2023-10-31 | Closed
SMC - SIAEC | ZEW2664012 | SDWP0003400047SNG | Provide | 2023-12-07 | Closed
SMC - SIAEC | ZEV9644019 | ETHCE00296951SNG | Provide | 2023-10-31 | Closed
SMC - SIAEC | ZFJ0973010 | CE00296951SNG | Provide | 2023-10-31 | Closed
SMC - SIAEC | ZEV9644017 | ELITE00171030SNG | Cease | 2023-12-14 | Closed
SMC - SIAEC | ZEV9748013 | 00171030SNG | Cease | 2023-12-14 | Closed
SMC - SIAEC | ZEV9748014 | 181426370 | Cease | 2023-12-14 | Closed
SMC - SIAEC | ZKQ1431016 | M0663236 | Cease | 2024-04-30 | Open
SMC - SIAEC | ZKQ1431017 | M0669964 | Cease | 2024-04-30 | Open
Data Post | ZEW2664023 | SDWP0003400058SNG | Provide | 2024-02-20 | Open
Data Post | ZEW2664024 | SDWP0003400059SNG | Provide | 2024-02-20 | Open
Data Post | ZKQ1180002 | ELITE00171062SNG | Cease | 2023-12-07 | Closed
Data Post | ZKQ1596003 | 00171062SNG | Cease | 2023-12-07 | Closed
Data Post | ZKQ1596004 | 181426438 | Cease | 2023-12-07 | Closed
Mentor Media | ZEW2664025 | SDWP0003400060SNG | Provide | 2024-02-23 | Open
Mentor Media | ZEW2664026 | SDWP0003400061SNG | Provide | 2024-02-23 | Open
Mentor Media | ZKQ1180003 | ELITE00171070SNG | Cease | 2023-12-07 | Closed
Mentor Media | ZKQ1596005 | 00171070SNG | Cease | 2023-12-07 | Closed
Mentor Media | ZKQ1596006 | 181426445 | Cease | 2023-12-07 | Closed
Scoot T1 | ZCG9563001 | SDWP0003400025SNG | Change | 2023-04-05 | Closed
Scoot T1 | ZEW2664035 | SDWP0003400070SNG | Provide | 2024-02-20 | Open
Scoot T1 | ZEW2664036 | SDWP0003400071SNG | Provide | 2024-02-20 | Open
Scoot T3 | ZCG9563002 | SDWP0003400026SNG | Change | 2023-03-24 | Closed
Scoot T3 | ZEW2664037 | SDWP0003400072SNG | Provide | 2023-06-20 | Closed
Scoot T3 | ZEW2664038 | SDWP0003400073SNG | Provide | 2023-06-20 | Closed
PTB4 - SIAEC | ZEW2664009 | SDWP0003400044SNG | Provide | 2024-02-27 | Open
PTB4 - SIAEC | ZFJ6272017 | ETHCE00296981SNG | Provide | 2024-01-09 | Closed
PTB4 - SIAEC | ZFJ7294019 | CE00296981SNG | Provide | 2024-01-09 | Closed
PTB4 - SIAEC | ZEW2664010 | SDWP0003400045SNG | Provide | 2024-02-27 | Open
PTB4 - SIAEC | ZFJ6272018 | ETHCE00297030SN | Provide | 2024-02-15 | Open
PTB4 - SIAEC | ZFJ7294020 | CE00297030SNG | Provide | 2024-02-15 | Open
PTB4 - SIAEC | ZFJ6272008 | ELITE00171034SNG | Cease | 2024-04-30 | Open
PTB4 - SIAEC | ZFJ7294009 | 00171034SNG | Cease | 2024-04-30 | Open
PTB4 - SIAEC | ZFJ7294010 | 181426387 | Cease | 2024-04-30 | Open
PTB4 - SIAEC | ZKQ1431015 | M0663233 | Cease | 2024-04-30 | Open
PTB4 - SIAEC | ZKQ1431014 | M0663135 | Cease | 2024-04-30 | Open
KRISSHOP @ CHANGI | ZEW2664027 | SDWP0003400062SNG | Provide | 2024-01-25 | Open
KRISSHOP @ CHANGI | ZFJ6272013 | ETHCE00296976SNG | Provide | 2023-12-01 | Closed
KRISSHOP @ CHANGI | ZFJ7294015 | CE00296976SNG | Provide | 2023-12-01 | Closed
KRISSHOP @ CHANGI | ZEW2664028 | SDWP0003400063SNG | Provide | 2024-01-25 | Open
KRISSHOP @ CHANGI | ZFJ6272014 | ETHCE00296977SNG | Provide | 2023-12-01 | Closed
KRISSHOP @ CHANGI | ZFJ7294016 | CE00296977SNG | Provide | 2023-12-01 | Closed
KRISSHOP @ CHANGI | ZFJ6272005 | ELITE00176685SNG | Cease | 2024-02-01 | Open
KRISSHOP @ CHANGI | ZFJ7294005 | 00176685SNG | Cease | 2024-02-01 | Open
KRISSHOP @ CHANGI | ZFJ7294006 | 181503918 | Cease | 2024-02-01 | Open
KRISSHOP @ CHANGI | ZKP3398006 | M0669464 | Cease | 2024-02-01 | Open
KRISSHOP @ CHANGI | ZKP3398008 | M0669565 | Cease | 2024-02-01 | Open
SICC1 | ZEW2664007 | SDWP0003400042SNG | Provide | 2024-02-26 | Open
SICC1 | ZEV9644015 | ETHCE00296939SNG | Provide | 2023-11-30 | Closed
SICC1 | ZFJ0973007 | CE00296939SNG | Provide | 2023-11-30 | Closed
SICC1 | ZEW2664008 | SDWP0003400043SNG | Provide | 2024-02-26 | Open
SICC1 | ZEV9644016 | ETHCE00296940SNG | Provide | 2023-12-13 | Closed
SICC1 | ZFJ0973008 | CE00296940SNG | Provide | 2023-12-13 | Closed
SICC1 | ZEV9644014 | ELITE00171027SNG | Cease | 2024-04-30 | Open
SICC1 | ZEV9748011 | 00171027SNG | Cease | 2024-04-30 | Open
SICC1 | ZEV9748012 | 181426363 | Cease | 2024-04-30 | Open
SICC1 | ZKP3398012 | M0612592 | Cease | 2024-04-30 | Open
SICC1 | ZKP3398013 | M0669967 | Cease | 2024-04-30 | Open
EC Engine | ZEW2664015 | SDWP0003400050SNG | Provide | 2023-12-14 | Open
EC Engine | ZFJ6272011 | ETHCE00296968SNG | Provide | 2023-12-12 | Closed
EC Engine | ZFJ7294013 | CE00296968SNG | Provide | 2023-12-13 | Closed
EC Engine | ZEW2664016 | SDWP0003400051SNG | Provide | 2023-12-14 | Open
EC Engine | ZFJ6272012 | ETHCE00296973SNG | Provide | 2023-12-12 | Closed
EC Engine | ZFJ7294014 | CE00296973SNG | Provide | 2023-12-13 | Closed
EC Engine | ZFJ6272001 | ELITE00171018SNG | Cease | 2023-12-20 | Closed
EC Engine | ZFJ7294003 | 00171018SNG | Cease | 2023-12-20 | Closed
EC Engine | ZFJ7294004 | 181426349 | Cease | 2023-12-20 | Closed
EC Engine | ZKQ1431005 | M0567355 | Cease | 2024-04-30 | Open
EC Engine | ZKQ1431006 | M0669965 | Cease | 2024-04-30 | Open
KRISSHOP @ SIGNATURE | ZEW2664029 | SDWP0003400064SNG | Provide | 2024-01-10 | Closed
KRISSHOP @ SIGNATURE | ZFJ2259012 | ETHCE00297027SNG | Provide | 2023-11-30 | Closed
KRISSHOP @ SIGNATURE | ZFJ2460007 | CE00297027SNG | Provide | 2023-11-30 | Closed
KRISSHOP @ SIGNATURE | ZEW2664030 | SDWP0003400065SNG | Provide | 2024-01-10 | Closed
KRISSHOP @ SIGNATURE | ZFJ2259013 | ETHCE00297028SNG | Provide | 2023-11-30 | Closed
KRISSHOP @ SIGNATURE | ZFJ2460008 | CE00297028SNG | Provide | 2023-11-30 | Closed
KRISSHOP @ SIGNATURE | ZFJ2259011 | ELITE00176684SNG | Cease | 2024-04-30 | Open
KRISSHOP @ SIGNATURE | ZFJ2321007 | 00176684SNG | Cease | 2024-04-30 | Open
KRISSHOP @ SIGNATURE | ZFJ2321008 | 181437009 | Cease | 2024-04-30 | Open
KRISSHOP @ SIGNATURE | ZKP3398010 | M0669352 | Cease | 2024-04-30 | Open
KRISSHOP @ SIGNATURE | ZKP3398011 | M0669376 | Cease | 2024-04-30 | Open
LOYANG - SSC | ZEW2664005 | SDWP0003400040SNG | Provide | 2024-02-23 | Open
LOYANG - SSC | ZEV9644011 | ETHCE00296927SNG | Provide | 2023-11-09 | Closed
LOYANG - SSC | ZFJ0973005 | CE00296927SNG | Provide | 2023-11-09 | Closed
LOYANG - SSC | ZEW2664006 | SDWP0003400041SNG | Provide | 2024-02-23 | Open
LOYANG - SSC | ZEV9644012 | ETHCE00296928SNG | Provide | 2023-11-29 | Closed
LOYANG - SSC | ZFJ0973006 | CE00296928SNG | Provide | 2023-11-29 | Closed
LOYANG - SSC | ZEV9644010 | ELITE00171012SNG | Cease | 2024-04-30 | Open
LOYANG - SSC | ZEV9748009 | 00171012SNG | Cease | 2024-04-30 | Open
LOYANG - SSC | ZEV9748010 | 181426325 | Cease | 2024-04-30 | Open
LOYANG - SSC | ZKQ1431012 | M0565969 | Cease | 2024-04-30 | Open
LOYANG - SSC | ZKQ1431013 | M0669904 | Cease | 2024-04-30 | Open
ALPS - SIAEC | ZEW2664013 | SDWP0003400048SNG | Provide | 2024-02-15 | Open
ALPS - SIAEC | ZFJ6272009 | ETHCE00296946SNG | Provide | 2023-12-21 | Closed
ALPS - SIAEC | ZFJ7294011 | CE00296946SNG | Provide | 2023-12-21 | Closed
ALPS - SIAEC | ZEW2664014 | SDWP0003400049SNG | Provide | 2024-02-15 | Open
ALPS - SIAEC | ZFJ6272010 | ETHCE00296964SNG | Provide | 2023-12-21 | Closed
ALPS - SIAEC | ZFJ7294012 | CE00296964SNG | Provide | 2023-12-21 | Closed
ALPS - SIAEC | ZFJ6272002 | ELITE00182102SNG | Cease | 2024-04-30 | Open
ALPS - SIAEC | ZFJ7294001 | 00182102SNG | Cease | 2024-04-30 | Open
ALPS - SIAEC | ZFJ7294002 | 181443618 | Cease | 2024-04-30 | Open
ALPS - SIAEC | ZKQ1431003 | M0575186 | Cease | 2024-04-30 | Open
ALPS - SIAEC | ZKQ1431004 | M0669963 | Cease | 2024-04-30 | Open
ESD CHANGI - SIAEC | ZEW2664003 | SDWP0003400038SNG | Provide | 2024-02-15 | Open
ESD CHANGI - SIAEC | ZEV9644008 | ETHCE00296909SNG | Provide | 2023-11-23 | Closed
ESD CHANGI - SIAEC | ZFJ0973003 | CE00296909SNG | Provide | 2023-11-23 | Closed
ESD CHANGI - SIAEC | ZEW2664004 | SDWP0003400039SNG | Provide | 2024-02-15 | Open
ESD CHANGI - SIAEC | ZEV9644009 | ETHCE00296914SNG | Provide | 2023-11-23 | Closed
ESD CHANGI - SIAEC | ZFJ0973004 | CE00296914SNG | Provide | 2023-11-23 | Closed
ESD CHANGI - SIAEC | ZEV9644007 | ELITE00171052SNG | Cease | 2024-04-30 | Open
ESD CHANGI - SIAEC | ZEV9748007 | 00171052SNG | Cease | 2024-04-30 | Open
ESD CHANGI - SIAEC | ZEV9748008 | 181513018 | Cease | 2024-04-30 | Open
ESD CHANGI - SIAEC | ZKP3398005 | M0661007 | Cease | 2024-04-30 | Open
ESD CHANGI - SIAEC |  | M0682358 | Cease
KRISLITE @ SIAEC | ZEW2664017 | SDWP0003400052SNG | Provide | 2024-02-22 | Open
KRISLITE @ SIAEC | ZFJ2259002 | ETHCE00296901SNG | Provide | 2023-12-08 | Closed
KRISLITE @ SIAEC | ZFJ2460001 | CE00296901SNG | Provide | 2023-12-08 | Closed
KRISLITE @ SIAEC | ZEW2664018 | SDWP0003400053SNG | Provide | 2024-02-22 | Open
KRISLITE @ SIAEC | ZFJ2259003 | ETHCE00296902SNG | Provide | 2023-12-08 | Closed
KRISLITE @ SIAEC | ZFJ2460002 | CE00296902SNG | Provide | 2023-12-08 | Closed
KRISLITE @ SIAEC | ZFJ2259001 | ELITE00171021SNG | Cease | 2024-04-30 | Open
KRISLITE @ SIAEC | ZFJ2321001 | 00171021SNG | Cease | 2024-04-30 | Open
KRISLITE @ SIAEC | ZFJ2321002 | 181426356 | Cease | 2024-04-30 | Open
KRISLITE @ SIAEC | ZKQ1431009 | M0567318 | Cease | 2024-04-30 | Open
KRISLITE @ SIAEC | ZKQ1431010 | M0669966 | Cease | 2024-04-30 | Open
KRISSHOP @ SICC2 | ZEW2664031 | SDWP0003400066SNG | Provide | 2024-02-29 | Open
KRISSHOP @ SICC2 | ZFJ6272015 | ETHCE00296978SNG | Provide | 2023-12-14 | Closed
KRISSHOP @ SICC2 | ZFJ7294017 | CE00296978SNG | Provide | 2023-12-14 | Closed
KRISSHOP @ SICC2 | ZEW2664032 | SDWP0003400067SNG | Provide | 2024-02-29 | Open
KRISSHOP @ SICC2 | ZFJ6272016 | ETHCE00301230SNG | Provide | 2023-12-14 | Closed
KRISSHOP @ SICC2 | ZFJ7294018 | CE00301230SNG | Provide | 2023-12-14 | Closed
KRISSHOP @ SICC2 | ZFJ6272007 | ELITE00203859SNG | Cease | 2024-04-30 | Open
KRISSHOP @ SICC2 | ZFJ7294007 | 00203859SNG | Cease | 2024-04-30 | Open
KRISSHOP @ SICC2 | ZFJ7294008 | 181478014 | Cease | 2024-04-30 | Open
KRISSHOP @ SICC2 |  |  | Cease
KRISSHOP @ SICC2 |  |  | Cease
Formulas:
Current CRD = [Current CRD, row above]

## SCOOT - T3
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [80 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [81 empty] | 2023-07-03 | 2023-07-06 | 2023-07-12 | 2023-08-09 | 2023-08-11 | 2023-08-14
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [63 empty] | SCOOT - T3 | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-02-06
|  | 2023-07-03 | NA | 2023-07-05 | 2023-07-06 | NA | 2023-07-10 | 2023-07-12 | NA | NA | NA | NA |  |  | 2023-03-24 | 2023-06-26 | [14 empty] | TIMELINES | [10 empty] | AIR REGISTER
SCOOT - T3 | Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric, with client owned links | COMPLETED | NA | COMPLETED | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA | NA | NEEDS ATTENTION | 2023-07-12 | AMENDMENT REQUIRED | NEEDS ATTENTION | AGGRESSIVE | 95.65% | [16 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[10 empty] | #N/A | [10 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Minimum SLA period | Maximum SLA Period | Minimum Lead time | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | SCOOT - T3 | Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric, with client owned links | 65 CHANGI AIRPORT TERMINAL 3. AIRPORT BOULEVARD. 819663 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide | ZEW2664037 ZEW2664038 | SDWP0003400072SNG SDWP0003400073SNG | 2023-06-28 | 0 | 32 | 2023-06-28 | 2023-08-11 |  |  |  | NA | 2023-07-12 | 2023-03-24 | 2023-06-20 | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[42 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [20 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[42 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | SCOOT - T3 | 2023-06-28 | 2023-07-12
[42 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[42 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [15 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [19 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [19 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [19 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [19 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | NA | [19 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [19 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [19 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | NA | [19 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | NA
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | NA
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | 2023-06-26 | [59 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 5 | Status |  | REFERENCE | Owner | [15 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA |  |  |  | NA | TD/TM | [15 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | NA | SDO/PARTNER | [15 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [16 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Confirmation |  |  |  | NA | CLIENT/PARTNER | [16 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[43 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [15 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 4 | 7 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 10 | 10 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [16 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 5 | 10 | [13 empty] | Instructions for Matching Order to DPE | COMPLETED |  |  | PC | [16 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 7 | 10 | [13 empty] | Instructions for CPE Order to ASE | COMPLETED |  |  | PC | [16 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 0 | 5 | 5 | 10 | 10 | [13 empty] | Handover email to Customer | COMPLETED |  |  | PE | [17 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 5 | 8 | [35 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 8 | 10 | [35 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 0 | 0 | 0 | 10 | 10 | [35 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 0 | 5 | 5 | 10 | 10 | [13 empty] | WBS | Status |  | Owner | Remarks | [56 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 0 | 5 | 5 | 10 | 10 | [13 empty] | Order Processing | [20 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [17 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [17 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [17 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [22 empty] | 2.5 |  | 0
|  |  | 4 |  |  |  | 4 | [10 empty] | 10 |  |  | HW released by Ingram |  |  | Ingram | [17 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 4 | 7 |  | 3 | 7 | 10 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 10 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 5 |  |  |  | 5 |  |  |  | 5 | [5 empty] | Site Survey
|  | 0 | 10 | 10 |  | E | 5 | 5 |  | I | 5 | 5 |  | J | 5 | 5 |  |  |  |  | Survey Schedule Confirmed
[6 empty] | 0 | 10 | 10 |  | 0 | 10 | 10 |  | 0 | 10 | 10 |  |  |  |  | Access Required
Access Documents submitted
|  |  | 5 |  |  |  | 0 |  |  |  | 0 | [9 empty] | Access Approved
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed
|  | 5 | 5 | 10 |  | 3 | 5 | 8 |  | 2 | 8 | 10 | [8 empty] | CE Routing
SLD Released
|  |  | 10 | [17 empty] | Patching Required
|  | H | 0 | 0 | [16 empty] | Patching Completed, if applicable
|  | 0 | 10 | 10 | [16 empty] | Routing Released
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | FALSE | 70 | TRUE | 84 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | FALSE | 70 | TRUE | 84 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | FALSE | 70 | TRUE | 84 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | 0 | 15 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 5 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 1.9149 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 95.65% | Pending Completion | 4.348%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 95.65%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 0
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0
|  | Work orders to be closed |  |  | 5 | Vairance | 3.6667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | TRUE | 84 | FALSE | 70
|  | Instructions for CPE Order to ASE | TRUE | 84 | FALSE | 70
|  | Handover email to Customer | TRUE | 84
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 34.7826 | 10.8696
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Documents submitted | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Approved | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Patching Completed, if applicable | TRUE | 84 | FALSE |  | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | FALSE | 70 | FALSE | 70 | 0 | 0
|  | CRD amended to Cease Date | FALSE | 70 | FALSE | 70 | 0 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | FALSE | 70 | TRUE | 84 | 0 | 2.5 | 12.5 | 7.5
|  | Schedule | TRUE | 84 |  |  | 2.5 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | TRUE | 84 |  |  | 2.5 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | TRUE | 84 |  |  | 2.5 | 0 | 10 | 0
|  | Handover email | TRUE | 84 |  |  | 2.5 | 0
|  | CRD amendment | TRUE | 84 |  |  | 2.5 | 0
|  | Work order closures | TRUE | 84 |  |  | 2.5 | 0
[6 empty] | Internal Dependencies | 45.6522
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 20
|  | Partially Completed |  |  |  | Post Provisioning | 10
|  | Fully Completed |  |  |  |  | 0.95652
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
96%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## TSQ
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-05-16 | NA | NA | NA | 2023-06-26 | 2023-06-27
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | TSQ | COMPLETED | NA | NA | NA | COMPLETED | COMPLETED | 2023-05-25
|  | 2023-05-16 | NA | 2023-05-18 | 2023-05-19 | NA | 2023-05-23 | 2023-05-25 | NA | NA | NA | NA |  |  | 2023-11-03 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
TSQ | SDWAN Connectivity setup at TSQ DC with C8500 Device | COMPLETED | NA | COMPLETED | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA | NA | NEEDS ATTENTION | 2023-05-25 |  |  |  | 81.3% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[10 empty] | #N/A | [10 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | TSQ | SDWAN Connectivity setup at TSQ DC with C8500 Device | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/ After Office Hours | Provide | ZEW2664034 | SDWP0003400069SNG | 2023-05-11 | 32 | 2023-06-26 |  |  | 2023-09-14 | NA | 2023-05-25 | 2023-11-03 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | TSQ | 2023-05-11 | 2023-05-25
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | NA
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | NA
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | NA | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | NA
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | NA | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | NA
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | NA
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 5 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA |  |  |  | NA | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | NA | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies | 2023-09-14 |  |  | COMPLETED | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Confirmation |  |  |  | NA | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 4 | 7 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 10 | 10 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 5 | 10 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 7 | 10 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 0 | 5 | 5 | 10 | 10 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | FALSE | 70 | TRUE | 84
|  | PO/SO to be issued | 3 | 5 | 8 | 5 | 8 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | FALSE | 70 | TRUE | 84
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 8 | 10 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | FALSE | 70 | TRUE | 84
|  | Cease Date Confirmation | 0 | 0 | 0 | 10 | 10 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 0 | 5 | 5 | 10 | 10 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 0 | 5 | 5 | 10 | 10 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 4 |  |  |  | 4 | [10 empty] | 10 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 4 | 7 |  | 3 | 7 | 10 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 10 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 5 |  |  |  | 5 |  |  |  | 5 | [5 empty] | Site Survey
|  | 0 | 10 | 10 |  | E | 5 | 5 |  | I | 5 | 5 |  | J | 5 | 5 |  |  |  |  | Survey Schedule Confirmed
[6 empty] | 0 | 10 | 10 |  | 0 | 10 | 10 |  | 0 | 10 | 10 |  |  |  |  | Access Required
Access Documents submitted
|  |  | 5 |  |  |  | 0 |  |  |  | 0 | [9 empty] | Access Approved
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed
|  | 5 | 5 | 10 |  | 3 | 5 | 8 |  | 2 | 8 | 10 | [8 empty] | CE Routing
SLD Released
|  |  | 10 | [17 empty] | Patching Required
|  | H | 0 | 0 | [16 empty] | Patching Completed, if applicable
|  | 0 | 10 | 10 | [16 empty] | Routing Released
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | FALSE | 70 | TRUE | 84 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | FALSE | 70 | TRUE | 84 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | FALSE | 70 | TRUE | 84 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | 5 | 10 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 5 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 1.9149 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 81.3% | Pending Completion | 18.7%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 81.3%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 0
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0
|  | Work orders to be closed |  |  | 5 | Vairance | 3.6667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 36.9565 | 4.3478
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | FALSE | 70 |  |  | 0 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Documents submitted | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Approved | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Patching Completed, if applicable | FALSE | 70 | TRUE |  | 0 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | FALSE | 70 | FALSE | 70 | 0 | 0
|  | CRD amended to Cease Date | FALSE | 70 | FALSE | 70 | 0 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | FALSE | 70 | TRUE | 84 | 0 | 2.5 | 12.5 | 7.5
|  | Schedule | TRUE | 84 |  |  | 2.5 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | TRUE | 84 |  |  | 2.5 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 41.3043
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 20
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.81304
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## DCE
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-08-04 | NA | NA | NA | 2023-09-14 | 2023-09-15
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | DCE DC | COMPLETED | NA | NA | NA | COMPLETED | COMPLETED | 2023-08-15
|  | 2023-08-04 | NA | 2023-08-08 | 2023-08-09 | NA | 2023-08-11 | 2023-08-15 | NA | NA | NA | NA |  |  | 2023-11-03 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
DCE DC | SDWAN Connectivity setup at TSQ DC with C8500 Device | COMPLETED | NA | COMPLETED | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA | NA | NEEDS ATTENTION | 2023-08-15 |  |  |  | 100% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[10 empty] | #N/A | [10 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | DCE DC | SDWAN Connectivity setup at TSQ DC with C8500 Device | 38A KIM CHUAN ROAD,537055 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/ After Offcie Hours | Provide | ZEW2664033 | SDWP0003400068SNG | 2023-08-01 | 32 | 2023-09-14 |  |  |  | NA | 2023-08-15 | 2023-11-03 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | DCE DC | 2023-08-01 | 2023-08-15
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | NA
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | NA
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | NA | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | NA
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | NA | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | NA
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | NA
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 5 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA |  |  |  | NA | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | NA | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders | 2023-11-10 |  |  | NA | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 4 | 7 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 10 | 10 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 5 | 10 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 7 | 10 | [13 empty] | Instructions for CPE Order to ASE | COMPLETED |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 0 | 5 | 5 | 10 | 10 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | FALSE | 70 | TRUE | 84
|  | PO/SO to be issued | 3 | 5 | 8 | 5 | 8 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | FALSE | 70 | TRUE | 84
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 8 | 10 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | FALSE | 70 | TRUE | 84
|  | Cease Date Confirmation | 0 | 0 | 0 | 10 | 10 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 0 | 5 | 5 | 10 | 10 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 0 | 5 | 5 | 10 | 10 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 4 |  |  |  | 4 | [10 empty] | 10 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 4 | 7 |  | 3 | 7 | 10 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 10 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 5 |  |  |  | 5 |  |  |  | 5 | [5 empty] | Site Survey
|  | 0 | 10 | 10 |  | E | 5 | 5 |  | I | 5 | 5 |  | J | 5 | 5 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 0 | 10 | 10 |  | 0 | 10 | 10 |  | 0 | 10 | 10 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 5 |  |  |  | 0 |  |  |  | 0 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 5 | 10 |  | 3 | 5 | 8 |  | 2 | 8 | 10 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 10 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 0 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 0 | 10 | 10 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | FALSE | 70 | TRUE | 84 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | FALSE | 70 | TRUE | 84 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | FALSE | 70 | TRUE | 84 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | 0 | 15 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 5 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 1.9149 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 100% | Pending Completion | 0%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 100%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 0
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0
|  | Work orders to be closed |  |  | 5 | Vairance | 3.6667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | TRUE | 84 | FALSE | 70
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 34.7826 | 15.2174
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Documents submitted | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Approved | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Patching Completed, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | CRD amended to Cease Date | FALSE | 70 | TRUE | 84 | 0 | 2.1739
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 20 | 0
|  | Schedule | TRUE | 84 |  |  | 2.5 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | GSP Booking, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Conference Bridge | TRUE | 84 |  |  | 2.5 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | TRUE | 84 |  |  | 2.5 | 0 | 10 | 0
|  | Handover email | TRUE | 84 |  |  | 2.5 | 0
|  | CRD amendment | TRUE | 84 |  |  | 2.5 | 0
|  | Work order closures | TRUE | 84 |  |  | 2.5 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 20
|  | Partially Completed |  |  |  | Post Provisioning | 10
|  | Fully Completed |  |  |  |  | 1
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
100%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## CHAI CHEE
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-09-25 | 2023-09-28 | 2023-10-04 | 2023-11-01 | 2023-11-03 | 2023-11-06
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | CHAI CHEE | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2023-10-17
|  | 2023-09-25 | NA | 2023-09-27 | 2023-09-28 | 2023-10-02 | 2023-10-02 | 2023-10-04 | 2023-10-02 | 2023-10-06 | 2023-10-10 | 2023-11-10 |  |  | 2023-09-11 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
CHAI CHEE | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2023-11-10 | NEEDS ATTENTION | 2023-10-17 | AMENDMENT REQUIRED |  | TO ARCHIVE | 100% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | CHAI CHEE | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 750B,WESTERN DIGITAL #04-05. CHAI CHEE ROAD. 469002 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664019 ZFJ2259005 ZFJ2460003 ZEW2664020 ZFJ2259006 ZFJ2460004 ZFJ2259004 ZFJ2321003 ZFJ2321004 | SDWP0003400054SNG ETHCE00296949SNG CE00296949SNG SDWP0003400055SNG ETHCE00296953SNG CE00296953SNG ELITE00171059SNG 00171059SNG 181426421 | 2023-09-20 | 32 | 2023-11-03 | 2023-09-11 | 2023-09-20 |  | 2023-11-10 | 2023-10-17 | 2023-09-11 |  | 1 | Cease work orders for Singnet E and V edgem devices need to be raised |  | Risk | Links cannot be brought up because of svc# tie not with Provide orders. | AM | High | Medium | Severe | [17 empty] | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 | [26 empty] | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 | [26 empty] | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 | [26 empty] | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | CHAI CHEE | 2023-09-20 | 2023-10-17
[40 empty] | 5 | [26 empty] | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED |  |  | Cease work orders for Singnet E links need to be raised. | [14 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed |  |  |  | TO ARCHIVE | [54 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-09-20 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 1 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner | 2023-09-11 |  |  | CONFIRMED | SDO/PARTNER | [13 empty] | Probability | Very High | [38 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High |  |  | 1 | [35 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders | 2023-11-10 |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium | [38 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | COMPLETED |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | COMPLETED |  |  | PC | [14 empty] | Probability | Very High | [38 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High | [38 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium | [38 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low | [38 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 1 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 0.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 0.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC | 2023-09-21
|  | Work orders to be closed | TRUE | 84 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | 10 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 100% | Pending Completion | 0%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 100%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | TRUE | 84 | FALSE | 70
|  | Instructions for CPE Order to ASE | TRUE | 84 | FALSE | 70
|  | Handover email to Customer | TRUE | 84
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 39.1304 | 10.8696
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | FALSE | 70 | TRUE | 84 | 0 | 2.1739
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Documents submitted | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Approved | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 15 | 5
|  | Schedule | TRUE | 84 |  |  | 2.5 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | TRUE | 84 |  |  | 2.5 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | TRUE | 84 |  |  | 2.5 | 0 | 10 | 0
|  | Handover email | TRUE | 84 |  |  | 2.5 | 0
|  | CRD amendment | TRUE | 84 |  |  | 2.5 | 0
|  | Work order closures | TRUE | 84 |  |  | 2.5 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 20
|  | Partially Completed |  |  |  | Post Provisioning | 10
|  | Fully Completed |  |  |  |  | 1
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed
100%

## ION
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-11-30 | 2023-12-05 | 2023-12-11 | 2024-01-08 | 2024-01-10 | 2024-01-29
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | ION | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | WIP | 2023-12-22
|  | 2023-11-30 | NA | 2023-12-04 | 2023-12-05 | 2023-12-07 | 2023-12-07 | 2023-12-11 | 2023-12-07 | 2023-12-13 | 2023-12-15 |  |  |  | 2023-09-25 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
ION | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2023-12-22 | AMENDMENT REQUIRED |  |  | 75% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | ION | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 2 ION ORCHARD #04-03C ORCHARD TURN 238801 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/ After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664001 ZEV9644003 ZFJ0973002 ZEW2664002 ZEV9644004 ZFJ0973001 ZEV9644005 ZEV9748001 ZEV9748002 | SDWP0003400036SNG ETHCE00296864SNG CE00296864SNG SDWP0003400037SNG ETHCE00296862SNG CE00296862SNG ELITE00169960SNG 00169960SNG 181426229 | 2023-11-27 | 32 | 2024-01-10 |  | 2023-11-27 |  |  | 2023-12-22 | 2023-09-25 |  | 1 | CE00296862SNG - order raised incorrectly for bandwidth as 10M, instead of 100M. | 2023-09-25 | Risk | configuration cannot be completed | SDE | High | High | Critical | 2023-09-29 | Follow up withorder raising team for rectifiation | Aileen/Kapu |  | Delay will postpone link provisioning | [12 empty] | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 | [26 empty] | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 | [26 empty] | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 | [26 empty] | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | ION | 2023-11-27 | 2023-12-22
[40 empty] | 5 | [26 empty] | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | 2024-01-29
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-09-28 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-11-27 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 1 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  |  | SDO/PARTNER | [13 empty] | Probability | Very High | [38 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High |  |  |  | 1 | [34 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium | [38 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 45
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | COMPLETED |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | COMPLETED |  |  | PC | [14 empty] | Probability | Very High | [38 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High | [38 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium | [38 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low | [38 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | FALSE | 70 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 1 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 0.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 0.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | 5 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 75% | Pending Completion | 25%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 75%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | TRUE | 84 | FALSE | 70
|  | Instructions for CPE Order to ASE | TRUE | 84 | FALSE | 70
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 41.3043 | 8.6957
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Documents submitted | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Approved | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 5 | 5
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | TD/TM & FE details, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 15
|  | WIP |  |  |  | Provisioning Check List | 10
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.75
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
75%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## SMC - SIAEC
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-10-20 | NA | 2023-10-31 | 2023-11-28 | 2023-11-30 | 2023-12-01
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | SMC- SIAEC | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2023-11-30
|  | 2023-10-20 | NA | 2023-10-24 | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-31 | NA | 2023-11-02 | 2023-11-06 |  |  |  | 2023-10-31 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
SMC- SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to integrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NA | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2023-11-30 | AMENDMENT REQUIRED |  |  | 97.83% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | SMC- SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to integrate SIA network to SDWAN fabric | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499614 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/ After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664011 ZEV9644018 ZFJ0973009 ZEW2664012 ZEV9644019 ZFJ0973010 ZEV9644017 ZEV9748013 ZEV9748014 | SDWP0003400046SNG ETHCE00296947SNG CE00296947SNG SDWP0003400047SNG ETHCE00296951SNG CE00296951SNG ELITE00171030SNG 00171030SNG 181426370 | 2023-10-17 | 32 | 2023-11-30 |  | 2023-10-17 |  |  | 2023-11-30 | 2023-10-31 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | SMC- SIAEC | 2023-10-17 | 2023-11-30
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | NA
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | NA | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-10-17 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | NA | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | NA | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | FALSE | 70 | TRUE | 84
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 0 | 0 | 0 | 14 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 14 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 0 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 0 | 14 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | 5 | 10 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.5166 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 97.83% | Pending Completion | 2.174%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 97.83%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 6.3333
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 39.1304 | 8.6957
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | FALSE | 70 |  |  | 0 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Documents submitted | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Approved | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 15 | 5
|  | Schedule | TRUE | 84 |  |  | 2.5 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | TRUE | 84 |  |  | 2.5 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | TRUE | 84 |  |  | 2.5 | 0 | 10 | 0
|  | Handover email | TRUE | 84 |  |  | 2.5 | 0
|  | CRD amendment | TRUE | 84 |  |  | 2.5 | 0
|  | Work order closures | TRUE | 84 |  |  | 2.5 | 0
[6 empty] | Internal Dependencies | 47.8261
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 20
|  | Partially Completed |  |  |  | Post Provisioning | 10
|  | Fully Completed |  |  |  |  | 0.97826
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
98%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## ALH Guard
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-12-04 | NA | 2023-12-13 | 2024-01-10 | 2024-01-12 | 2024-02-12
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | ALH GUARD | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-01-12
|  | 2023-12-04 | NA | 2023-12-06 | 2023-12-07 | 2023-12-11 | 2023-12-11 | 2023-12-13 | 2023-12-11 | 2023-12-15 | 2023-12-19 |  |  |  | 2023-10-16 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
ALH GUARD | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-12 | AMENDMENT REQUIRED |  |  | 90.65% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | ALH GUARD | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 4 AIRLINE HOUSE GUARDHOUSE AIRLINE ROAD 819825 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/ After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664021 ZFJ2259009 ZFJ2460005 ZEW2664022 ZFJ2259010 ZFJ2460006 ZFJ2259008 ZFJ2321005 ZFJ2321006 | SDWP0003400056SNG ETHCE00296962SNG CE00296962SNG SDWP0003400057SNG ETHCE00296963SNG CE00296963SNG ELITE00171056SNG 00171056SNG 181426414 | 2023-11-29 | 32 | 2024-01-12 |  | 2023-11-29 | 2023-12-05 |  | 2024-01-12 | 2023-10-16 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | ALH GUARD | 2023-11-29 | 2024-01-12
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | NA
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-11-29 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | NA | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies | 2023-12-05 |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 53
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | FALSE | 70 | TRUE | 84
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | 10 | 10 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | TRUE | 84 | TRUE | 84 | 5 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 90.65% | Pending Completion | 9.348%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 90.65%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 32.6087 | 13.0435
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | FALSE | 70 | TRUE | 84 | 0 | 2.1739
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Documents submitted | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Approved | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | FALSE | 70 | FALSE | 70 | 0 | 0
|  | CRD amended to Cease Date | FALSE | 70 | FALSE | 70 | 0 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 15 | 5
|  | Schedule | TRUE | 84 |  |  | 2.5 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | TRUE | 84 |  |  | 2.5 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 45.6522
|  | Completion Status |  |  |  | Risk Analysis | 25
|  | WIP |  |  |  | Provisioning Check List | 20
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.90652
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed
91%

## DATAPOST
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2024-01-12 | 2024-01-24 | 2024-01-31 | 2024-02-14 | 2024-03-15 | 2024-03-18
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | DATAPOST | COMPLETED | COMPLETED | WIP | WIP | TO BE SCHEDULED | TO BE SCHEDULED | 2024-02-05
|  | 2023-12-26 | NA | 2023-12-28 | 2023-12-29 | NA | 2024-01-02 | 2024-01-04 | NA | NA | NA |  |  |  | 2024-02-20 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
DATAPOST | Provisioning of Singnet Ethernet Links with client provided deiverse link and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | RISK | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA |  | NEEDS ATTENTION | 2024-02-05 |  |  |  | 41.09% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[10 empty] | #N/A | [10 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | DATAPOST | Provisioning of Singnet Ethernet Links with client provided deiverse link and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 4,AYER RAJAH CRESCENT. #03-00. 139960 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/ After Office Hours | Provide Provide | ZEW2664023 ZEW2664024 | SDWP0003400058SNG SDWP0003400059SNG | 2023-12-21 | 32 | 2024-02-05 |  | 2023-12-21 |  |  | 2024-02-05 | 2024-02-20 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | DATAPOST | 2024-01-03 | 2024-02-05
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed |  | ZEW2664023 | Provide | SDWP0003400058SNG | [9 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [6 empty] | Provide | [10 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [6 empty] | Provide | [10 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | 2023-12-28 | [6 empty] | Cease | ELITE00171062SNG | [9 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [6 empty] | Cease | [10 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | 2024-01-31
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | NA | [6 empty] | Cease | [10 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | 2024-02-14
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [5 empty] | ZEW2664024 | Provide | SDWP0003400059SNG | [9 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | 2024-03-15
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [6 empty] | Cease | [10 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | 2024-03-18
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | NA | [6 empty] | Cease | [10 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | NA
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | NA
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 5 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-12-21 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 7
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  |  | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 15
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 20
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | NA | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 52
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 53
|  | IKOM | 3 | 0 | 3 | 4 | 7 | [13 empty] | Kick off Email to Client | 2023-12-22 |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 10 | 10 | [13 empty] | Instructions for Internal Orders to ASE | 2023-12-22 |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 5 | 10 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 7 | 10 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 0 | 5 | 5 | 10 | 10 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 5 | 8 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | FALSE | 70 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 8 | 10 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | FALSE | 70 | FALSE | 70
|  | Cease Date Confirmation | 0 | 0 | 0 | 10 | 10 | [33 empty] | Very Low | [38 empty] | HW Installation | FALSE | 70 | FALSE | 70
|  | Site Survey Completion | 0 | 5 | 5 | 10 | 10 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | FALSE | 70 | FALSE | 70
|  | CE Routing | 0 | 5 | 5 | 10 | 10 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 4 |  |  |  | 4 | [10 empty] | 10 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 4 | 7 |  | 3 | 7 | 10 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 10 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 5 |  |  |  | 5 |  |  |  | 5 | [5 empty] | Site Survey
|  | 0 | 10 | 10 |  | E | 5 | 5 |  | I | 5 | 5 |  | J | 5 | 5 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 0 | 10 | 10 |  | 0 | 10 | 10 |  | 0 | 10 | 10 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 5 |  |  |  | 0 |  |  |  | 0 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 5 | 10 |  | 3 | 5 | 8 |  | 2 | 8 | 10 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 10 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 0 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 0 | 10 | 10 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | FALSE | 70 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | FALSE | 70 | TRUE | 84 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | FALSE | 70 | TRUE | 84 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | FALSE | 70 | TRUE | 84 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | 5 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 5 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 1.9149 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 41.09% | Pending Completion | 58.91%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 41.09%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 0
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0
|  | Work orders to be closed |  |  | 5 | Vairance | 3.6667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | FALSE | 70
|  | Instrcutions for Internal Orders to ASE | FALSE | 70
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 21.7391 | 4.3478
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | FALSE | 70 |  |  | 0 | 0
HW Readiness
|  | Survey Schedule Confirmed | FALSE | 70 |  |  | 0 | 0
|  | Access Required | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Access Documents submitted | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Access Approved | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Site Survey Completed | FALSE | 70 |  |  | 0 | 0
CE Routing
|  | SLD Released | FALSE | 70 |  |  | 0 | 0
|  | Patching Required | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Patching Completed, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Routing Released | FALSE | 70 |  |  | 0 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | FALSE | 70 | FALSE | 70 | 0 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | FALSE | 70 | FALSE | 70 | 0 | 0 | 0 | 0
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | TD/TM & FE details, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Site POC | FALSE | 70 |  |  | 0 | 0
|  | TAC booking, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | GSP Booking, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 26.087
|  | Completion Status |  |  |  | Risk Analysis | 15
|  | WIP |  |  |  | Provisioning Check List | 0
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.41087
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
41%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## Mentor Media
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2024-01-12 | 2024-01-24 | 2024-01-31 | 2024-02-14 | 2024-03-15 | 2024-03-18
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | Mentor Media | COMPLETED | COMPLETED | WIP | WIP | TO BE SCHEDULED | TO BE SCHEDULED | 2024-02-12
|  | 2024-01-02 | NA | 2024-01-04 | 2024-01-05 | NA | 2024-01-09 | 2024-01-11 | NA | NA | NA |  |  |  | 2024-02-23 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
Mentor Media | Provisioning of Singnet Ethernet Links with client provided deiverse link and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | RISK | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA |  | NEEDS ATTENTION | 2024-02-12 |  |  |  | 43.26% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[10 empty] | #N/A | [10 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | Mentor Media | Provisioning of Singnet Ethernet Links with client provided deiverse link and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 47,JALAN BUROH. #01-02. 619491 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/ After Office Hours | Provide Provide | ZEW2664025 ZEW2664026 | SDWP0003400060SNG SDWP0003400061SNG | 2023-12-28 | 32 | 2024-02-12 |  | 2023-12-28 |  |  | 2024-02-12 | 2024-02-23 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | Mentor Media | 2024-01-03 | 2024-02-12
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | 2024-01-04 | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | 2024-01-31
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | NA | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | 2024-02-14
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | 2024-03-15
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | 2024-03-18
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | NA | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | NA
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | NA
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 5 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-12-28 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 7
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  |  | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 15
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 20
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | NA | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 52
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 53
|  | IKOM | 3 | 0 | 3 | 4 | 7 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 10 | 10 | [13 empty] | Instructions for Internal Orders to ASE | 2023-12-29 |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 5 | 10 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 7 | 10 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 0 | 5 | 5 | 10 | 10 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 5 | 8 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | FALSE | 70 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 8 | 10 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | FALSE | 70 | FALSE | 70
|  | Cease Date Confirmation | 0 | 0 | 0 | 10 | 10 | [33 empty] | Very Low | [38 empty] | HW Installation | FALSE | 70 | FALSE | 70
|  | Site Survey Completion | 0 | 5 | 5 | 10 | 10 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | FALSE | 70 | FALSE | 70
|  | CE Routing | 0 | 5 | 5 | 10 | 10 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 4 |  |  |  | 4 | [10 empty] | 10 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 4 | 7 |  | 3 | 7 | 10 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 10 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 5 |  |  |  | 5 |  |  |  | 5 | [5 empty] | Site Survey
|  | 0 | 10 | 10 |  | E | 5 | 5 |  | I | 5 | 5 |  | J | 5 | 5 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 0 | 10 | 10 |  | 0 | 10 | 10 |  | 0 | 10 | 10 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 5 |  |  |  | 0 |  |  |  | 0 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 5 | 10 |  | 3 | 5 | 8 |  | 2 | 8 | 10 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 10 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 0 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 0 | 10 | 10 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | FALSE | 70 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | FALSE | 70 | TRUE | 84 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | FALSE | 70 | TRUE | 84 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | FALSE | 70 | TRUE | 84 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | 5 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 5 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 1.9149 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 43.26% | Pending Completion | 56.74%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 43.26%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 0
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0
|  | Work orders to be closed |  |  | 5 | Vairance | 3.6667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | FALSE | 70
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 26.087 | 2.1739
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | FALSE | 70 | FALSE | 70 | 0 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | FALSE | 70 |  |  | 0 | 0
|  | Access Required | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Access Documents submitted | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Access Approved | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Site Survey Completed | FALSE | 70 |  |  | 0 | 0
CE Routing
|  | SLD Released | FALSE | 70 |  |  | 0 | 0
|  | Patching Required | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Patching Completed, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Routing Released | FALSE | 70 |  |  | 0 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | FALSE | 70 | FALSE | 70 | 0 | 0 | 0 | 0
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | TD/TM & FE details, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Site POC | FALSE | 70 |  |  | 0 | 0
|  | TAC booking, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | GSP Booking, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 28.2609
|  | Completion Status |  |  |  | Risk Analysis | 15
|  | WIP |  |  |  | Provisioning Check List | 0
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.43261
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
43%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## Scoot T1
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2024-01-09 | NA | NA | NA | 2024-02-19 | 2024-02-20
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | Scoot T1 | COMPLETED | NA | NA | NA | COMPLETED | COMPLETED | 2024-02-19
|  | 2024-01-09 | NA | 2024-01-11 | 2024-01-12 | NA | 2024-01-16 | 2024-01-18 | NA | NA | NA |  |  |  | 2023-04-05 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
Scoot T1 | Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric, with client owned links | COMPLETED | NA | COMPLETED | COMPLETED | NA | COMPLETED | COMPLETED | NA | NA | NA |  | NEEDS ATTENTION | 2024-02-19 | AMENDMENT REQUIRED |  |  | 80% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[10 empty] | #N/A | [10 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | Scoot T1 | Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric, with client owned links | 80 CHANGI AIRPORT T1 #04-15 AIRPORT BOULEVARD 819642 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/ After Office Hours | Provide Provide | ZEW2664035 ZEW2664036 | SDWP0003400070SNG SDWP0003400071SNG | 2024-01-04 | 32 | 2024-02-19 |  | 2024-01-04 |  |  | 2024-02-19 | 2023-04-05 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | Scoot T1 | 2024-01-04 | 2024-02-19
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | NA
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | NA
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | NA | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | NA
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | NA | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | NA
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | NA
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 5 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2024-01-04 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  |  | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | NA | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 4 | 7 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 10 | 10 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 5 | 10 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 7 | 10 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 0 | 5 | 5 | 10 | 10 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | FALSE | 70 | TRUE | 84
|  | PO/SO to be issued | 3 | 5 | 8 | 5 | 8 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | FALSE | 70 | TRUE | 84
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 8 | 10 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | FALSE | 70 | TRUE | 84
|  | Cease Date Confirmation | 0 | 0 | 0 | 10 | 10 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 0 | 5 | 5 | 10 | 10 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 0 | 5 | 5 | 10 | 10 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 4 |  |  |  | 4 | [10 empty] | 10 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 4 | 7 |  | 3 | 7 | 10 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 10 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 5 |  |  |  | 5 |  |  |  | 5 | [5 empty] | Site Survey
|  | 0 | 10 | 10 |  | E | 5 | 5 |  | I | 5 | 5 |  | J | 5 | 5 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 0 | 10 | 10 |  | 0 | 10 | 10 |  | 0 | 10 | 10 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 5 |  |  |  | 0 |  |  |  | 0 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 5 | 10 |  | 3 | 5 | 8 |  | 2 | 8 | 10 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 10 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 0 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 0 | 10 | 10 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | FALSE | 70 | TRUE | 84 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | FALSE | 70 | TRUE | 84 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | FALSE | 70 | TRUE | 84 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | 5 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 5 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 1.9149 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 80% | Pending Completion | 20%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 80%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 0
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0
|  | Work orders to be closed |  |  | 5 | Vairance | 3.6667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 32.6087 | 17.3913
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Documents submitted | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Approved | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Patching Completed, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | CRD amended to Cease Date | FALSE | 70 | TRUE | 84 | 0 | 2.1739
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | FALSE | 70 | TRUE | 84 | 0 | 2.5 | 7.5 | 7.5
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 15
|  | WIP |  |  |  | Provisioning Check List | 15
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.8
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
80%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## PTB4 - SIAEC
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2024-01-16 | NA | 2024-01-25 | 2024-02-22 | 2024-02-26 | 2024-02-27
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | PTB4 - SIAEC | COMPLETED | NA | COMPLETED | WIP | WIP | TO BE SCHEDULED | 2024-02-26
|  | 2024-01-16 | NA | 2024-01-18 | 2024-01-19 | 2024-01-23 | 2024-01-23 | 2024-01-25 | 2024-01-23 | 2024-01-29 | 2024-01-31 |  |  |  | 2024-01-09 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
PTB4 - SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | RISK | RISK |  | NEEDS ATTENTION | 2024-02-26 | AMENDMENT REQUIRED |  |  | 72.5% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | PTB4 - SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 10 AIRPORT BOULEVARD #01-44. CHANGI AIRPORT TERMINAL 4 819665 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/ After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664009 ZFJ6272017 ZFJ7294019 ZEW2664010 ZFJ6272018 ZFJ7294020 ZFJ6272008 ZFJ7294009 ZFJ7294010 | SDWP0003400044SNG ETHCE00296981SNG CE00296981SNG SDWP0003400045SNG ETHCE00296982SNG CE00297030SNG ELITE00171034SNG 00171034SNG 181426387 | 2024-01-11 | 32 | 2024-02-26 |  | 2024-01-11 |  |  | 2024-02-26 | 2024-01-09 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | PTB4 - SIAEC | 2024-01-11 | 2024-02-26
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | NA
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | 2024-02-22
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | 2024-02-26
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | 2024-02-27
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | 2024-01-29
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | 2024-01-31
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2024-01-11 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  |  | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  |  | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | FALSE | 70 | TRUE | 84
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | FALSE | 70 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | FALSE | 70 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | FALSE | 70 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | FALSE | 70 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | FALSE | 70 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | 5 | 0 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 72.5% | Pending Completion | 27.5%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 72.5%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 32.6087 | 17.3913
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | FALSE | 70 | TRUE | 84 | 0 | 2.1739
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Documents submitted | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Approved | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Patching Completed, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | FALSE | 70 | FALSE | 70 | 0 | 0 | 7.5 | 5
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 10
|  | WIP |  |  |  | Provisioning Check List | 12.5
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.725
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
73%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## KRISSHOP @ CHANGI
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2024-01-23 | 2024-01-26 | 2024-02-01 | 2024-02-29 | 2024-03-04 | 2024-03-05
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | Krisshop @ Changi | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-03-04
|  | 2024-01-23 | NA | 2024-01-25 | 2024-01-26 | 2024-01-30 | 2024-01-30 | 2024-02-01 | 2024-01-30 | 2024-02-05 | 2024-02-07 |  |  |  | 2023-12-01 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
Krisshop @ Changi | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | RISK | RISK |  | NEEDS ATTENTION | 2024-03-04 | AMENDMENT REQUIRED |  |  | 80% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | Krisshop @ Changi | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | #03-02 CHANGI SOUTH LANE 486045 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664027 ZFJ6272013 ZFJ7294015 ZEW2664028 ZFJ6272014 ZFJ7294016 ZFJ6272005 ZFJ7294005 ZFJ7294006 | SDWP0003400062SNG ETHCE00296976SNG CE00296976SNG SDWP0003400063SNG ETHCE00296977SNG CE00296977SNG ELITE00176685SNG 00176685SNG 181503918 | 2024-01-18 | 32 | 2024-03-04 | 0 | 2024-01-18 |  |  | 2024-03-04 | 2023-12-01 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | Krisshop @ Changi | 2024-01-18 | 2024-03-04
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED |  |  | Survey scheduled on 13-Oct-23 | [14 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | 2024-02-05
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | 2024-02-07
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2024-01-18 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | CONFIRMED | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | FALSE | 70 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | FALSE | 70 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | 10 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 80% | Pending Completion | 20%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 80%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 39.1304 | 10.8696
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Documents submitted | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Approved | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 5 | 5
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | Site POC | FALSE | 70 |  |  | 0 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 10
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.8
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
80%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## SICC1
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2024-01-30 | 2024-02-02 | 2024-02-08 | 2024-03-07 | 2024-03-11 | 2024-03-12
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | SICC1 | COMPLETED | COMPLETED | COMPLETED | COMPLETED | TO BE SCHEDULED | TO BE SCHEDULED | 2024-03-11
|  | 2024-01-30 | NA | 2024-02-01 | 2024-02-02 | 2024-02-06 | 2024-02-06 | 2024-02-08 | 2024-02-06 | 2024-02-12 | 2024-02-14 |  |  |  | 2023-11-30 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
SICC1 | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-03-11 | AMENDMENT REQUIRED |  |  | 71.3% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | SICC1 | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664007 ZEV9644015 ZFJ0973007 ZEW2664008 ZEV9644016 ZFJ0973008 ZEV9644014 ZEV9748011 ZEV9748012 | SDWP0003400042SNG ETHCE00296939SNG CE00296939SNG SDWP0003400043SNG ETHCE00296940SNG CE00296940SNG ELITE00171027SNG 00171027SNG 181426363 | 2024-01-25 | 32 | 2024-03-11 | 0 | 2024-01-25 |  |  | 2024-03-11 | 2023-11-30 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | SICC1 | 2024-01-25 | 2024-03-11
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | 2024-03-11
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | 2024-03-12
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2024-01-25 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | CONFIRMED | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  |  | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | FALSE | 70 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | FALSE | 70 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | 10 | 0 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 71.3% | Pending Completion | 28.7%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 71.3%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 39.1304 | 2.1739
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | FALSE | 70 |  |  | 0 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | FALSE | 70 |  |  | 0 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Documents submitted | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Approved | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | FALSE | 70 | FALSE | 70 | 0 | 0
|  | CRD amended to Cease Date | FALSE | 70 | FALSE | 70 | 0 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 10 | 5
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 41.3043
|  | Completion Status |  |  |  | Risk Analysis | 15
|  | WIP |  |  |  | Provisioning Check List | 15
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.71304
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
71%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## EC Engine
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2024-02-06 | 2024-02-09 | 2024-02-15 | 2024-03-14 | 2024-03-18 | 2024-03-19
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | EC Engine | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-03-18
|  | 2024-02-06 | NA | 2024-02-08 | 2024-02-09 | 2024-02-13 | 2024-02-13 | 2024-02-15 | 2024-02-13 | 2024-02-19 | 2024-02-21 |  |  |  | 2023-12-12 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
EC Engine | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-03-18 | AMENDMENT REQUIRED |  |  | 97.5% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | EC Engine | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 300, LOYANG AVENUE 509071 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664015 ZFJ6272011 ZFJ7294013 ZEW2664016 ZFJ6272012 ZFJ7294014 ZFJ6272001 ZFJ7294003 ZFJ7294004 | SDWP0003400050SNG ETHCE00296968SNG CE00296968SNG SDWP0003400051SNG ETHCE00296973SNG CE00296973SNG ELITE00171018SNG 00171018SNG 181426349 | 2024-02-01 | 32 | 2024-03-18 | 2023-11-30 | 2024-02-01 |  |  | 2024-03-18 | 2023-12-12 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | EC Engine | 2024-02-01 | 2024-03-18
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2024-02-01 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner | 2023-11-30 |  |  | CONFIRMED | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | 10 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 97.5% | Pending Completion | 2.5%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 97.5%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 41.3043 | 8.6957
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Documents submitted | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Access Approved | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 15 | 5
|  | Schedule | TRUE | 84 |  |  | 2.5 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | TRUE | 84 |  |  | 2.5 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | TRUE | 84 |  |  | 2.5 | 0 | 7.5 | 0
|  | Handover email | TRUE | 84 |  |  | 2.5 | 0
|  | CRD amendment | TRUE | 84 |  |  | 2.5 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 20
|  | Partially Completed |  |  |  | Post Provisioning | 7.5
|  | Fully Completed |  |  |  |  | 0.975
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
98%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## KRISSHOP @ SIGNATURE
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-11-24 | 2023-11-29 | 2023-12-05 | 2024-01-02 | 2024-01-04 | 2024-01-05
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | KRISSHOP @ SIGNATURE | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-01-04
|  | 2023-11-24 | NA | 2023-11-28 | 2023-11-29 | 2023-12-01 | 2023-12-01 | 2023-12-05 | 2023-12-01 | 2023-12-07 | 2023-12-11 |  |  |  | 2023-11-30 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
KRISSHOP @ SIGNATURE | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-04 | AMENDMENT REQUIRED |  |  | 97.5% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | KRISSHOP @ SIGNATURE | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | THE SIGNATURE #08-06/07 CHANGI BUSINESS PARK CENTRAL 2 486066 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664029 ZFJ2259012 ZFJ2460007 ZEW2664030 ZFJ2259013 ZFJ2460008 ZFJ2259011 ZFJ2321007 ZFJ2321008 | SDWP0003400064SNG ETHCE00297027SNG CE00297027SNG SDWP0003400065SNG ETHCE00297028SNG CE00297028SNG ELITE00176684SNG 00176684SNG 181437009 | 2023-11-21 | 32 | 2024-01-04 |  | 2023-11-21 |  |  | 2024-01-04 | 2023-11-30 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | KRISSHOP @ SIGNATURE | 2023-11-21 | 2024-01-04
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-11-21 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | NA | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | 2023-11-22 |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | 2023-11-22 |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | 2023-11-22 |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | 2023-11-22 |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | 5 | 10 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 97.5% | Pending Completion | 2.5%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 97.5%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | FALSE | 70
|  | Instrcutions for Internal Orders to ASE | FALSE | 70
|  | Instructions for Matching Order to ASE | FALSE | 70 | FALSE | 70
|  | Instructions for CPE Order to ASE | FALSE | 70 | FALSE | 70
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 47.8261 | 2.1739
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | FALSE | 70 | TRUE | 84 | 0 | 2.1739
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Documents submitted | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Approved | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 15 | 5
|  | Schedule | TRUE | 84 |  |  | 2.5 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | TRUE | 84 |  |  | 2.5 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | TRUE | 84 |  |  | 2.5 | 0 | 7.5 | 0
|  | Handover email | TRUE | 84 |  |  | 2.5 | 0
|  | CRD amendment | TRUE | 84 |  |  | 2.5 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 20
|  | Partially Completed |  |  |  | Post Provisioning | 7.5
|  | Fully Completed |  |  |  |  | 0.975
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
98%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## LOYANG - SSC
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-12-19 | 2023-12-22 | 2023-12-28 | 2024-01-25 | 2024-02-26 | 2024-02-27
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | LOYANG - SSC | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-01-29
|  | 2023-12-19 | NA | 2023-12-21 | 2023-12-22 | 2023-12-26 | 2023-12-26 | 2023-12-28 | 2023-12-26 | 2024-01-01 | 2024-01-03 |  |  |  | 2023-11-09 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
LOYANG - SSC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-29 | AMENDMENT REQUIRED |  |  | 85% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | LOYANG - SSC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 60,SIA SUPPLIES CENTRE, LOYANG WAY, 508751 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664005 ZEV9644011 ZFJ0973005 ZEW2664006 ZEV9644012 ZFJ0973006 ZEV9644010 ZEV9748009 ZEV9748010 | SDWP0003400040SNG ETHCE00296927SNG CE00296927SNG SDWP0003400041SNG ETHCE00296928SNG CE00296928SNG ELITE00171012SNG 00171012SNG 181426325 | 2023-12-14 | 32 | 2024-01-29 | 0 | 2023-12-14 |  |  | 2024-01-29 | 2023-11-09 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | LOYANG - SSC | 2023-12-14 | 2024-01-29
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed |  |  | Provide | [10 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [6 empty] | Provide | [10 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [6 empty] | Provide | [10 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [6 empty] | Cease | [10 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [6 empty] | Cease | [10 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [6 empty] | Provide | [10 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [6 empty] | Provide | [10 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [6 empty] | Provide | [10 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [6 empty] | Cease | [10 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED | [6 empty] | Cease
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED | [6 empty] | Cease
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [7 empty] | Cease | [50 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner |  | ZEV9748010 | Cease | [10 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-12-14 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | CONFIRMED | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 52
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 53
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | 10 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 85% | Pending Completion | 15%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 85%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 45.6522 | 4.3478
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | FALSE | 70 | TRUE | 84 | 0 | 2.1739
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Documents submitted | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Approved | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 10 | 5
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 15
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.85
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
85%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## ALPS - SIAEC
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-12-19 | 2023-12-22 | 2023-12-28 | 2024-01-25 | 2024-02-26 | 2024-02-27
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | ALPS - SIAEC | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-01-29
|  | 2023-12-19 | NA | 2023-12-21 | 2023-12-22 | 2023-12-26 | 2023-12-26 | 2023-12-28 | 2023-12-26 | 2024-01-01 | 2024-01-03 |  |  |  | 2023-12-21 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
ALPS - SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-29 | AMENDMENT REQUIRED |  |  | 80% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | ALPS - SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508988 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664013 ZFJ6272009 ZFJ7294011 ZEW2664014 ZFJ6272010 ZFJ7294012 ZFJ6272002 ZFJ7294001 ZFJ7294002 | SDWP0003400048SNG ETHCE00296946SNG CE00296946SNG SDWP0003400049SNG ETHCE00296964SNG CE00296964SNG ELITE00182102SNG 00182102SNG 181443618 | 2023-12-14 | 32 | 2024-01-29 | 0 | 2023-12-14 |  |  | 2024-01-29 | 2023-12-21 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | ALPS - SIAEC | 2023-12-14 | 2024-01-29
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-12-14 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | CONFIRMED | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  |  | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 52
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 53
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | 10 | 0 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | FALSE | 70 | 0 | 0 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 80% | Pending Completion | 20%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 80%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 50 | 0
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Documents submitted | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Approved | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 10 | 5
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 15
|  | WIP |  |  |  | Provisioning Check List | 15
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.8
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
80%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## ESD CHANGI - SIAEC
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-12-08 | 2023-12-13 | 2023-12-19 | 2024-01-16 | 2024-01-18 | 2024-01-19
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | ESD CHANGI - SIAEC | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2024-01-18
|  | 2023-12-08 | NA | 2023-12-12 | 2023-12-13 | 2023-12-15 | 2023-12-15 | 2023-12-19 | 2023-12-15 | 2023-12-21 | 2023-12-25 |  |  |  | 2023-11-23 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
ESD CHANGI - SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-18 | AMENDMENT REQUIRED |  |  | 78.15% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | ESD CHANGI - SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 36,SATS MAINTENANCE CENTRE, CHANGI NORTH CRESCENT, 499620 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664003 ZEV9644008 ZFJ0973003 ZEW2664004 ZEV9644009 ZFJ0973004 ZEV9644007 ZEV9748007 ZEV9748008 | SDWP0003400038SNG ETHCE00296909SNG CE00296909SNG SDWP0003400039SNG ETHCE00296914SNG CE00296914SNG ELITE00171052SNG 00171052SNG 181513018 | 2023-12-05 | 32 | 2024-01-18 | 0 | 2023-12-05 |  |  | 2024-01-18 | 2023-11-23 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | ESD CHANGI - SIAEC | 2023-12-05 | 2024-01-18
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | COMPLETED
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | COMPLETED
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-12-05 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | CONFIRMED | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | TRUE | 84 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | TRUE | 84 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | 10 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 78.15% | Pending Completion | 21.85%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 78.15%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 43.4783 | 2.1739
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Documents submitted | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Approved | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | FALSE | 70 |  |  | 0 | 0
|  | IP address retained or New Provide | FALSE | 70 | FALSE | 70 | 0 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 10 | 2.5
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | FALSE | 70 | FALSE | 70 | 0 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 45.6522
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 12.5
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.78152
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
78%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## KRISLITE @ SIAEC
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-12-15 | 2023-12-20 | 2023-12-26 | 2024-01-23 | 2024-01-25 | 2024-01-26
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | KRISLITE @ SIAEC | COMPLETED | COMPLETED | COMPLETED | COMPLETED | WIP | WIP | 2024-01-25
|  | 2023-12-15 | NA | 2023-12-19 | 2023-12-20 | 2023-12-22 | 2023-12-22 | 2023-12-26 | 2023-12-22 | 2023-12-28 | 2024-01-01 |  |  |  | 2023-12-08 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
KRISLITE @ SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-01-25 | AMENDMENT REQUIRED |  |  | 87.5% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | KRISLITE @ SIAEC | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 9, #03-00 LOYANG WAY 508722 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664017 ZFJ2259002 ZFJ2460001 ZEW2664018 ZFJ2259003 ZFJ2460002 ZFJ2259001 ZFJ2321001 ZFJ2321002 | SDWP0003400052SNG ETHCE00296901SNG CE00296901SNG SDWP0003400053SNG ETHCE00296902SNG CE00296902SNG ELITE00171021SNG 00171021SNG 181426356 | 2023-12-12 | 32 | 2024-01-25 | 0 | 2023-12-12 |  |  | 2024-01-25 | 2023-12-08 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | KRISLITE @ SIAEC | 2023-12-12 | 2024-01-25
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED |  |  | Resurvey initiated
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | 2024-01-25
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | 2024-01-26
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-12-12 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | CONFIRMED | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | FALSE | 70 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | FALSE | 70 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | 10 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 87.5% | Pending Completion | 12.5%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 87.5%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 50 | 0
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Documents submitted | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Approved | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Patching Completed, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 12.5 | 5
|  | Schedule | TRUE | 84 |  |  | 2.5 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | FALSE | 70 |  |  | 0 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 17.5
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.875
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
88%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## KRISSHOP @ SICC2
2024-02-09
Dashboard Catalyst
| 2024-02-09 | [78 empty] | Site ID | Order Processing | Access Clearance for Site Survey | Site Survey | MUX Installation & Link Readiness | HW Installation | Testing and Handover | Target RFS
| Summary Tab catalyst | [79 empty] | 2023-12-22 | 2023-12-27 | 2024-01-02 | 2024-01-30 | 2024-02-01 | 2024-02-02
Site ID | Scope | IKOM | Matching Orders | Internal Work Orders | EKOM | Site Survey Schedule | PO/SO to be issued | CPE ETA confirmation at Destination | Cease Date Confirmation | Site Survey Completion | CE Routing | Cease CRD |  | Target RFS (D) | CRD | Work orders to be closed | Timeline | % completed | [61 empty] | KRISSHOP @ SICC2 | COMPLETED | COMPLETED | COMPLETED | COMPLETED | WIP | WIP | 2024-02-01
|  | 2023-12-22 | NA | 2023-12-26 | 2023-12-27 | 2023-12-29 | 2023-12-29 | 2024-01-02 | 2023-12-29 | 2024-01-04 | 2024-01-08 |  |  |  | 2023-12-14 | [15 empty] | TIMELINES | [8 empty] | AIR REGISTER
KRISSHOP @ SICC2 | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | COMPLETED | NA | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | NEEDS ATTENTION | 2024-02-01 | AMENDMENT REQUIRED |  |  | 87.5% | [14 empty] | EXTERNAL DEPENDENCIES |  |  |  |  | CRD |  | Project #: |  | Updated by: | Hashim Aslam | Inherent Impact (Without Controls) |  |  |  | Date Last Updated: | 2023-06-17 |  |  |  | Residual Impact | [11 empty] | Impact Status | Master Risk Matrix |  | Risk Matricies
[21 empty] | Project Code | Site ID | SOW | Address | Contact Person | Wknd./Non-Wknd. | WO Type | WO# | Svc# | Project Initiated on | Maximum SLA Period | Maximum Lead time | INFRABUILD READINESS | CPE READINESS | EXTERNAL DEPENDENCY | Confirmed Cease Date | Target RFS | Provide/Change CRD | Scheduled Provisioning Date | # | Description | Date Opened | Type | Consequences | Ownership | Probability | Impact | Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date | Description | Date Opened | Type | Consequences | Ownership | Residual Probability | Residual Impact | Residual Impact Rating | Targeted Completion Date | Mitigating action | Mitigation Owner | Actual Completion Date |  | Impact: |  | Very Low | Low | Medium | High | Very High | NIL | Action Item | Very High | Very High
[21 empty] | SOAE233X | KRISSHOP @ SICC2 | Provisioning of Diverse Singnet Ethernet Links and Replacement of Vedge 1000 device with Cisco C8200 device to intergrate SIA network to SDWAN fabric | 30,SATS INFLIGHT CATERING, CHANGI NORTH CRESCENT, 499612 | Aristofae Rojas +65 81819185 9Aristofae_Rojas@singaporeair.com.sg | Weekday/After Office Hours | Provide Provide Provide Provide Provide Provide Cease Cease Cease | ZEW2664031 ZFJ6272015 ZFJ7294017 ZEW2664032 ZFJ6272016 ZFJ7294018 ZFJ6272007 ZFJ7294007 ZFJ7294008 | SDWP0003400066SNG ETHCE00296978SNG CE00296978SNG SDWP0003400067SNG ETHCE00296979SNG CE00296979SNG ELITE00203859SNG 00203859SNG 181478014 | 2023-12-19 | 32 | 2024-02-01 | 0 | 2023-12-19 |  |  | 2024-02-01 | 2023-12-14 |  | 1 |  |  | Risk |  |  | High | Very High | Critical | [6 empty] | Risk |  |  | Very High | Medium | Severe |  |  |  |  | OPEN | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | NIL | Issue | High | High | Action Item | Issue | Risk
[40 empty] | 2 |  |  | Risk |  |  | Very High | High | Critical | [6 empty] | Risk |  |  | High | Medium | Severe |  |  |  |  | OPEN |  | High | Sustainable | Moderate | Severe | Critical | Critical | NIL | Risk | Medium | Medium | Very High | Very High | Very High
[20 empty] | Date | PI Notes | [18 empty] | 3 |  |  | Risk |  |  | High | Medium | Severe | [6 empty] | Risk |  |  | Medium | Low | Moderate |  |  |  |  | OPEN |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | NIL |  | Low | Low | High | High | High |  | Site ID | Project Initiated on | Target RFS
[40 empty] | 4 |  |  | Risk |  |  | Medium | Low | Moderate | [6 empty] | Risk |  |  | Low | Low | Sustainable |  |  |  |  | OPEN |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | NIL |  | Very Low | Very Low | Medium | Medium | Medium |  | KRISSHOP @ SICC2 | 2023-12-19 | 2024-02-01
[40 empty] | 5 |  |  | Risk |  |  | High | Very Low | Sustainable | [6 empty] | Risk |  |  | NIL | NIL | NIL |  |  |  |  | CLOSED |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | NIL |  | NIL | NIL | Low | Low | Low
[40 empty] | 6 | [26 empty] | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  |  |  | Very Low | Very Low | Very Low
[21 empty] | Description | Target Date | Status |  | REMARKS | Date Completed | [13 empty] | 7
|  | RFS Analysis | [16 empty] | POWER PLAY | WBS | IKOM | COMPLETED | [17 empty] | 8 | [36 empty] | Action Item | Issue | Risk |  | Description | Target Date | Status |  | REMARKS | Date Completed
|  | Days required for Admin Works | 5 | [17 empty] | Matching Orders | NA | [17 empty] | 9 | [36 empty] | Very High | Very High | Very High | WBS | Order Processing | COMPLETED
[21 empty] | Internal Work Orders | COMPLETED | [17 empty] | 10 | [36 empty] | High | High | High |  | Access Clearance for Site Survey | COMPLETED
|  | CRITICAL PATH ANALYSIS | [18 empty] | EKOM | COMPLETED | [17 empty] | 11 | [36 empty] | Medium | Medium | Medium |  | Site Survey | COMPLETED
|  | Activity | Predecessor | Description | Duration | CPA | [14 empty] | Site Survey Schedule | COMPLETED | [17 empty] | 12 | [36 empty] | Low | Low | Low |  | MUX Installation & Link Readiness | COMPLETED
|  | A | - | IKOM | 3 | 3 | [14 empty] | PO/SO to be issued | COMPLETED | [17 empty] | 13 | [36 empty] | Very Low | Very Low | Very Low |  | HW Installation | 2024-02-01
|  | B | - | Matching Orders | 5 | 5 | [14 empty] | CPE ETA | COMPLETED | [17 empty] | 14 | [36 empty] | NIL | NIL | NIL |  | Testing and Handover | 2024-02-02
|  | C | - | Internal Work Orders | 5 | 5 | [14 empty] | Cease Date Confirmation | COMPLETED | [17 empty] | 15
|  | D | A | EKOM | 6 | 3 | [14 empty] | Site Survey Completion | COMPLETED
|  | E | B,C | Site Survey Schedule | 8 | 3 | [14 empty] | CE Routing | COMPLETED
|  | F | C | PO/SO to be issued | 8 | 3 | [14 empty] | Work Orders to be closed | [58 empty] | DASHBOARD ANALYSIS
|  | G | F | CPE ETA | 10 | 2 | [14 empty] | Duration to complete critical tasks | 14 | Status |  | REFERENCE | Owner | [13 empty] | Inherent Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items | Issues | Risk | [30 empty] | Activity | Description | Duration
|  | H |  | Cease Date Confirmation | 8 | 8 | [13 empty] | EXTERNAL DEPENDENCIES | CPE at Destination ETA | 2023-12-19 |  |  | CONFIRMED | TD/TM | [13 empty] | Impact: |  | Very Low | Low | Medium | High | Very High |  |  | 5 | [30 empty] | A | Order Processing | 3
|  | I | E | Site Survey Completion | 12 | 4 | [14 empty] | Infrabuild/RFS date by Partner |  |  |  | CONFIRMED | SDO/PARTNER | [13 empty] | Probability | Very High |  |  |  | 1 | [34 empty] | B | Access Clearance for Site Survey | 6
|  | J | I | CE Routing | 14 | 2 | [14 empty] | External Dependencies |  |  |  | NA | CLIENT | [14 empty] | High | 1 |  | 1 |  | 1 | [33 empty] | C | Site Survey | 10
|  | K |  | Work Orders to be closed | 4 | [15 empty] | Cease Date Agreed with Stakeholders |  |  |  | CONFIRMED | CLIENT/PARTNER | [14 empty] | Medium |  | 1 | [36 empty] | D | MUX Installation & Link Readiness | 30
[41 empty] | Low | [38 empty] | E | HW Installation | 32
|  | Description | Duration | ES | EF | LS | LF | [13 empty] | Communication Checklist | Target Date | Status |  | Owner | Date Completed | Remarks | [13 empty] | Very Low | [38 empty] | F | Testing Completed and Handed Over | 33
|  | IKOM | 3 | 0 | 3 | 8 | 11 | [13 empty] | Kick off Email to Client | COMPLETED |  |  | PE
|  | Matching Orders | 0 | 0 | 0 | 5 | 5 | [13 empty] | Instructions for Internal Orders to ASE | COMPLETED |  |  | PC | [14 empty] | Residual Impact Matrix |  | Date Last Updated: | 2023-06-17 |  |  |  | Action Items |  | Issues |  | Risks
|  | Internal Work Orders | 5 | 0 | 5 | 0 | 5 | [13 empty] | Instructions for Matching Order to DPE | NA |  |  | PC | [14 empty] | Impact: |  | Very Low | Low | Medium | High | Very High | Closed | Open | Closed | Open | Closed | Open | [27 empty] | Dashboard Catalysts
|  | EKOM | 3 | 3 | 6 | 11 | 14 | [13 empty] | Instructions for CPE Order to ASE | NA |  |  | PC | [14 empty] | Probability | Very High |  |  | 1 | [35 empty] | Order Processing | TRUE | 84 | FALSE | 70
|  | Site Survey Schedule | 3 | 5 | 8 | 5 | 8 | [13 empty] | Handover email to Customer |  |  |  | PE | [15 empty] | High |  |  | 1 | [35 empty] | Access Clearance for Site Survey | TRUE | 84 | FALSE | 70
|  | PO/SO to be issued | 3 | 5 | 8 | 9 | 12 | [33 empty] | Medium |  | 1 | [36 empty] | Site Survey | TRUE | 84 | FALSE | 70
|  | CPE ETA confirmation at Destination | 2 | 8 | 10 | 12 | 14 | [33 empty] | Low |  | 1 | [36 empty] | MUX Installation & Link Readiness | TRUE | 84 | FALSE | 70
|  | Cease Date Confirmation | 8 | 0 | 8 | 6 | 14 | [33 empty] | Very Low | [38 empty] | HW Installation | FALSE | 70 | FALSE | 70
|  | Site Survey Completion | 4 | 8 | 12 | 8 | 12 | [13 empty] | WBS | Status |  | Owner | Remarks | [54 empty] | Testing and Handover | FALSE | 70 | FALSE | 70
|  | CE Routing | 2 | 12 | 14 | 12 | 14 | [13 empty] | Order Processing | [18 empty] | Risk Rating | Inherent |  | Residual
|  | Work orders to be closed | [18 empty] | SDWAN Orders Processed |  |  | SDE/SDO | [15 empty] | Risk | 50% | 5 | 50%
[21 empty] | Link Orders Processed |  |  | SDE/SDO | [15 empty] | Issues | 30% |  | 30%
[21 empty] | Diversity Confirmation in orders |  |  | SDE/SDO | [15 empty] | Action Items | 20% |  | 20%
[21 empty] | HW Readiness | [20 empty] | 2.5 |  | 0
|  |  | 8 |  |  |  | 8 | [10 empty] | 14 |  |  | HW released by Ingram |  |  | Ingram | [15 empty] | Nett Rating |  | 2.5
|  | A | 0 | 3 |  | D | 3 | 6 | [9 empty] | FINISH |  |  | HW availability at Xsys |  |  | Xsys
|  | 3 | 8 | 11 |  | 3 | 11 | 14 | [12 empty] | BOM Confirmation |  |  | Xsys
[21 empty] | HW Ready for Deployment |  |  | Xsys
|  |  | 5 | [17 empty] | S/N. of Hardware onbaorded in Smart Portal |  |  | GSP
|  | B | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | Site Survey
|  | 0 | 5 | 5 |  | E | 5 | 8 |  | I | 8 | 12 |  | J | 12 | 14 |  |  |  |  | Survey Schedule Confirmed |  |  | SDO
[6 empty] | 3 | 5 | 8 |  | 4 | 8 | 12 |  | 2 | 12 | 14 |  |  |  |  | Access Required |  |  | Client
[21 empty] | Access Documents submitted |  |  | PM
|  |  | 0 |  |  |  | 4 |  |  |  | 4 | [9 empty] | Access Approved |  |  | Client
|  | C | 0 | 5 |  | F | 5 | 8 |  | G | 8 | 10 | [8 empty] | Site Survey Completed |  |  | SDO
|  | 5 | 0 | 5 |  | 3 | 9 | 12 |  | 2 | 12 | 14 | [8 empty] | CE Routing
[21 empty] | SLD Released |  |  | CE
|  |  | 6 | [17 empty] | Patching Required |  |  | CE
|  | H | 0 | 8 | [16 empty] | Patching Completed, if applicable |  |  | CE
|  | 8 | 6 | 14 | [16 empty] | Routing Released |  |  | CE
Cease Date Confirmation
|  | Deadline Catalysts | [18 empty] | Cease Date Confirmation from Client |  |  | Client
|  | IKOM | TRUE | 84 | FALSE | 70 | [14 empty] | CRD amended to Cease Date |  |  | PC
|  | Matching Orders | FALSE | 70 | TRUE | 84 | [14 empty] | Technical Alignment
|  | Internal Work Orders | TRUE | 84 | FALSE | 70 | [14 empty] | Network Diagram |  |  | CS
|  | EKOM | TRUE | 84 | FALSE | 70 | [14 empty] | IP address retained or New Provide |  |  | CS
|  | Site Survey Schedule | TRUE | 84 | FALSE | 70 | [14 empty] | VLAN information, if applicable |  |  | CS
|  | PO/SO to be issued | TRUE | 84 | FALSE | 70 | [14 empty] | WAN/ LAN IP info from customer/Partner |  |  | GSP
|  | CPE ETA confirmation at Destination | TRUE | 84 | FALSE | 70 | [14 empty] | Provisioning
|  | Cease Date Confirmation | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | Pre-provisioning - Local loop/Cutover | Status |  | Owner | Remarks | Handover date | Billing Start Date | Remarks
|  | Site Survey Completion | TRUE | 84 | FALSE | 70 | [14 empty] | Handover documents - Local Loop |  |  | Partner
|  | CE Routing | TRUE | 84 | FALSE | 70 | [14 empty] | Schedule |  |  | PC
|  | Work orders to be closed | FALSE | 70 | [16 empty] | Technical IKOM, if applicable |  |  | PC
[21 empty] | TD/TM & FE details, if applicable |  |  | PC
|  | External Depedencies Catalysts | [18 empty] | Site POC |  |  | Customer
|  | INFRABUILD DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | 10 | 5 | [10 empty] | TAC booking, if applicable |  |  | PC
|  | CPE ETA DEPENDENCY | TRUE | 84 | FALSE | 70 | 5 | 0 | [12 empty] | GSP Booking, if applicable |  |  | PC
|  | EXTERNAL DEPENDENCY | FALSE | 70 | TRUE | 84 | 0 | 5 | [12 empty] | Conference Bridge |  |  | PC
[21 empty] | Post Provisioning/OLLC Activation | Status |  | Owner | Remarks
[21 empty] | SR form Signed by Client |  |  | Customer
|  | PROBABILITY ANALYSIS | [18 empty] | Handover email |  |  | PE
|  | Duration to complete critical tasks | 14 | [17 empty] | CRD amendment |  |  | PC
|  | Standard Deviation | 2.6771 | [17 empty] | Work order closures |  |  | PC
[21 empty] | Percentage Completed | 87.5% | Pending Completion | 12.5%
|  | Description | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | [13 empty] | Project Progress | 87.5%
|  | IKOM | 2 | 3 | 5 | 3.1667 | 0.5
|  | Matching Orders | 3 | 5 | 10 | 5.5 | 0
|  | Internal Work Orders | 3 | 5 | 10 | 5.5 | 1.1667
|  | EKOM | 4 | 6 | 8 | 6 | 0.66667
|  | Site Survey Schedule | 5 | 8 | 10 | 7.8333 | 0.83333
|  | PO/SO to be issued | 5 | 8 | 10 | 7.8333 | 0.83333
|  | CPE ETA confirmation at Destination | 9 | 10 | 12 | 10.1667 | 0.5
|  | Cease Date Confirmation | 7 | 8 | 12 | 8.5 | 0.83333
|  | Site Survey Completion | 10 | 12 | 16 | 12.3333 | 1
|  | CE Routing | 11 | 14 | 16 | 13.8333 | 0.83333
|  | Work orders to be closed |  |  | 5 | Vairance | 7.1667
|  | DEPENDENCY ANALYSIS | Minimum SLA period | Maximum SLA Period
|  | Order Raising | 0 | 0
|  | Partner |  | 32
Sales
Client
TD/TM
CS
PM
Communication Catalysts
|  | Kick off Email to Client | TRUE | 84
|  | Instrcutions for Internal Orders to ASE | TRUE | 84
|  | Instructions for Matching Order to ASE | FALSE | 70 | TRUE | 84
|  | Instructions for CPE Order to ASE | FALSE | 70 | TRUE | 84
|  | Handover email to Customer | FALSE | 70
WBS Catalysts
|  | Order Processing |  | 23 |  |  | 2.1739
|  | SDWAN Orders Processed | TRUE | 84 |  |  | 2.1739 | 0 | 43.4783 | 6.5217
|  | Link Orders Processed | TRUE | 84 |  |  | 2.1739 | 0
|  | Diversity Confirmation in orders | TRUE | 84 | FALSE | 70 | 2.1739 | 0
HW Readiness
|  | HW released by Ingram | TRUE | 84 |  |  | 2.1739 | 0
|  | HW availability at Xsys | TRUE | 84 |  |  | 2.1739 | 0
|  | BOM Confirmation | TRUE | 84 |  |  | 2.1739 | 0
|  | HW Ready for Deployment | TRUE | 84 |  |  | 2.1739 | 0
|  | S/N. of Hardware onbaorded in Smart Portal | TRUE | 84 |  |  | 2.1739 | 0
HW Readiness
|  | Survey Schedule Confirmed | TRUE | 84 |  |  | 2.1739 | 0
|  | Access Required | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Documents submitted | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Access Approved | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | Site Survey Completed | TRUE | 84 |  |  | 2.1739 | 0
CE Routing
|  | SLD Released | TRUE | 84 |  |  | 2.1739 | 0
|  | Patching Required | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Patching Completed, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | Routing Released | TRUE | 84 |  |  | 2.1739 | 0
Cease Date Confirmation
|  | Cease Date Confirmation from Client | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | CRD amended to Cease Date | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Technical Alignment
|  | Network Diagram | TRUE | 84 |  |  | 2.1739 | 0
|  | IP address retained or New Provide | TRUE | 84 | FALSE | 70 | 2.1739 | 0
|  | VLAN information, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.1739
|  | WAN/ LAN IP info from customer/Partner | TRUE | 84 | FALSE | 70 | 2.1739 | 0
Provisioning
|  | Pre-provisioning - Local loop/Cutover |  | 8 |  |  | 2.5
|  | Handover documents - Local Loop | TRUE | 84 | FALSE | 70 | 2.5 | 0 | 12.5 | 5
|  | Schedule | FALSE | 70 |  |  | 0 | 0
|  | Technical IKOM, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | TD/TM & FE details, if applicable | TRUE | 84 | FALSE | 70 | 2.5 | 0
|  | Site POC | TRUE | 84 |  |  | 2.5 | 0
|  | TAC booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | GSP Booking, if applicable | FALSE | 70 | TRUE | 84 | 0 | 2.5
|  | Conference Bridge | TRUE | 84 |  |  | 2.5 | 0
|  | Post Provisioning/OLLC Activation |  | 4 |  |  | 2.5
|  | SR form Signed by Client | FALSE | 70 |  |  | 0 | 0 | 0 | 0
|  | Handover email | FALSE | 70 |  |  | 0 | 0
|  | CRD amendment | FALSE | 70 |  |  | 0 | 0
|  | Work order closures | FALSE | 70 |  |  | 0 | 0
[6 empty] | Internal Dependencies | 50
|  | Completion Status |  |  |  | Risk Analysis | 20
|  | WIP |  |  |  | Provisioning Check List | 17.5
|  | Partially Completed |  |  |  | Post Provisioning | 0
|  | Fully Completed |  |  |  |  | 0.875
Work Order Status
Open
Closed
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
Completed
NA
Completed
Completed
Confirmed
NA
Confirmed
NA
Applicable
NA
Yes
Retain
Provide
Received
Completed
NA
Completed
NA
Yes
NA
Yes
NA
NA
Confirmed
Confirmed
NA
Confirmed
Confirmed
NA
Confirmed
NA
Created & Shared
Confirmed
Sent to Customer
Completed
Completed
Confirmed
NA
Completed
Completed
Completed
Completed
Completed
NA
NA
Completed
NA
Provided
88%
Yes
Exchange Diverse
Path Diverse
Completed
Confirmed
Confirmed
Confirmed
Onboarded
Confirmed
Required
Submitted
Approved
Completed
Completed
Required
Completed
NA
NA
Not Required
NA
NA
Released
Completed
NA
Completed
NA
Completed
NA
NA
Completed
NA
NA
Completed
NA
NA
Completed

## Work Order Details
|  | Project Code | SOAE233X
| Site Name | WO# | WO TYPE | Svc# | A - End Address | Exchange (for domestic circuits) | B - End Address | Exchange (for domestic circuits) | Product | Target CRD | WO Status
| DCE Headend | ZEW2664034 | Provide | SDWP0003400069SNG | 38A KIM CHUAN ROAD,537055 | PL |  |  | CN - ConnectPlus IP VPN | 2023-11-03 | Closed
| DCE Headend |  | Cease |  | 38A KIM CHUAN ROAD,537055 |  |  |  | V edge 1000 Device
| TSQ Headend | ZEW2664033 | Provide | SDWP0003400068SNG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 | CG |  |  | CN - ConnectPlus IP VPN | 2023-11-03 | Closed
| TSQ Headend |  | Cease |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 |  |  |  | V edge 1000 Device
| ION | ZEW2664001 | Provide | SDWP0003400036SNG | 2 ION ORCHARD #04-03C ORCHARD TURN 238801 | OC | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-02-15 | Open
| ION | ZEV9644003 | Provide | ETHCE00296864SNG | 2 ION ORCHARD #04-05C ORCHARD TURN 238801 | OC | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet Ethernet | 2023-09-25 | Closed
| ION | ZFJ0973002 | Provide | CE00296864SNG | 2 ION ORCHARD #04-05C ORCHARD TURN 238801 | OC | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-09-25 | Closed
| ION | ZKQ1431007 | Cease | M0583682 | 2 Orchard Turn, ION Orchard #04-03C |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| ION | ZKQ1431008 | Cease | SDWP0003400009SNG | Work Orders to be raised |  |  |  | V edge Device | 2024-04-30 | Open
| ION | ZEW2664002 | Provide | SDWP0003400037SNG | 2 ION ORCHARD #04-03C ORCHARD TURN 238801 | OC | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-02-15 | Open
| ION | ZEV9644004 | Provide | ETHCE00296862SNG | 2 ION ORCHARD #04-05C ORCHARD TURN 238801 | OC | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet Ethernet | 2023-09-25 | Closed
| ION | ZFJ0973001 | Provide | CE00296862SNG | 2 ION ORCHARD #04-05C ORCHARD TURN 238801 | OC | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-09-25 | Closed
| ION | ZKQ1431008 | Cease | M0669817 | 2 Orchard Turn, ION Orchard #04-03C |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-04-30 | Open
| ION | ZKQ1431008 | Cease | SDWP0003400010SNG | Work Orders to be raised |  |  |  | V edge Device | 2024-04-30 | Open
| ION | ZEV9644005 | Cease | ELITE00169960SNG | 2 Orchard Turn, ION Orchard #04-03C |  |  |  | SingNet Elite | 2024-04-30 | Open
| ION | ZLL8699001 | Cease | 00169960SNG | 2 Orchard Turn, ION Orchard #04-03C |  |  |  | CN - Meg@pop Suite Of IP Services | 2024-04-30 | Open
| ION | ZEV9748002 | Cease | 181426229 | 2 Orchard Turn, ION Orchard #04-03C |  |  |  | TS - FTTH | 2024-04-30 | Open
| Chai Chee | ZEW2664019 | Provide | SDWP0003400054SNG | 750B,WESTERN DIGITAL #04-05. CHAI CHEE ROAD. 469002 | BD | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2023-11-03 | Closed
| Chai Chee | ZFJ2259005 | Provide | ETHCE00296949SNG | 750B,WESTERN DIGITAL #04-05. CHAI CHEE ROAD. 469002 | BD | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet Ethernet | 2023-09-11 | Closed
| Chai Chee | ZFJ2460003 | Provide | CE00296949SNG | 750B,WESTERN DIGITAL #04-05. CHAI CHEE ROAD. 469002 | BD | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-09-11 | Closed
| Chai Chee | ZKP3398002 | Cease | M0578588 | 750B CHAI CHEE ROAD WESTERN DIGITAL #04-05 |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| Chai Chee |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| Chai Chee | ZEW2664020 | Provide | SDWP0003400055SNG | 750B,WESTERN DIGITAL #04-05. CHAI CHEE ROAD. 469002 | BD | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2023-11-03 | Closed
| Chai Chee | ZFJ2259006 | Provide | ETHCE00296953SNG | 750B,WESTERN DIGITAL #04-05. CHAI CHEE ROAD. 469002 | BD | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet Ethernet | 2023-09-11 | Closed
| Chai Chee | ZFJ2460004 | Provide | CE00296953SNG | 750B,WESTERN DIGITAL #04-05. CHAI CHEE ROAD. 469002 | BD | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-09-11 | Closed
| Chai Chee | ZKP3398001 | Cease | M0567363 | 750B,WESTERN DIGITAL #04-05. CHAI CHEE ROAD. 469002 |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-04-30 | Open
| Chai Chee |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| Chai Chee | ZFJ2259004 | Cease | ELITE00171059SNG | 750B CHAI CHEE ROAD WESTERN DIGITAL #04-05 |  |  |  | SingNet Elite | 2023-11-10 | Closed
| Chai Chee | ZFJ2321003 | Cease | 00171059SNG | 750B CHAI CHEE ROAD WESTERN DIGITAL #04-05 |  |  |  | CN - Meg@pop Suite Of IP Services | 2023-11-10 | Closed
| Chai Chee | ZFJ2321004 | Cease | 181426421 | 750B CHAI CHEE ROAD WESTERN DIGITAL #04-05 |  |  |  | TS - FTTH | 2023-11-10 | Closed
| ALH Guard | ZEW2664021 | Provide | SDWP0003400056SNG | 4 AIRLINE HOUSE GUARDHOUSE AIRLINE ROAD 819825 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-02-12 | Open
| ALH Guard | ZFJ2259009 | Provide | ETHCE00296962SNG | 4 AIRLINE HOUSE GUARDHOUSE AIRLINE ROAD 819825 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet Ethernet | 2023-10-16 | Closed
| ALH Guard | ZFJ2460005 | Provide | CE00296962SNG | 4 AIRLINE HOUSE GUARDHOUSE AIRLINE ROAD 819825 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-10-16 | Closed
| ALH Guard |  | Cease | M0567363 | 4 Airline Road, Airline house Guardhouse Pass Office |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E
| ALH Guard |  | Cease | SDWP0003400027SNG | Work Orders to be raised |  |  |  | V edge Device
| ALH Guard | ZEW2664022 | Provide | SDWP0003400057SNG | 4 AIRLINE HOUSE GUARDHOUSE AIRLINE ROAD 819825 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-02-12 | Open
| ALH Guard | ZFJ2259010 | Provide | ETHCE00296963SNG | 4 AIRLINE HOUSE GUARDHOUSE AIRLINE ROAD 819825 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet Ethernet | 2023-10-16 | Closed
| ALH Guard | ZFJ2460006 | Provide | CE00296963SNG | 4 AIRLINE HOUSE GUARDHOUSE AIRLINE ROAD 819825 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-10-16 | Closed
| ALH Guard |  | Cease | SDWP0003400028SNG | Work Orders to be raised |  |  |  | V edge Device
| ALH Guard | ZFJ2259008 | Cease | ELITE00171056SNG | 4 Airline Road, Airline house Guardhouse Pass Office |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | SingNet Elite | 2024-04-30 | Open
| ALH Guard | ZFJ2321005 | Cease | 00171056SNG | 4 Airline Road, Airline house Guardhouse Pass Office |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | CN - Meg@pop Suite Of IP Services | 2024-04-30 | Open
| ALH Guard | ZFJ2321006 | Cease | 181426414 | 4 Airline Road, Airline house Guardhouse Pass Office |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | TS - FTTH | 2024-04-30 | Open
| Data Post | ZEW2664023 | Provide | SDWP0003400058SNG | 4,AYER RAJAH CRESCENT. #03-00. 139960 | AR | Address Not Provided | PL | CN - ConnectPlus IP VPN | 2024-02-20 | Open
| Data Post |  |  | ELITE00171062SNG | Work Orders to be raised |  | 4 AYER RAJAH CRESCENT #03-00 |  | SingNet Elite
| Data Post | ZEW2664024 | Provide | SDWP0003400059SNG | 4,AYER RAJAH CRESCENT. #03-00. 139960 | AR |  | CG | CN - ConnectPlus IP VPN | 2024-02-20 | Open
| Data Post |  | Cease | SDWP0003400017SNG | Work Orders to be raised |  |  |  | V edge Device
| Data Post |  | Cease | SDWP0003400018SNG | Work Orders to be raised |  |  |  | V edge Device
| Mentor Media | ZEW2664025 | Provide | SDWP0003400060SNG | 47,JALAN BUROH. #01-02. 619491 | JR | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-02-23 | Open
| Mentor Media |  |  | ELITE00171070SNG | Work Orders to be raised |  | 47 JALAN BUROH #01-02 |  | SingNet Elite
| Mentor Media | ZEW2664026 | Provide | SDWP0003400061SNG | 47,JALAN BUROH. #01-02. 619491 | JR | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-02-23 | Open
| Mentor Media |  | Cease | SDWP0003400019SNG | Work Orders to be raised |  |  |  | V edge Device
| Mentor Media |  | Cease | SDWP0003400020SNG | Work Orders to be raised |  |  |  | V edge Device
| Scoot T1 | ZCG9563001 | Change | SDWP0003400025SNG | 80 CHANGI AIRPORT T1 #04-15 AIRPORT BOULEVARD 819642 | CG | Address Not Provided |  | CN - ConnectPlus IP VPN | 2023-04-05 | Closed
| Scoot T1 | ZEW2664035 | Provide | SDWP0003400070SNG | 80 CHANGI AIRPORT T1 #04-15 AIRPORT BOULEVARD 819642 | CG | Address Not Provided |  | CN - ConnectPlus IP VPN | 2024-02-20 | Open
| Scoot T1 | ZEW2664036 | Provide | SDWP0003400071SNG | 80 CHANGI AIRPORT T1 #04-15 AIRPORT BOULEVARD 819642 | CG | Address Not Provided |  | CN - ConnectPlus IP VPN | 2024-02-20 | Open
| Scoot T1 |  | Cease | SDWP0003400026SNG | Work Orders to be raised |  |  |  | V edge Device
| Scoot T3 | ZCG9563002 | Change | SDWP0003400026SNG | 65 CHANGI AIRPORT TERMINAL 3 #B1-17 AIRPORT BOULEVARD 819663 | CG | Address Not Provided |  | CN - ConnectPlus IP VPN | 2023-03-24 | Closed
| Scoot T3 | ZEW2664037 | Provide | SDWP0003400072SNG | 65 CHANGI AIRPORT TERMINAL 3. AIRPORT BOULEVARD. 819663 | CG | Address Not Provided |  | CN - ConnectPlus IP VPN | 2023-06-20 | Closed
| Scoot T3 | ZEW2664038 | Provide | SDWP0003400073SNG | 65 CHANGI AIRPORT TERMINAL 3. AIRPORT BOULEVARD. 819663 | CG | Address Not Provided |  | CN - ConnectPlus IP VPN | 2023-06-20 | Closed
| Scoot T3 |  | Cease | SDWP0003400025SNG | Work Orders to be raised |  |  |  | V edge Device
| SMC - SIAEC | ZEW2664011 | Provide | SDWP0003400046SNG | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499614 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2023-12-07 | Closed
| SMC - SIAEC | ZEV9644018 | Provide | ETHCE00296947SNG | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499614 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet Ethernet | 2023-10-31 | Closed
| SMC - SIAEC | ZFJ0973009 | Provide | CE00296947SNG | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499614 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-10-31 | Closed
| SMC - SIAEC | ZKQ1431016 | Cease | M0663236 | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499615 |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| SMC - SIAEC |  | Cease | SDWP0003400013SNG | Work Orders to be raised |  |  |  | V edge Device
| SMC - SIAEC | ZEW2664012 | Provide | SDWP0003400047SNG | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499614 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2023-12-07 | Closed
| SMC - SIAEC | ZEV9644019 | Provide | ETHCE00296951SNG | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499614 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet Ethernet | 2023-10-31 | Closed
| SMC - SIAEC | ZFJ0973010 | Provide | CE00296951SNG | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499614 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-10-31 | Closed
| SMC - SIAEC | ZKQ1431017 | Cease | M0669964 | 34,SATS MAINTENANCE CENTRE. CHANGI NORTH CRESCENT. 499615 |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-04-30 | Open
| SMC - SIAEC |  | Cease | SDWP0003400014SNG | Work Orders to be raised |  |  |  | V edge Device
| SMC - SIAEC | ZEV9644017 | Cease | ELITE00171030SNG | 34 CHANGI NORTH CRESCENT SATS MAINTENANCE CENTRE |  |  |  | SingNet Elite | 2023-12-14 | Closed
| SMC - SIAEC | ZEV9748013 | Cease | 00171030SNG | 34 CHANGI NORTH CRESCENT SATS MAINTENANCE CENTRE |  |  |  | CN - Meg@pop Suite Of IP Services | 2023-12-14 | Closed
| SMC - SIAEC | ZEV9748014 | Cease | 181426370 | 34 CHANGI NORTH CRESCENT SATS MAINTENANCE CENTRE |  |  |  | TS - FTTH | 2023-12-14 | Closed
| PTB4 - SIAEC | ZEW2664009 | Provide | SDWP0003400044SNG | 10 AIRPORT BOULEVARD #01-44. CHANGI AIRPORT TERMINAL 4 819665 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-02-27 | Open
| PTB4 - SIAEC | ZFJ6272017 | Provide | ETHCE00296981SNG | 10 AIRPORT BOULEVARD #01-44. CHANGI AIRPORT TERMINAL 4 819665 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet Ethernet | 2024-01-09 | Closed
| PTB4 - SIAEC | ZFJ7294019 | Provide | CE00296981SNG | 10 AIRPORT BOULEVARD #01-44. CHANGI AIRPORT TERMINAL 4 819665 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2024-01-09 | Closed
| PTB4 - SIAEC | ZKQ1431015 | Cease | M0663233 | 10 AIRPORT BOULEVARD CHANGI AIRPORT T4 #01-44 |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| PTB4 - SIAEC |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| PTB4 - SIAEC | ZEW2664010 | Provide | SDWP0003400045SNG | 10 AIRPORT BOULEVARD #01-44. CHANGI AIRPORT TERMINAL 4 819665 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-02-27 | Open
| PTB4 - SIAEC | ZFJ6272018 | Provide | ETHCE00297030SN | 10 AIRPORT BOULEVARD #01-44. CHANGI AIRPORT TERMINAL 4 819665 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet Ethernet | 2024-02-15 | Open
| PTB4 - SIAEC | ZFJ7294020 | Provide | CE00297030SNG | 10 AIRPORT BOULEVARD #01-44. CHANGI AIRPORT TERMINAL 4 819665 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2024-02-15 | Open
| PTB4 - SIAEC | ZKQ1431014 | Cease | M0663135 | 10 AIRPORT BOULEVARD CHANGI AIRPORT T4 #01-44 |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-04-30 | Open
| PTB4 - SIAEC |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| PTB4 - SIAEC | ZFJ6272008 | Cease | ELITE00171034SNG | 10 AIRPORT BOULEVARD CHANGI AIRPORT T4 #01-44 |  |  |  | SingNet Elite | 2024-04-30 | Open
| PTB4 - SIAEC | ZFJ7294009 | Cease | 00171034SNG | 10 AIRPORT BOULEVARD CHANGI AIRPORT T4 #01-44 |  |  |  | CN - Meg@pop Suite Of IP Services | 2024-04-30 | Open
| PTB4 - SIAEC | ZFJ7294010 | Cease | 181426387 | 10 AIRPORT BOULEVARD CHANGI AIRPORT T4 #01-44 |  |  |  | TS - FTTH | 2024-04-30 | Open
| KRISSHOP @ CHANGI | ZEW2664027 | Provide | SDWP0003400062SNG | #03-02 CHANGI SOUTH LANE 486045 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-01-25 | Open
| KRISSHOP @ CHANGI | ZFJ6272013 | Provide | ETHCE00296976SNG | #03-02 CHANGI SOUTH LANE 486045 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet Ethernet | 2023-12-01 | Closed
| KRISSHOP @ CHANGI | ZFJ7294015 | Provide | CE00296976SNG | #03-02 CHANGI SOUTH LANE 486045 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-12-01 | Closed
| KRISSHOP @ CHANGI | ZKP3398006 | Cease | M0669464 | 5 CHANGI SOUTH LANE #03-02 |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-02-01 | Open
| KRISSHOP @ CHANGI |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| KRISSHOP @ CHANGI | ZEW2664028 | Provide | SDWP0003400063SNG | #03-02 CHANGI SOUTH LANE 486045 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-01-25 | Open
| KRISSHOP @ CHANGI | ZFJ6272014 | Provide | ETHCE00296977SNG | #03-02 CHANGI SOUTH LANE 486045 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet Ethernet | 2023-12-01 | Closed
| KRISSHOP @ CHANGI | ZFJ7294016 | Provide | CE00296977SNG | #03-02 CHANGI SOUTH LANE 486045 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-12-01 | Closed
| KRISSHOP @ CHANGI | ZKP3398008 | Cease | M0669565 | 5 CHANGI SOUTH LANE #03-02 |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-02-01 | Open
| KRISSHOP @ CHANGI |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| KRISSHOP @ CHANGI | ZFJ6272005 | Cease | ELITE00176685SNG | 5 CHANGI SOUTH LANE #03-02 |  |  |  | SingNet Elite | 2024-02-01 | Open
| KRISSHOP @ CHANGI | ZFJ7294005 | Cease | 00176685SNG | 5 CHANGI SOUTH LANE #03-02 |  |  |  | CN - Meg@pop Suite Of IP Services | 2024-02-01 | Open
| KRISSHOP @ CHANGI | ZFJ7294006 | Cease | 181503918 | 5 CHANGI SOUTH LANE #03-02 |  |  |  | TS - FTTH | 2024-02-01 | Open
| SICC1 | ZEW2664007 | Provide | SDWP0003400042SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-02-26 | Open
| SICC1 | ZEV9644015 | Provide | ETHCE00296939SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet ethernet | 2023-11-30 | Closed
| SICC1 | ZFJ0973007 | Provide | CE00296939SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-11-30 | Closed
| SICC1 | ZKP3398012 | Cease | M0612592 | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| SICC1 | ZKP3398013 | Cease | SDWP0003400029SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 |  |  |  | V edge Device | 2024-04-30 | Open
| SICC1 |  | Provide | SDWP0003400043SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | #N/A | #N/A
| SICC1 |  | Provide | ETHCE00296940SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet Ethernet | #N/A | #N/A
| SICC1 |  | Provide | CE00296940SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | #N/A | #N/A
| SICC1 | ZKP3398013 | Cease | M0669967 | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-04-30 | Open
| SICC1 |  | Cease | SDWP0003400030SNG | Work Orders to be raised |  |  |  | V edge Device
| SICC1 | ZEV9644014 | Cease | ELITE00171027SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 |  |  |  | SingNet Elite | 2024-04-30 | Open
| SICC1 | ZEV9748011 | Cease | 00171027SNG | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 |  |  |  | CN - Meg@pop Suite Of IP Services | 2024-04-30 | Open
| SICC1 | ZEV9748012 | Cease | 181426363 | 20,ADMIN BLK #02-00 AIRPORT BOULEVARD ROAD 819659 |  |  |  | TS - FTTH | 2024-04-30 | Open
ETF/EOF | EC Engine | ZEW2664015 | Provide | SDWP0003400050SNG | 300, LOYANG AVENUE 509071 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2023-12-14 | Open
| EC Engine | ZFJ6272011 | Provide | ETHCE00296968SNG | 300, LOYANG AVENUE 509071 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet Ethernet | 2023-12-12 | Closed
| EC Engine | ZFJ7294013 | Provide | CE00296968SNG | 300, LOYANG AVENUE 509071 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-12-13 | Closed
| EC Engine | ZKQ1431005 | Cease | M0567355 | 300 LOYANG AVENUE |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| EC Engine |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| EC Engine | ZEW2664016 | Provide | SDWP0003400051SNG | 300, LOYANG AVENUE 509071 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2023-12-14 | Open
| EC Engine | ZFJ6272012 | Provide | ETHCE00296973SNG | 300, LOYANG AVENUE 509071 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet Ethernet | 2023-12-12 | Closed
| EC Engine | ZFJ7294014 | Provide | CE00296973SNG | 300, LOYANG AVENUE 509071 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-12-13 | Closed
| EC Engine | ZKQ1431006 | Cease | M0669965 | 300 LOYANG AVENUE |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-04-30 | Open
| EC Engine |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| EC Engine | ZFJ6272001 | Cease | ELITE00171018SNG | 300 LOYANG AVENUE |  |  |  | SingNet Elite | 2023-12-20 | Closed
| EC Engine | ZFJ7294003 | Cease | 00171018SNG | 300 LOYANG AVENUE |  |  |  | CN - Meg@pop Suite Of IP Services | 2023-12-20 | Closed
| EC Engine | ZFJ7294004 | Cease | 181426349 | 300 LOYANG AVENUE |  |  |  | TS - FTTH | 2023-12-20 | Closed
| KRISSHOP @ SIGNATURE | ZEW2664029 | Provide | SDWP0003400064SNG | THE SIGNATURE #08-06/07 CHANGI BUSINESS PARK CENTRAL 2 486066 | TP | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-01-10 | Closed
| KRISSHOP @ SIGNATURE | ZFJ2259012 | Provide | ETHCE00297027SNG | THE SIGNATURE #08-06/07 CHANGI BUSINESS PARK CENTRAL 2 486066 | TP | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet Ethernet | 2023-11-30 | Closed
| KRISSHOP @ SIGNATURE | ZFJ2460007 | Provide | CE00297027SNG | THE SIGNATURE #08-06/07 CHANGI BUSINESS PARK CENTRAL 2 486066 | TP | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-11-30 | Closed
| KRISSHOP @ SIGNATURE | ZKP3398010 | Cease | M0669352 | CHANGI BUSINESS PARK CENTRAL 2 THE SIGNATURE #08-06/07 |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| KRISSHOP @ SIGNATURE |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| KRISSHOP @ SIGNATURE | ZEW2664008 | Provide | SDWP0003400065SNG | THE SIGNATURE #08-06/07 CHANGI BUSINESS PARK CENTRAL 2 486066 | TP | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-02-26 | Open
| KRISSHOP @ SIGNATURE | ZEV9644016 | Provide | ETHCE00297028SNG | THE SIGNATURE #08-06/07 CHANGI BUSINESS PARK CENTRAL 2 486066 | TP | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet ethernet | 2023-12-13 | Closed
| KRISSHOP @ SIGNATURE | ZFJ0973008 | Provide | CE00297028SNG | THE SIGNATURE #08-06/07 CHANGI BUSINESS PARK CENTRAL 2 486066 | TP | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-12-13 | Closed
| KRISSHOP @ SIGNATURE | ZKP3398011 | Cease | M0669376 | CHANGI BUSINESS PARK CENTRAL 2 THE SIGNATURE #08-06/07 |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-04-30 | Open
| KRISSHOP @ SIGNATURE |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| KRISSHOP @ SIGNATURE | ZFJ2259011 | Cease | ELITE00176684SNG | CHANGI BUSINESS PARK CENTRAL 2 THE SIGNATURE #08-06/07 |  |  |  | SingNet Elite | 2024-04-30 | Open
| KRISSHOP @ SIGNATURE | ZFJ2321007 | Cease | 00176684SNG | CHANGI BUSINESS PARK CENTRAL 2 THE SIGNATURE #08-06/07 |  |  |  | CN - Meg@pop Suite Of IP Services | 2024-04-30 | Open
| KRISSHOP @ SIGNATURE | ZFJ2321008 | Cease | 181437009 | CHANGI BUSINESS PARK CENTRAL 2 THE SIGNATURE #08-06/07 |  |  |  | TS - FTTH | 2024-04-30 | Open
| LOYANG - SIAEC | ZEW2664005 | Provide | SDWP0003400040SNG | 60,SIA SUPPLIES CENTRE, LOYANG WAY, 508751 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-02-23 | Open
| LOYANG - SIAEC | ZEV9644011 | Provide | ETHCE00296927SNG | 60,SIA SUPPLIES CENTRE, LOYANG WAY, 508751 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet ethernet | 2023-11-09 | Closed
| LOYANG - SIAEC | ZFJ0973005 | Provide | CE00296927SNG | 60,SIA SUPPLIES CENTRE, LOYANG WAY, 508751 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-11-09 | Closed
| LOYANG - SIAEC | ZKQ1431012 | Cease | M0565969 | SATS INFLIGHT CATERING CTR 1, 20 Airport Boulevard Admin Blk Level 2 |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| LOYANG - SIAEC | ZKQ1431013 | Cease |  | Work Orders to be raised |  |  |  | V edge Device | 2024-04-30 | Open
| LOYANG - SIAEC | ZEW2664006 | Provide | SDWP0003400041SNG | 60,SIA SUPPLIES CENTRE, LOYANG WAY, 508751 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-02-23 | Open
| LOYANG - SIAEC | ZEV9644012 | Provide | ETHCE00296928SNG | 60,SIA SUPPLIES CENTRE, LOYANG WAY, 508751 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet ethernet | 2023-11-29 | Closed
| LOYANG - SIAEC | ZFJ0973006 | Provide | CE00296928SNG | 60,SIA SUPPLIES CENTRE, LOYANG WAY, 508751 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-11-29 | Closed
| LOYANG - SIAEC | ZKQ1431013 | Cease | M0669904 | SATS INFLIGHT CATERING CTR 1, 20 Airport Boulevard Admin Blk Level 2 |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-04-30 | Open
| LOYANG - SIAEC | ZKQ1431013 | Cease |  | Work Orders to be raised |  |  |  | V edge Device | 2024-04-30 | Open
| LOYANG - SIAEC | ZEV9644010 | Cease | ELITE00171012SNG | SATS INFLIGHT CATERING CTR 1, 20 Airport Boulevard Admin Blk Level 2 |  |  |  | SingNet Elite | 2024-04-30 | Open
| LOYANG - SIAEC | ZEV9748009 | Cease | 00171012SNG | SATS INFLIGHT CATERING CTR 1, 20 Airport Boulevard Admin Blk Level 2 |  |  |  | CN - Meg@pop Suite Of IP Services | 2024-04-30 | Open
| LOYANG - SIAEC | ZEV9748010 | Cease | 181426325 | SATS INFLIGHT CATERING CTR 1, 20 Airport Boulevard Admin Blk Level 2 |  |  |  | TS - FTTH | 2024-04-30 | Open
| ALPS - SIAEC | ZEW2664013 | Provide | SDWP0003400048SNG | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508988 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-02-15 | Open
| ALPS - SIAEC | ZFJ6272009 | Provide | ETHCE00296946SNG | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508988 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet ethernet | 2023-12-21 | Closed
| ALPS - SIAEC | ZFJ7294011 | Provide | CE00296946SNG | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508988 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-12-21 | Closed
| ALPS - SIAEC | ZKQ1431003 | Cease | M0575186 | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508989 |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| ALPS - SIAEC |  | Cease | SDWP0003400011SNG | Work Orders to be raised |  |  |  | V edge Device
| ALPS - SIAEC | ZEW2664014 | Provide | SDWP0003400049SNG | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508988 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-02-15 | Open
| ALPS - SIAEC | ZFJ6272010 | Provide | ETHCE00296964SNG | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508988 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet ethernet | 2023-12-21 | Closed
| ALPS - SIAEC | ZFJ7294012 | Provide | CE00296964SNG | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508988 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-12-21 | Closed
| ALPS - SIAEC | ZKQ1431004 | Cease | M0669963 | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508989 |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-04-30 | Open
| ALPS - SIAEC |  | Cease | SDWP0003400012SNG | Work Orders to be raised |  |  |  | V edge Device
| ALPS - SIAEC | ZFJ6272002 | Cease | ELITE00182102SNG | 25,LOYANG OFFSHORE SUPPLY BASE 302, #04-08 LOYANG CRESCENT 508989 |  |  |  | SingNet Elite | 2024-04-30 | Open
| ALPS - SIAEC | ZFJ7294001 | Cease | 00182102SNG | 25 LOYANG CRESCENT BLDG 302 #04-08 Loyang Offshore Supply Base |  |  |  | CN - Meg@pop Suite Of IP Services | 2024-04-30 | Open
| ALPS - SIAEC | ZFJ7294002 | Cease | 181443618 | 25 LOYANG CRESCENT BLDG 302 #04-08 Loyang Offshore Supply Base |  |  |  | TS - FTTH | 2024-04-30 | Open
EES/UNITED SQUARE | ESD CHANGI - SIAEC | ZEW2664003 | Provide | SDWP0003400038SNG | 36,SATS MAINTENANCE CENTRE, CHANGI NORTH CRESCENT, 499620 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-02-15 | Open
| ESD CHANGI - SIAEC | ZEV9644008 | Provide | ETHCE00296909SNG | 36,SATS MAINTENANCE CENTRE, CHANGI NORTH CRESCENT, 499620 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet ethernet | 2023-11-23 | Closed
| ESD CHANGI - SIAEC | ZFJ0973003 | Provide | CE00296909SNG | 36,SATS MAINTENANCE CENTRE, CHANGI NORTH CRESCENT, 499620 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-11-23 | Closed
| ESD CHANGI - SIAEC | ZKP3398005 | Cease | M0661007 | 36 CHANGI NORTH CRESCENT Singapore 499620 |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| ESD CHANGI - SIAEC |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| ESD CHANGI - SIAEC | ZEW2664004 | Provide | SDWP0003400039SNG | 36,SATS MAINTENANCE CENTRE, CHANGI NORTH CRESCENT, 499620 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-02-15 | Open
| ESD CHANGI - SIAEC | ZEV9644009 | Provide | ETHCE00296914SNG | 36,SATS MAINTENANCE CENTRE, CHANGI NORTH CRESCENT, 499620 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet ethernet | 2023-11-23 | Closed
| ESD CHANGI - SIAEC | ZFJ0973004 | Provide | CE00296914SNG | 36,SATS MAINTENANCE CENTRE, CHANGI NORTH CRESCENT, 499620 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-11-23 | Closed
| ESD CHANGI - SIAEC |  | Cease | M0682358 | 36,SATS MAINTENANCE CENTRE, CHANGI NORTH CRESCENT, 499620 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | Singnet E
| ESD CHANGI - SIAEC |  | Cease |  | Work Orders to be raised |  |  |  | V edge Device
| ESD CHANGI - SIAEC | ZEV9644007 | Cease | ELITE00171052SNG | 36 CHANGI NORTH CRESCENT Singapore 499620 |  |  |  | SingNet Elite | 2024-04-30 | Open
| ESD CHANGI - SIAEC | ZEV9748007 | Cease | 00171052SNG | 36 CHANGI NORTH CRESCENT Singapore 499620 |  |  |  | CN - Meg@pop Suite Of IP Services | 2024-04-30 | Open
| ESD CHANGI - SIAEC | ZEV9748008 | Cease | 181513018 | 36 CHANGI NORTH CRESCENT Singapore 499620 |  |  |  | TS - FTTH | 2024-04-30 | Open
| KRISLITE @ SIAEC | ZEW2664017 | Provide | SDWP0003400052SNG | 9, #03-00 LOYANG WAY 508722 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-02-22 | Open
| KRISLITE @ SIAEC | ZFJ2259002 | Provide | ETHCE00296901SNG | 9, #03-00 LOYANG WAY 508722 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet ethernet | 2023-12-08 | Closed
| KRISLITE @ SIAEC | ZFJ2460001 | Provide | CE00296901SNG | 9, #03-00 LOYANG WAY 508722 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-12-08 | Closed
| KRISLITE @ SIAEC | ZKQ1431009 | Cease | M0567318 | 9 LOYANG WAY #03-00 |  | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) |  | Singnet E | 2024-04-30 | Open
| KRISLITE @ SIAEC | ZKQ1431010 | Cease |  | Work Orders to be raised |  |  |  | V edge Device | 2024-04-30 | Open
| KRISLITE @ SIAEC | ZEW2664018 | Provide | SDWP0003400053SNG | 9, #03-00 LOYANG WAY 508722 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-02-22 | Open
| KRISLITE @ SIAEC | ZFJ2259003 | Provide | ETHCE00296902SNG | 9, #03-00 LOYANG WAY 508722 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet ethernet | 2023-12-08 | Closed
| KRISLITE @ SIAEC | ZFJ2460002 | Provide | CE00296902SNG | 9, #03-00 LOYANG WAY 508722 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-12-08 | Closed
| KRISLITE @ SIAEC | ZKQ1431010 | Cease | M0669966 | 9 LOYANG WAY #03-00 |  | 38A,KIM CHUAN ROAD.537055 (DCE) |  | Singnet E | 2024-04-30 | Open
| KRISLITE @ SIAEC | ZKQ1431010 | Cease |  | Work Orders to be raised |  |  |  | V edge Device | 2024-04-30 | Open
| KRISLITE @ SIAEC | ZFJ2259001 | Cease | ELITE00171021SNG | 9 LOYANG WAY #03-00 |  |  |  | SingNet Elite | 2024-04-30 | Open
| KRISLITE @ SIAEC | ZFJ2321001 | Cease | 00171021SNG | 9 LOYANG WAY #03-00 |  |  |  | CN - Meg@pop Suite Of IP Services | 2024-04-30 | Open
| KRISLITE @ SIAEC | ZFJ2321002 | Cease | 181426356 | 9 LOYANG WAY #03-00 |  |  |  | TS - FTTH | 2024-04-30 | Open
| KRISSHOP @ SICC2 | ZEW2664031 | Provide | SDWP0003400066SNG | 30,SATS INFLIGHT CATERING, CHANGI NORTH CRESCENT, 499612 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - ConnectPlus IP VPN | 2024-02-29 | Open
| KRISSHOP @ SICC2 | ZFJ6272015 | Provide | ETHCE00296978SNG | 30,SATS INFLIGHT CATERING, CHANGI NORTH CRESCENT, 499612 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | SingNet ethernet | 2023-12-14 | Closed
| KRISSHOP @ SICC2 | ZFJ7294017 | Provide | CE00296978SNG | 30,SATS INFLIGHT CATERING, CHANGI NORTH CRESCENT, 499612 | CG | 722,UPPER CHANGI ROAD EAST #02-00/01 486854 (TSQ) | PL | CN - Meg@pop Suite Of IP Services | 2023-12-14 | Closed
| KRISSHOP @ SICC2 | ZEW2664032 | Provide | SDWP0003400067SNG | 30,SATS INFLIGHT CATERING, CHANGI NORTH CRESCENT, 499612 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - ConnectPlus IP VPN | 2024-02-29 | Open
| KRISSHOP @ SICC2 | ZFJ6272016 | Provide | ETHCE00301230SNG | 30,SATS INFLIGHT CATERING, CHANGI NORTH CRESCENT, 499612 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | SingNet ethernet | 2023-12-14 | Closed
| KRISSHOP @ SICC2 | ZFJ7294018 | Provide | CE00301230SNG | 30,SATS INFLIGHT CATERING, CHANGI NORTH CRESCENT, 499612 | CG | 38A,KIM CHUAN ROAD.537055 (DCE) | CG | CN - Meg@pop Suite Of IP Services | 2023-12-14 | Closed
| KRISSHOP @ SICC2 |  | Cease | SDWP0003400035SHI | Work Orders to be raised |  |  |  | ISR1100 device
| KRISSHOP @ SICC2 | ZFJ6272007 | Cease | ELITE00203859SNG | 30 CHANGI NORTH CRESCENT SATS INFLIGHT CATERING |  |  |  | SingNet Elite | 2024-04-30 | Open
| KRISSHOP @ SICC2 | ZFJ7294007 | Cease | 00203859SNG | 30 CHANGI NORTH CRESCENT SATS INFLIGHT CATERING |  |  |  | CN - Meg@pop Suite Of IP Services | 2024-04-30 | Open
| KRISSHOP @ SICC2 | ZFJ7294008 | Cease | 181478014 | 30 CHANGI NORTH CRESCENT SATS INFLIGHT CATERING |  |  |  | TS - FTTH | 2024-04-30 | Open

## Stakeholder Register
Department | Product | Level 1 | contact details | Level 2 | contact details
Product | SD WAN | Tan Ping Cheng | pingcheng@singtel.com / +65 98451598
| Singnet Ethernet | Ho Yiyi | hoyiyi@singtel.com / +65 65144070
Bid Team |  | Kelvin Lai | kevin.lai@singtel.com | Hong Zhong Cheng | zhongcheng@singtel.com / +65 82999661
Sales Specialist |  | Mindy/Gerardine | mindy.wong@singtel.com / +65 86863765 | Whilmer | ganwhilmer@singtel.com / +65 97878853
Sales |  | David Phoo/ Rucha | davidphoo@singtel.com / +65 83395380 | Alvin Tan | alvintek@singtel.com / +65 68383393
PM |  | Hashim Aslam / Santosh Kumar/ Muhamad Hamizan | hashim@singtel.com / +65 81291179 ¦¦ xv.santoshkumar.moharana@singtel.com | Kairav Mody | kairavmody@singtel.com / +65 91193673
Solution | Singnet Ethernet | Siti Rosimah | siti@singtel.com / +65 97898229 | Niraj Vinod Sinha | nirajs@singtel.com / +65 68382729
| SDWAN | Winston Goh | winstgoh@singtel.com / +65 85188665
ITPM/CTS | ITPM/CTS | Jayanthi / Banjo | jayanthi@singtel.com /+65 96778402 ¦¦ banjo.ysibido@singtel.com | Dincy | dincy.josephorevillo@singtel.com
GSP | GSP | Niranjan Kawde | niranjan.kawde@singtel.com / 08223852009
Service Management |  | Raymond Chew | raymond.chew@singtel.com | Alan Chan
Client | Scoot | Joey Puah/Atul Kumar/ | Atul_Kumar@singaporeair.com.sg | Cheng Tiang Kak | tiangkak_cheng@singaporeair.com.sg
| SIA | Thomas Sum / Qiu Shiguang/Aris | Thomas_SumPY@singaporeair.com.sg ¦¦ ShiGuang_Qiu@singaporeair.com.sg | Cheng Tiang Kak | tiangkak_cheng@singaporeair.com.sg
| SIA EC | James Phee |  | Cheng Tiang Kak | tiangkak_cheng@singaporeair.com.sg
CG exchange controller |  | Zar Tun / Denel Carinugan | zar.tun@singtel.com / 96735196 ¦¦ denel.carinugan@singtel.com / 98196013 | Asarabali Mohamed Saleem | saleema@singtel.com / 85000117
OC exchange controller |  | Asarabali Mohamed Saleem | saleema@singtel.com / 85000117 | Asarabali Mohamed Saleem | saleema@singtel.com / 85000117
BD exchange controller |  | Sanim Bin Selamat | sanimsel@singtel.com / 96635091 | Asarabali Mohamed Saleem | saleema@singtel.com / 85000117
AR exchange controller |  | Asher Lai | asher.lai@singtel.com / 89401396 | Tan Yim Hai Eric | tanyimhai@singtel.com / 81272680
JR exchange controller |  | Faizal | faizal.mdsaleh@singtel.com / 81295237 | Tan Yim Hai Eric | tanyimhai@singtel.com / 81272680
TP exchange controller |  | Freda Andiano | freda.andiano@singtel.com / 81295261 | Asarabali Mohamed Saleem | saleema@singtel.com / 85000117
PL exchange controller |  | Ye Myint | ye.myint@singtel.com / 81294862 | Tan Yim Hai Eric | tanyimhai@singtel.com / 81272680
| POC Name | POC Number | POC Email
CHAI CHEE | Sitihalimatu Ali | 90290460 | SitiHalimatu_Ali@singaporeair.com.sg
| Terrence Chew | 91078150 | Terrence_chewbh@singaporeair.com.sg
ION | Sharon Lee | 65417920 | sharon_lee@singaporeair.com.sg
| Bernadette Yeo | 96558052 | bernadette_yeo@singaporeair.com.sg
ALH GUARD | Alfred Leong | 93878764 | Alfred_Leong@Singaporeair.com.sg
DATAPOST | Steve Lim | 92374889 | steve.lim@datapost.com.sg
Mentor Media | Kriz Phua | 97546589 | kriz_phua@mentormedia.com
Scoot T1 | Joey Puah Gie Ee | 90229292 | joey_puah@flyscoot.com
SMC- SIAEC | Hosoon Tan | 94368719 | hosoon_tan@singaporeair.com.sg
| Alhafiz Azami | 80497605 | alhafiz_azami@singaporeair.com.sg
PTB4 - SIAEC | Hosoon Tan | 94368719 | hosoon_tan@singaporeair.com.sg
Krisshop @ Changi South Lane | Edwin Koh | 65068711 | Edwin_Koh@krisshop.com
| Siti Nur Hawa | 85691804 | siti_nurhawa@krisshop.com
SICC1 | Liz Wee | 65414651 | liz_wee@singaporeair.com.sg
| Sweechoo Tan | 65416263 | sweechoo_tan@singaporeair.com.sg
EC Engine | SooAnn Lim | 93266708 | soonann_lim@singaporeair.com.sg
| Kayliang Koh | 97460899 | kevin.lai@singtel.com
KRISSHOP @ SIGNATURE | Siti Nur Hawa | 85691804 | siti_nurhawa@krisshop.com
LOYANG - SIAEC (SSC-Suppy Centre?) | Siying Png | 91370601 | Siying_Png@singaporeair.com.sg
ALPS - SIAEC | AnnBeng Kang Vincent Leong | 65492060 65415990 | annbeng_kang@singaporeair.com.sg Vincent_Leong@singaporeair.com.sg
ESD CHANGI - SIAEC | WeeKhiang Tay | 97292895 | Weekhiang_Tay@singaporeair.com.sg
KRISLITE @ SIAEC | WeiChien Lim | 82223049 | weichien_lim@singaporeair.com.sg
KRISSHOP @ SICC2 | Patrick Kwang | 65068709 | Patrick_Kwang@krisshop.com

## BOM
Cisco 8200 BOM for all remote sites
Line Number | Part Number | Description | Qty
2 | C8200-1N-4T | Cisco Catalyst C8200-1N-4T Router | 2
2.0.1 | CON-OSP-C82001N4 | SNTC-24X7X4OS Cisco Catalyst C8200 | 2
2.1 | MEM-C8200-8GB | Cisco Catalyst 8200 Edge 8GB memory | 2
2.2 | M2USB-16G | Cisco Catalyst 8000 Edge M.2 USB 16GB | 2
2.3 | CAB-ACU | AC Power Cord (UK), C13, BS 1363, 2.5m | 2
2.4 | C-RFID-1R | Cisco Catalyst 8000 Edge RFID - 1RU | 2
2.5 | C8000-HSEC | U.S. Export Restriction Compliance license for C8000 series | 2
2.6 | C8200-RM-19-1R | Cisco Catalyst 8200 Rack mount kit - 19" 1R | 2
2.7 | NETWORK-PNP-LIC | Network Plug-n-Play Connect for zero-touch device deployment | 2
2.8 | C8200-NIM-BLANK | Cisco Catalyst 8200 Edge NIM Blank | 2
2.9 | C8200-PIM-BLANK | Cisco Catalyst 8200 Edge PIM Blank | 2
2.1 | TE-R-SW | TE agent for IOSXE on Enterprise Routing | 2
2.11 | IOSXE-CTRL-MODE | IOS XE SD-WAN boot up mode for Unified image | 2
2.12 | SC8KBEUK9-176 | UNIVERSAL | 2
2.13 | DNA-P-T1-A-3Y | Cisco DNA Advantage On-Prem Lic 3Y - upto 200M (Aggr, 400M) | 2
2.14 | SVS-PDNA-ADV | Embedded Support for SW - Tiered DNA Advantage On-Prem | 2
2.15 | DSTACK-T1-A | Cisco DNA Advantage Stack - upto 200M (Aggr, 400M) | 2
2.16 | NWSTACK-T1-A | Cisco Network Advantage Stack - upto 200M (Aggr, 400M) | 2
2.17 | SDWAN-UMB-ADV | Cisco Umbrella for DNA Advantage | 2
2.18 | SDWAN-ONPREM-PF | Cisco SDWAN On Prem Deployment Option | 2

## Lessons Learnt
S.No. | Site ID | Description
1
2
3
4
5
6
7
8
9
10